## Slide 1
PROGRESS REPORT
DISTRICT –
REGION
, 2023

## Slide 2: District Overview
Taluka | Category | No. of Schemes |  | Work Order Issued |  | Work In Progress |  | Work Not Started | 
 |  | PMC | TSP | PMC | TSP | PMC | TSP | PMC | TSP
Amgaon | Retro | 5 | 3 | 5 | 3 | 4 | 0 | 1 | 3
 | New | 1 | 18 | 1 | 1 | 1 | 1 | 0 | 0
Deori | Retro | 28 | 6 | 18 | 6 | 9 | 6 | 9 | 0
 | New | 17 | 90 | 17 | 11 | 7 | 8 | 10 | 3
Gondia | Retro | 33 | 13 | 23 | 13 | 11 | 12 | 12 | 1
 | New | 5 | 38 | 5 | 9 | 5 | 7 | 0 | 2
Goregaon | Retro | 29 | 9 | 21 | 9 | 4 | 9 | 17 | 0
 | New | 1 | 70 | 0 | 3 | 0 | 3 | 0 | 0
Morgaon Arjuni | Retro | 21 | 8 | 19 | 8 | 8 | 6 | 11 | 2
 | New | 3 | 28 | 2 | 2 | 0 | 1 | 2 | 1
Sadak Arjuni | Retro | 61 | 2 | 37 | 2 | 12 | 2 | 25 | 0
 | New | 1 | 45 | 1 | 2 | 1 | 1 | 0 | 1
Salekasa | Retro | 20 | 4 | 12 | 4 | 6 | 3 | 6 | 1
 | New | 16 | 60 | 13 | 0 | 2 | 0 | 11 | 0
Tiroda | Retro | 74 | 1 | 56 | 1 | 28 | 1 | 28 | 0
 | New | 9 | 32 | 4 | 3 | 3 | 2 | 1 | 1
Total | Retro | 271 | 46 | 191 | 46 | 82 | 39 | 109 | 7
 | New | 53 | 381 | 43 | 31 | 19 | 23 | 24 | 8
Grand Total |  | 324 | 427 | 234 | 77 | 101 | 62 | 133 | 15
 |  | 751 |  | 311 |  | 163 |  | 148 | 

## Slide 3: Executive Summary Work in Progress Schemes
Taluka | Category | No. of Schemes | No. of Schemes based on Physical Progress % |  |  |  | 
 |  |  | < 25% | 25 < 50% | 50 < 75% | 75 < 100% | Commissioned
Amgaon | Retro | 4 | 2 | 2 | 0 | 0 | 0
 | New | 2 | 1 | 0 | 1 | 0 | 0
Deori | Retro | 15 | 11 | 4 | 0 | 0 | 0
 | New | 15 | 12 | 3 | 0 | 0 | 0
Gondia | Retro | 23 | 19 | 3 | 1 | 0 | 0
 | New | 12 | 9 | 3 | 0 | 0 | 0
Goregaon | Retro | 13 | 9 | 3 | 1 | 0 | 0
 | New | 3 | 3 | 0 | 0 | 0 | 0
Morgaon Arjuni | Retro | 14 | 10 | 3 | 0 | 1 | 0
 | New | 1 | 1 | 0 | 0 | 0 | 0
Sadak Arjuni | Retro | 14 | 13 | 1 | 0 | 0 | 0
 | New | 2 | 2 | 0 | 0 | 0 | 0
Salekasa | Retro | 9 | 6 | 2 | 1 | 0 | 0
 | New | 2 | 1 | 0 | 1 | 0 | 0
Tiroda | Retro | 29 | 25 | 4 | 0 | 0 | 0
 | New | 5 | 2 | 3 | 0 | 0 | 0
Total | Retro | 121 | 95 | 22 | 3 | 1 | 0
 | New | 42 | 31 | 9 | 2 | 0 | 0
Grand Total |  | 163 | 126 | 31 | 5 | 1 | 0

## Slide 4: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
Amgaon Taluka | Amgaon Taluka |  |  |  |  |  |  | 
1 | Kosamtola | Pravin S. Somvanshi | 49,08,003 | 14-10-2022 | 6 Months | 26.11% | - | -
2 | Jambhurtola | Shubham Umesh Sakure | 24,48,351 | 13-10-2022 | 3 Months | 25.12% | - | -
3 | Dhobitola+Makkitola | Anand G. Thakur | 69,99,943 | 16-01-2023 | 10 Months | 1.21% | - | -
4 | Asoli | Pravin S. Somvanshi | 52,84,055 | 14-10-2022 | 8 Months | 0.50% | - | -
Deori Taluka | Deori Taluka |  |  |  |  |  |  | 
5 | Tekabedar | Pravin S. Somvanshi | 36,34,023 | 15-07-2022 | 12 Months | 48.77% | - | -
6 | Ambhora | Rajvir Construction | 66,41,677 | 04-10-2022 | 8 Months | 42.55% | - | -
7 | Saliyatola | Uma Construction | 35,90,798 | 28-07-2022 | 12 Months | 38.86% | - | -
8 | Nawatola (Bharregaon) | Uma Construction | 64,42,399 | 03-01-2023 | 10 Months | 27.98% | - | -
9 | Gawditola | Pravin S. Somvanshi | 15,64,482 | 28-07-2022 | 6 Months | 21.55% | - | -
10 | Devatola | Abhishek K. Jain | 1,37,94,848 | 15-07-2022 | 24 Months | 14.26% | - | -
11 | Ilukchuha | Lokesh Bhandarkar | 9,08,359 | 20-01-2023 | 3 Months | 7.84% | - | -
12 | Rehadi | Pravin S. Somvanshi | 26,01,728 | 28-07-2022 | 12 Months | 6.16% | - | -

## Slide 5: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
13 | Sundaridand | Akash Rajesh Mishra | 12,72,293 | 14-10-2022 | 3 Months | 2.73% | - | -
14 | Lendijob | Lokesh Bhandarkar | 33,24,601 | 11-01-2023 | 6 Months | 1.69% | - | -
15 | Gonditola |  |  |  |  | 1.56% | - | -
16 | Mohantola | Akash Rajesh Mishra | 6,65,011 | 10-10-2022 | 3 Months | 1.24% | - | -
17 | Mohandi | R.P Raut | 35,07,580 | 15-07-2022 | 12 Months | 0.98% | - | -
18 | Purada | Uma Construction | 1,62,28,181 | 03-01-2023 | 15 Months | 0.63% | - | -
19 | Sherdepar | Rajvir Construction | 93,68,111 | 03-01-2023 | 10 Months | 0.04% | - | -
Gondia Taluka | Gondia Taluka |  |  |  |  |  |  | 
20 | Kochewahi | Pravin S. Somvanshi | 49,83,517 | 14-10-2022 | 6 Months | 68.24% | - | -
21 | Chhipiya | Shubham Umesh Sakure | 25,87,657 | 13-10-2022 | 3 Months | 46.25% | - | -
22 | Jagantola | Komal Narayan Katare | 45,09,521 | 13-10-2022 | 6 Months | 27.90% | - | -
23 | Wadgaon | Abhishek K. Jain | 1,06,40,148 | 14-10-2022 | 17 Months | 27.81% | - | -
24 | Bairagitola | Nitesh Kailash Goutam | 12,31,094 | 17-01-2023 | 3 Months | 18.91% | - | -
25 | Marartola | Komal Narayan Katare | 39,68,392 | 14-10-2022 | 6 Months | 15.99% | - | -

## Slide 6: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
26 | Kasa | Komal Narayan Katare | 73,77,681 | 14-10-2022 | 8 Months | 15.05% | - | -
27 | Shivni | Komal Narayan Katare | 31,37,005 | 14-10-2022 | 6 Months | 14.85% | - | -
28 | Banathar | Komal Narayan Katare | 31,42,539 | 14-10-2022 | 6 Months | 14.46% | - | -
29 | Zilmili | Shubham Umesh Sakure | 20,03,035 | 13-10-2022 | 3 Months | 13.53% | - | -
30 | Khatiya | Shalikram D. Lichade | 79,33,402 | 15-07-2022 | 24 Months | 9.52% | - | -
31 | Navargaon Kala | Abhishek K. Jain | 1,26,93,947 | 02-01-2023 | 12 Months | 9.25% | - | -
32 | Gudma & Hetitola | Abhishekh Jain | 84,83,855 | 02-01-2023 | 10 Months | 8.16% | - | -
33 | Wadad | Abhishek K. Jain | 90,55,452 | 03-01-2023 | 10 Months | 4.55% | - | -
34 | Fattepur. | Balaji Builder & Suplyer | 80,08,615 | 18-11-2022 | 12 Months | 2.59% | - | -
35 | Rajegaon | Saburi Construction | 88,44,709 | 02-01-2023 | 10 Months | 2.05% | - | -
36 | Pardiband | Komal Narayan Katare | 74,91,785 | 03-01-2023 | 10 Months | 1.95% | - | -
37 | Khadbanda | Komal Narayan Katare | 66,73,432 | 14-10-2022 | 8 Months | 0.89% | - | -
38 | Dattora | Abhishek K. Jain | 95,18,816 | 02-01-2023 | 10 Months | 0.78% | - | -
39 | Sejgaon | Komal Narayan Katare | 73,86,868 | 03-01-2023 | 10 Months | 0.55% | - | -

## Slide 7: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
40 | Chichtola | Khomesh V. Couragade | 14,91,762 | 25-01-2023 | 3 Months | 0.52% | - | -
41 | Sejgaon Kh | Ms. Saburi Construction Company | 80,93,201 | 03-01-2023 | 10 Months | 0.30% | - | -
42 | Irri | Abhishek K. Jain | 1,38,60,611 | 02-01-2023 | 12 Months | 0.09% | - | -
Goregaon Taluka | Goregaon Taluka |  |  |  |  |  |  | 
43 | Telankhedi | Shubham Umesh Sakure | 2,47,930 | 18-07-2022 | 6 Months | 67.00% | - | -
44 | Bagadband | Mulchand Rajaram Khandvahe | 23,87,380 | 15-07-2022 | 12 Months | 48.27% | - | -
45 | Palkheda | Yogesh Suresh Nagpure | 6,97,344 | 18-07-2022 | 6 Months | 37.63% | - | -
46 | Hiratola+Chanditola | Komal Narayan Katare | 1,15,75,119 | 14-10-2022 | 17 Months | 25.85% | - | -
47 | Satwa | Mulchand Khandwahe | 78,62,992 | 14-10-2022 | 12 Months | 19.26% | - | -
48 | Gauritola(Tilli) | Shalikram D. Lichade | 78,12,183 | 14-10-2022 | 12 Months | 12.50% | - | -
49 | Dawwa | Mulchand Khandwahe | 74,20,702 | 14-10-2022 | 8 Months | 5.67% | - | -
50 | Malpuri | Shubham Jogesh Tivari | 24,78,168 | 14-10-2022 | 3 Months | 4.54% | - | -
51 | Kamargaon | Sabari Construction Company | 91,61,741 | 09-11-2022 | 12 Months | 3.81% | - | -
52 | Chichgaontola | Sabari Construction Company | 95,54,100 | 09-11-2022 | 12 Months | 1.77% | - | -

## Slide 8: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
53 | Ghumara | Mulchand Rajaram Khandwahe | 24,14,790 | 15-07-2022 | 12 Months | 1.61% | - | -
54 | Chichgaon | Sabari Construction Company | 41,73,957 | 09-11-2022 | 6 Months | 1.02% | - | -
55 | Tilli | Shalikram D. Lichade | 55,97,178 | 14-10-2022 | 8 Months | 0.61% | - | -
Moregaon Arjuni Taluka | Moregaon Arjuni Taluka |  |  |  |  |  |  | 
56 | Bori Sawari | Pravin Nanaji Mandape | 13,54,375 | 23-09-2022 | 6 Months | 88.47% | - | -
57 | Mahurkuda | S.R.Jaiswal | 19,90,142 | 15-07-2022 | 6 Months | 31.29% | - | -
58 | Yegaon | Pravin S. Somvanshi | 39,76,692 | 15-07-2022 | 12 Months | 29.00% | - | -
59 | Gawarra | Pravin Nanaji Mandape | 15,10,625 | 12-05-2022 | 6 Months | 28.98% | - | -
60 | Kohalgaon | Yogesh Suresh Nagpure | 9,03,816 | 18-07-2022 | 6 Months | 23.70% | - | -
61 | Bhurshi Tola | S.R. Jaiswal | 29,23,251 | 15-07-2022 | 12 Months | 23.25% | - | -
62 | Ramnagar | Chetan Gulab Nakade | 12,96,365 | 27-09-2022 | 6 Months | 22.40% | - | -
63 | Arattondi | Chetan Gulab Nakade | 21,02,822 | 13-10-2022 | 3 Months | 10.47% | - | -
64 | Vihirgaon Bardya | S.R.Jayswal | 23,84,980 | 15-07-2022 | 12 Months | 5.75% | - | -
65 | Dhabetekdi | Akash Rajesh Mishra | 19,32,550 | 14-10-2022 | 3 Months | 0.70% | - | -

## Slide 9: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
66 | Kanholi | Ms. Sabri Construction Company | 62,48,039 | 09-11-2022 | 8 Months | 0.56% | - | -
67 | Tukumnarayan | Pravin S. Somvanshi | 20,65,215 | 26-07-2022 | 12 Months | 0.49% | - | -
68 | Kanhalgaon | Rajkumar Pardhi/Pardhi Traders | 31,96,474 | 16-01-2023 | 6 Months | 0.28% | - | -
69 | Idla | S.R. Jaiswal | 75,13,829 | 14-10-2022 | 12 Months | 0.26% | - | -
Sadak Arjuni Taluka | Sadak Arjuni Taluka |  |  |  |  |  |  | 
70 | Sindhipar | Pravin S. Somvanshi | 37,67,518 | 14-10-2022 | 6 Months | 40.76% | - | -
71 | Mundritola. | Saburi Construction Company | 45,84,213 | 09-11-2022 | 6 Months | 23.78% | - | -
72 | Dunda | Saburi Construction Company | 49,58,742 | 09-11-2022 | 6 Months | 16.19% | - | -
73 | Thadezari | C.K Construction | 16,09,727 | 15-07-2022 | 6 Months | 7.87% | - | -
74 | Bamhni Sadak | Abhishek K. Jain | 20,66,488 | 15-07-2022 | 12 Months | 1.31% | - | -
75 | Kokanatola | Shubham Umesh Sakure | 7,63,470 | 18-07-2022 | 6 Months | 1.24% | - | -
76 | Murpar Ram | Abhishek K. Jain | 23,17,456 | 15-07-2022 | 12 Months | 1.21% | - | -
77 | Pipari | C.K Construction | 23,65,373 | 15-07-2022 | 12 Months | 1.14% | - | -
78 | Mahuli | Mahesh M. Agrawal | 25,00,008 | 09-11-2022 | 3 Months | 1.10% | - | -

## Slide 10: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
79 | Nainpur | Mahesh M. Agrawal | 22,14,719 | 09-11-2022 | 3 Months | 0.62% | - | -
80 | Ghoti | Pravin S. Somvanshi | 76,16,165 | 01-12-2022 | 12 Months | 0.40% | - | -
81 | Birri | Mohammad Arshad Latif Kuraishi | 16,61,959 | 18-10-2022 | 3 Months | 0.30% | - | -
82 | Mundipar | Mahesh M. Agrawal | 29,79,789 | 09-11-2022 | 3 Months | 0.18% | - | -
83 | Mhaswani | Pravin S. Somvanshi | 01/01/27626 | 03-01-2023 | 10 Months | 0.06% | - | -
Salekasa Taluka | Salekasa Taluka |  |  |  |  |  |  | 
84 | Chinchtola | R.P. Raut | 59,04,117 | 05-08-2022 | 24 Months | 60.01% | - | -
85 | Sherpar | S.R. Jaiswal | 18,69,413 | 15-07-2022 | 6 Months | 47.59% | - | -
86 | Gandhitola,Salaitola,Bhajiyadand. | Anand G. Thakur | 69,38,183 | 18-10-2022 | 8 Months | 36.32% | - | -
87 | Rondha | Pravin S. Somvanshi | 38,66,902 | 14-10-2022 | 6 Months | 24.97% | - | -
88 | Kadhotitola | Pravin S. Somvanshi | 47,07,478 | 14-10-2022 | 6 Months | 21.78% | - | -
89 | Ghonsi | Anand G. Thakur | 43,51,090 | 18-10-2022 | 6 Months | 2.56% | - | -
90 | Surjatola | Komal Narayan Katare | 30,31,451 | 13-10-2022 | 6 Months | 1.01% | - | -
91 | Domatola | Mulchand Khandwahe | 56,45,817 |  | 10 Months | 0.90% | - | -

## Slide 11: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
92 | Kolgrah | Anand G. Thakur | 70,78,874 | 15-07-2022 | 24 Months | 0.54% | - | -
Tiroda Taluka | Tiroda Taluka |  |  |  |  |  |  | 
93 | Bodalkasa | Abhishek K. Jain | 35,32,658 | 15-07-2022 | 12 Months | 43.88% | - | -
94 | Bhimnagar | Shubham Umesh Sakure | 14,81,398 | 02-11-2022 | 6 Months | 40.65% | - | -
95 | Jamuniya | Shalikram D. Lichde | 40,17,135 | 15-07-2022 | 12 Months | 39.66% | - | -
96 | Khopda+Isapur | Komal Narayan Katare | 1,27,31,954 | 14-10-2022 | 17 Months | 27.58% | - | -
97 | Sarra | Yogesh Suresh Nagpure | 26,48,825 | 13-10-2022 | 3 Months | 21.47% | - | -
98 | Mendha | Pravin S. Somvanshi | 53,29,735 | 14-10-2022 | 8 Months | 20.91% | - | -
99 | Nahartola | Abhishek K. Jain | 22,06,189 | 15-07-2022 | 12 Months | 13.99% | - | -
100 | Pindkepar | Premchand S. Khobragade | 32,99,771 | 10-01-2023 | 6 Months | 13.24% | - | -
101 | Bhiwapur | Samadhan Construction | 1,30,66,523 | 30-01-2023 | 12 Months | 12.68% | - | -
102 | Bora+Boratola. | Komal Narayan Katare | 1,32,89,031 | 03-01-2023 | 12 Months | 10.96% | - | -
103 | Paraswada | Komal Narayan Katare | 1,03,52,234 | 03-01-2023 | 12 Months | 10.81% | - | -
104 | Bopesar + Khodgaon | Saburi Construction Company | 96,76,216 | 09-11-2022 | 12 Months | 10.69% | - | -

## Slide 12: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
105 | Malhi | Pravin S. Somvanshi | 54,42,145 | 14-10-2022 | 8 Months | 10.37% | - | -
106 | Sonekhari | Samadhan Construction | 22,08,887 | 15-07-2022 | 12 Months | 9.84% | - | -
107 | Selotpar | S.R. Jaiswal | 83,21,591 | 14-10-2022 | 12 Months | 6.38% | - | -
108 | Satona | Ms Saburi Construction | 73,20,401 | 09-11-2022 | 8 Months | 5.52% | - | -
109 | Barbaspura | Abhishek K. Jain | 70,74,368 | 15-07-2022 | 24 Months | 5.51% | - | -
110 | Bhajepar | Shyamsundar P. Raut | 1,24,23,143 | 09-11-2022 | 17 Months | 4.34% | - | -
111 | Dhiwartola | Premchand S. Khobragade | 9,74,427 | 10-01-2023 | 3 Months | 4.01% | - | -
112 | Silli | Saburi Construction Company | 92,90,875 | 09-11-2022 | 12 Months | 2.24% | - | -
113 | Navezari | S.R.Jaiswal | 53,12,093 | 14-10-2022 | 8 Months | 1.60% | - | -
114 | Berdipar+Khuripar | Sabari Construction Company | 97,16,426 | 09-11-2022 | 12 Months | 1.46% | - | -
115 | Boda | Komal Narayan Katare | 1,03,78,637 | 03-01-2023 | 12 Months | 1.24% | - | -
116 | Karti Bk | R.P. Raut | 1,39,95,645 | 18-01-2023 | 12 Months | 0.71% | - | -
117 | Koylari | Pravin S. Somvanshi | 84,75,831 | 15-07-2022 | 24 Months | 0.59% | - | -
118 | Nimgaon | Samadhan Construction | 50,68,965 | 15-07-2022 | 24 Months | 0.45% | - | -

## Slide 13: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
119 | Sonegaon | Pravin S. Somvanshi | 84,74,382 | 15-07-2022 | 24 Months | 0.25% | - | -
120 | Ghatkuroda | Samadhan Construction | 73,66,540 | 15-07-2022 | 24 Months | 0.05% | - | -
121 | Birsi |  |  |  |  | 0.03% | - | -

## Slide 14: Abstract of Schemes – Work in Progress Category – “New”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
Amgaon Taluka | Amgaon Taluka |  |  |  |  |  |  | 
1 | Thantola | Komal N. Katare | 65,49,751 | 18-07-2022 | 24 Months | 63.61% | - | -
2 | Waghadongri | Komal Narayan Katare | 32,98,800 | 13-10-2022 | 6 Months | 0.09% | - | -
Deori Taluka | Deori Taluka |  |  |  |  |  |  | 
3 | Paurzola | Rajvir Construction | 33,61,940 | 14-10-2022 | 6 Months | 44.01% | - | -
4 | Gadegaon | Rajvir Construction | 72,04,685 | 04-10-2022 | 8 Months | 32.61% | - | -
5 | Kosabi | Akash Rajesh Mishra | 14,49,839 | 14-10-2022 | 3 Months | 28.27% | - | -
6 | Kotjambhura | Uma Construction | 60,40,995 | 18-10-2022 | 8 Months | 22.61% | - | -
7 | Borgaon | Uma Construction | 74,31,892 | 18-10-2022 | 8 Months | 21.46% | - | -
8 | Nakti & Naktitola | R.P Raut | 27,23,774 | 15-07-2022 | 12 Months | 7.22% | - | -
9 | Dhobisarad+Powerhousetoli+Akhartoli | Uma Construction | 1,15,72,712 | 18-10-2022 | 17 Months | 6.75% | - | -
10 | Nilaj | Komal Narayan Katare | 39,02,141 | 13-10-2022 | 6 Months | 3.05% | - | -
11 | Dhanori | Shubham Jogesh Tivari | 9,95,292 | 14-10-2022 | 3 Months | 2.77% | - | -
12 | Sindbiri | Komal Narayan Katare | 39,40,524 | 13-10-2022 | 6 Months | 2.42% | - | -

## Slide 15: Abstract of Schemes – Work in Progress Category – “New”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
13 | Wasani | R.P Raut | 26,54,092 | 15-07-2022 | 12 Months | 1.42% | - | -
14 | Mangezari |  |  |  |  | 0.85% | - | -
15 | Padampur | Rajvir Construction | 58,88,565 | 14-10-2022 | 8 Months | 0.85% | - | -
16 | Bhagi | Uma Construction | 90,89,776 | 28-07-2022 | 24 Months | 0.36% | - | -
17 | Misapiri | Rajvir Construction | 89,10,066 | 03-01-2023 | 10 Months | 0.02% | - | -
Gondia Taluka | Gondia Taluka |  |  |  |  |  |  | 
18 | Pipartola | Pravin S. Somvanshi | 37,42,660 | 15-07-2022 | 12 Months | 40.78% | - | -
19 | Girutola | Pravin S. Somvanshi | 45,57,329 | 15-07-2022 | 24 Months | 34.52% | - | -
20 | Balmatola | Laxminarayan A. Dhapade | 48,81,361 | 15-07-2022 | 24 Months | 25.91% | - | -
21 | Pujaritola | Samadhan Construction | 75,79,923 | 18-10-2022 | 12 Months | 13.06% | - | -
22 | Deutola | Pravin Somvanshi | 78,92,795 | 01-12-2022 | 12 Months | 10.54% | - | -
23 | Chidiyatola | Khomesh V. Chouragade | 33,01,642 | 05-01-2023 | 6 Months | 4.76% | - | -
24 | Kharra | Arvind Construction | 32,80,638 | 18-11-2022 | 6 Months | 3.04% | - | -
25 | Umari | Ms. Saburi Construction Company | 90,20,054 | 03-01-2023 | 10 Months | 1.24% | - | -

## Slide 16: Abstract of Schemes – Work in Progress Category – “New”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
26 | Karutola | Komal Narayan Katare | 52,74,644 | 12-12-2022 | 8 Months | 0.87% | - | -
27 | Birsi(Das) | Komal Narayan Katare | 82,67,412 | 14-10-2022 | 12 Months | 0.75% | - | -
28 | Pangadi | Mohammad Arshad Latif Kureshi | 28,19,153 | 18-10-2022 | 3 Months | 0.46% | - | -
29 | Sonpuri | Shalikram D. Lichde | 84,28,238 | 14-10-2022 | 12 Months | 0.10% | - | -
Goregaon Taluka | Goregaon Taluka |  |  |  |  |  |  | 
30 | Gidhadi | Komal Narayan Katare | 1,72,28,919 | 14-10-2022 | 17 Months | 22.73% | - | -
31 | Gondekhari. | Arvind Construction | 1,44,89,075 | 18-11-2022 | 16 Months | 5.68% | - | -
32 | Gowaritola | Shubham Jogesh Tivari | 28,07,368 | 14-10-2022 | 3 Months | 1.12% | - | -
Moregaon Arjuni Taluka | Moregaon Arjuni Taluka |  |  |  |  |  |  | 
33 | Kanhalgaon | S.R. Jaiswal | 79,71,892 | 14-10-2022 | 12 Months | 1.50% | - | -
Sadak Arjuni Taluka | Sadak Arjuni Taluka |  |  |  |  |  |  | 
34 | Temani | Yogesh Suresh Nagpure | 12,17,569 | 18-07-2022 | 6 Months | 22.30% | - | -
35 | Maneri | Arvind Construction | 27/10/20383 | 18-11-2022 | 8 Months | 21.30% | - | -

## Slide 17: Abstract of Schemes – Work in Progress Category – “New”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
Salekasa Taluka | Salekasa Taluka |  |  |  |  |  |  | 
36 | Mohatola | Komal Narayan Katare | 67,84,144 | 14-10-2022 | 8 Months | 53.26% | - | -
37 | Pathri | Anand G. Thakur | 77,31,430 | 16-01-2023 | 10 Months | 0.50% | - | -
Tiroda Taluka | Tiroda Taluka |  |  |  |  |  |  | 
38 | Ledala | Rajendra Timaji Narnavare | 40,99,045 | 04-10-2022 | 6 Months | 35.63% | - | -
39 | Manora | C.K. Construction | 39,97,579 | 04-10-2022 | 6 Months | 29.88% | - | -
40 | Mendipur | Samadhan Construction | 98,54,445 | 18-11-2022 | 16 Months | 28.65% | - | -
41 | Nawargaon | Samadhan Construction | 94,42,198 | 18-11-2022 | 12 Months | 2.10% | - | -
42 | Baywada | Pravin S. Somvanshi | 23,98,788 | 18-07-2022 | 12 Months | 1.54% | - | -

## Slide 18
Dashboard

## Slide 19
Dashboard
Work Status

## Slide 20
Dashboard
Progress Milestone

## Slide 21
Dashboard
Work Status – “New” Schemes
Work Status – “Retro” Schemes

## Slide 22
MS Project
Work in Progress Schemes

## Slide 23
Sample Site Visit Photos

## Slide 24
Taluka

## Slide 25
Thank You!