## Slide 1
NABARD CONSULTANCY SERVICES
PROGRESS REPORT
DISTRICT: THANE
JAL JEEVAN MISSION
KONKAN REGION
JANUARY 2023

## Slide 2: District Work Status
Taluka | Category | No. of Schemes | Work Order Issued | Work In Progress | Work Not Started

## Slide 3: Executive Summary Work in Progress Schemes
Taluka | Category | Total No. of Schemes | No. of Schemes based on Physical Progress % |  |  |  | 
 |  |  | < 25% | 25 < 50% | 50 < 75% | 75 < 100% | Commissioned

## Slide 4: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
Aurangabad Taluka |  |  |  |  |  |  |  | 
1 | Girnar Tanda | Nilesh Chavan | 12,79,706 | 05-15-2022 | 3 Months | 83.89% | 69.91% | 8.95
2 | Karodi | Shree Satynarayan Sandulal Jajure | 16,06,431 | 28-07-2022 | 3 Months | 67.22% | 60.21% | -
3 | Gangapur Nehari | Shree Mahesh Babanrao Pere | 29,15,304 | 23-01-2023 | 3 Months | 39.30% | - | -
4 | Bhindon | Shree Satyanarayan Sandulal Jajure | 22,83,695 | 07-06-2022 | 3 Months | 35.25% | 35.08% | -
5 | Shindon | Shree Sataynarayan Sandulal Jajure | 31,49,725 | 06-07-2022 | 3 Months | 30.09% | 29.12% | 9.17
6 | Jatwada | Shree Ashok Nanaji Randhe | 33,86,082 | 23-01-2023 | 5 Months | 18.26% | - | -
7 | Pardari & Pardari Tanda | Nilesh Construction | 47,43,303 | 02-01-2023 | 6 Months | 12.83% | 11.47% | 5.44
8 | Kachhighati | Sarpanch , Grampanchayat - Sultanpur | 10,11,937 | 31-03-2022 | 3 Months | 0.92% | - | -
9 | Georai Kuber | Sarpanch, Grampanchayat - Georai Kuber | 11,82,267 | 06-23-2022 | 3 Months | 0.51% | - | -
10 | Shendraban & Gangapur | Shree Yogesh Uttamrao Rathod | 15,63,077 | 12-30-2022 | 6 Months | 0.44% | - | -
11 | Kankora | Sarpanch Grampanchayat - Sarola | 4,35,699 | 23-06-2022 | 3 Months | 0.39% | - | -
12 | Satana | Shree Sudarshan Dilip Bhatane | 15,80,255 | 09-12-2022 | 3 Months | 0.25% | - | -
13 | Pirwadi | Sarpanch , Grampanchayat - Pirwadi | 7,49,071 | 23-06-2022 | 3 Months | 0.23% | - | -

## Slide 5: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
14 | Dudhad | Amogh Dadarao Dakore | 26,53,501 | 01-30-2023 | 6 Months | 0.22% | - | -
15 | Garkheda | Shrimati Punam Tushar Ghodake | 24,05,153 | 30-01-2023 | 6 Months | 0.17% | - | -
16 | Karmad | M/S Khushi Construction | 60,56,627 | 31-01-2023 | 9 Months | 0.17% | - | -
17 | Takli Shimpi&Takli Vaidya | Sarpanch, Grampanchayat - Nipani | 10,88,941 | 28-07-2022 | 3 Months | 0.17% | - | -
18 | Ghardon | Shree Uttamrao Rathod | 50,94,479 | 17-11-2022 | 6 Months | 0.15% | - | -
19 | Daigavhan | M/S Ghuge Construction | 35,96,639 | 22-11-2022 | 3 Months | 0.14% | - | -
20 | Pimpalkhuta & Kanchanpur | M/S S P Construction | 1,20,43,429 | 12-27-2022 | 18 Months | 0.14% | - | -
21 | Bagtalab | Amogh Dadarao Dakore | 17,77,320 | 23-01-2023 | 3 Months | 0.14% | - | -
22 | Patoda | Shree Mahesh Babanrao Pere | 34,73,852 | 20-02-2023 | 3 Months | 0.14% | - | -
23 | Murumkheda | Shree Atul Laxman Jadhao | 62,14,497 | 23-01-2023 | 9 Months | 0.13% | - | -
24 | Donwada | M/S Sparsha Infra | 25,12,467 | 12-30-2022 | 6 Months | 0.11% | - | -
25 | Laygaon | Shree Asaram Govindrao Pawar | 26,72,566 | 23-01-2023 | 5 Months | 0.10% | - | -
26 | Wadkha | Shree Pramod Kakasaheb Kawade | 1,10,98,524 | 30-06-2022 | 18 Months | 0.10% | - | -
27 | Borwadi Tanda | Shree Mangesh Shrichand Rothod | 48,19,118 | 20-02-2023 | 6 Months | 0.10% | - | -

## Slide 6: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs

## Slide 7: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs

## Slide 8: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs

## Slide 9: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs

## Slide 10: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs

## Slide 11: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs

## Slide 12: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs

## Slide 13: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs

## Slide 14: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs

## Slide 15: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs

## Slide 16: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs

## Slide 17: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs

## Slide 18: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs

## Slide 19: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs

## Slide 20: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs

## Slide 21: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs

## Slide 22: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs

## Slide 23: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs

## Slide 24: Abstract of Schemes – Work in Progress Category – “New”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs

## Slide 25: Abstract of Schemes – Work in Progress Category – “New”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs

## Slide 26: Abstract of Schemes – Work in Progress Category – “New”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs

## Slide 27: Abstract of Schemes – Work in Progress Category – “New”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs

## Slide 28: Abstract of Schemes – Work in Progress Category – “New”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs

## Slide 29: Abstract of Schemes – Work in Progress Category – “New”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs

## Slide 30: Abstract of Schemes – Work in Progress Category – “New”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs

## Slide 31: Abstract of Schemes – Work in Progress Category – “New”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs

## Slide 32: Abstract of Schemes – Work in Progress Category – “New”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs

## Slide 33: Abstract of Schemes – Work in Progress Category – “New”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs

## Slide 34: Abstract of Schemes – Work in Progress Category – “New”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs

## Slide 35: Abstract of Schemes – Work in Progress Category – “New”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs

## Slide 36: Abstract of Schemes – Work in Progress Category – “New”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs

## Slide 37: Abstract of Schemes – Work in Progress Category – “New”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs

## Slide 38: Abstract of Schemes – Work in Progress Category – “New”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs

## Slide 39: Abstract of Schemes – Work in Progress Category – “New”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs

## Slide 40: Abstract of Schemes – Work in Progress Category – “New”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs

## Slide 41: Abstract of Schemes – Work in Progress Category – “New”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs

## Slide 42: Abstract of Schemes – Work in Progress Category – “New”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs

## Slide 43: Abstract of Schemes – Work in Progress Category – “New”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs

## Slide 44: Abstract of Schemes – Work Completed Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs

## Slide 45: Abstract of Schemes – Work Completed Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs

## Slide 46: Abstract of Schemes – Work Completed Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs

## Slide 47: Abstract of Schemes – Work Completed Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs

## Slide 48: Abstract of Schemes – Work Completed Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs

## Slide 49: Abstract of Schemes – Work Completed Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs

## Slide 50: Abstract of Schemes – Work Completed Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs

## Slide 51: Abstract of Schemes – Work Completed Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs

## Slide 52: Abstract of Schemes – Work Completed Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs

## Slide 53: Abstract of Schemes – Work Completed Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs

## Slide 54: Abstract of Schemes – Work Completed Category – “New”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs

## Slide 55: Abstract of Schemes – Work Completed Category – “New”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs

## Slide 56: Abstract of Schemes – Work Completed Category – “New”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs

## Slide 57: Abstract of Schemes – Work Completed Category – “New”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs

## Slide 58: Abstract of Schemes – Work Completed Category – “New”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs

## Slide 59: Abstract of Schemes – Work Completed Category – “New”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs

## Slide 60: Abstract of Schemes – Work Completed Category – “New”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs

## Slide 61: Abstract of Schemes – Work Completed Category – “New”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs

## Slide 62: Abstract of Schemes – Work Completed Category – “New”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs

## Slide 63: Abstract of Schemes – Work Completed Category – “New”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs

## Slide 64
DASHBOARD

## Slide 65
Work Status
Dashboard

## Slide 66
Dashboard
Progress Milestone

## Slide 67
Work Status: Taluka Wise
Work Status:
Dashboard

## Slide 68
MS – PROJECT
Work in Progress Schemes

## Slide 69
Project Overview Physical Progress vs Financial Progress vs Time Overrun

## Slide 70
Late Schemes

## Slide 71
SAMPLE SITE VISIT PHOTOS

## Slide 72
, Tal.

## Slide 73
Thank You!