## Slide 1
PROGRESS REPORT
DISTRICT –
REGION
, 2023

## Slide 2: District Overview
Taluka | Category | No. of Schemes |  | Work Order Issued |  | Work In Progress |  | Work Not Started | 
 |  | PMC | TSP | PMC | TSP | PMC | TSP | PMC | TSP
Bhoom | Retro | 27 | 28 | 27 | 27 | 18 | 15 | 9 | 12
 | New | 8 | 9 | 8 | 9 | 4 | 6 | 4 | 3
Kalamb | Retro | 20 | 19 | 20 | 18 | 13 | 15 | 7 | 3
 | New | 8 | 7 | 8 | 7 | 5 | 5 | 3 | 2
Lohara | Retro | 13 | 0 | 13 | 0 | 5 | 0 | 8 | 0
 | New | 2 | 0 | 2 | 0 | 1 | 0 | 1 | 0
Omerga | Retro | 39 | 2 | 39 | 2 | 18 | 0 | 21 | 2
 | New | 11 | 4 | 11 | 4 | 6 | 0 | 5 | 4
Osmanabad | Retro | 20 | 32 | 20 | 29 | 4 | 19 | 16 | 10
 | New | 14 | 18 | 14 | 17 | 7 | 11 | 7 | 6
Paranda | Retro | 34 | 17 | 34 | 17 | 23 | 8 | 11 | 9
 | New | 16 | 3 | 16 | 3 | 10 | 2 | 6 | 1
Tuljapur | Retro | 37 | 31 | 37 | 31 | 19 | 18 | 18 | 13
 | New | 0 | 4 | 0 | 4 | 0 | 4 | 0 | 0
Washi | Retro | 25 | 3 | 25 | 3 | 15 | 0 | 10 | 3
 | New | 6 | 1 | 6 | 1 | 4 | 0 | 2 | 1
Total | Retro | 215 | 132 | 215 | 127 | 115 | 75 | 100 | 52
 | New | 65 | 46 | 65 | 45 | 37 | 28 | 28 | 17
Grand Total |  | 280 | 178 | 280 | 172 | 152 | 103 | 128 | 69
 |  | 458 |  | 452 |  | 255 |  | 197 | 

## Slide 3: Executive Summary Work in Progress Schemes
Taluka | Category | No. of Schemes | No. of Schemes based on Physical Progress % |  |  |  | 
 |  |  | < 25% | 25 < 50% | 50 < 75% | 75 < 100% | Commissioned
Bhoom | Retro | 33 | 28 | 4 | 1 | 0 | 0
 | New | 10 | 10 | 0 | 0 | 0 | 0
Kalamb | Retro | 28 | 18 | 4 | 5 | 1 | 0
 | New | 10 | 5 | 4 | 1 | 0 | 0
Lohara | Retro | 5 | 1 | 4 | 0 | 0 | 0
 | New | 1 | 1 | 0 | 0 | 0 | 0
Omerga | Retro | 18 | 16 | 2 | 0 | 0 | 0
 | New | 6 | 5 | 1 | 0 | 0 | 0
Osmanabad | Retro | 23 | 10 | 7 | 4 | 2 | 0
 | New | 18 | 10 | 7 | 0 | 1 | 0
Paranda | Retro | 31 | 23 | 6 | 1 | 1 | 0
 | New | 12 | 9 | 2 | 0 | 1 | 0
Tuljapur | Retro | 37 | 23 | 10 | 3 | 1 | 0
 | New | 4 | 2 | 2 | 0 | 0 | 0
Washi | Retro | 15 | 11 | 4 | 0 | 0 | 0
 | New | 4 | 1 | 2 | 1 | 0 | 0
Total | Retro | 190 | 130 | 41 | 14 | 5 | 0
 | New | 65 | 43 | 18 | 2 | 2 | 0
Grand Total |  | 255 | 173 | 59 | 16 | 7 | 0

## Slide 4: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
Bhoom Taluka | Bhoom Taluka |  |  |  |  |  |  | 
1 | Bhavanwadi(Sukta) | Sandipan Shahuraj Gund | 13,73,869 | 10-06-2022 | 18 Months | 58.62% | 53.95% | 7.41
2 | Anjansonda | Shubham Kisan Jadhav | 21,59,028 | 10-06-2022 | 18 Months | 44.45% | - | -
3 | Hivarda | Shubham Kisan Jadhav | 14,42,802 | 10-06-2022 | 18 Months | 41.13% | - | -
4 | Devangra | Abadev Baburao Vanve | 63,70,670 | 18-10-2022 | 15 Months | 28.42% | - | -
5 | Ambi | R N Kokate Construction Company | 49,69,389 | 23-06-2022 | 18 Months | 26.31% | - | -
6 | Pathrud | Vanve Abadev Baburao | 41,80,713 | 29-06-2022 | 18 Months | 21.19% | - | -
7 | Gormala | Vikram Sampat Khanvilkar | 10,21,454 | 26-07-2022 | 18 Months | 14.72% | - | -
8 | Lanjeshwar | Ms S V Bhoite | 79,92,150 | 28-10-2022 | 15 Months | 14.66% | - | -
9 | Bavi | Ghodake Namdev Murlidhar | 71,24,055 | 03-11-2022 | 15 Months | 14.65% | - | -
10 | Burundwadi | Vikram Sampat Khanvilkar | 21,24,020 | 30-01-2023 | 15 Months | 13.11% | - | -
11 | Ashta | Rajkumar Shrimant Ghrat | 93,89,128 | 14-10-2022 | 15 Months | 12.51% | - | -
12 | Ganegaon | Ms Soham Construction | 98,08,724 | 05-01-2023 | 15 Months | 8.98% | - | -
13 | Devlali | Mukesh Ankush Ghumre | 1,36,94,433 | 31-01-2023 | 15 Months | 5.71% | - | -

## Slide 5: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
14 | Ulup | Ms. R.D. Construction | 73,22,771 | 21-10-2022 | 15 Months | 1.64% | - | -
15 | Nagewadi | Vaishnavi Balaji Gawli | 33,70,930 | 23-09-2022 | 15 Months | 1.51% | - | -
16 | Kasari | Rajkumar Shrimant Gharat | 57,70,125 | 12-01-2023 | 15 Months | 1.35% | - | -
17 | Wadachi Wadi | B.B. Lahamge | 41,05,719 | 03-10-2022 | 15 Months | 1.19% | - | -
18 | Ghatnandur | Abadev Baburao Vanve | 44,68,741 | 14-10-2022 | 15 Months | 1.02% | - | -
19 | Bhongiri | Sayyad Naushad Shabbir | 31,04,283 | 11-03-2022 | 15 Months | 0.80% | - | -
20 | Bahranpur | Ch. Dnyaneshwar Mauli M S S | 21,21,728 | 06-10-2022 | 18 Months | 0.73% | - | -
21 | Nannajwadi | Daivshala Datta Sathe | 25,25,422 | 18-01-2023 | 15 Months | 0.64% | - | -
22 | Anandwadi | Abadev Baburao Vanve | 84,50,912 | 18-01-2023 | 15 Months | 0.56% | - | -
23 | Wakwad | Ms S A Group Developers | 73,45,063 | 11-01-2023 | 15 Months | 0.44% | - | -
24 | Nipani | R.N. Kokate Construction | 50,46,589 | 07-11-2022 | 15 Months | 0.42% | - | -
25 | Umachiwadi | Aniket Sadashiv Nagargoje | 27,75,750 | 25-01-2023 | 15 Months | 0.42% | - | -
26 | Sadesaangvi | R.N. Kokate Construction | 47,23,888 | 14-10-2022 | 15 Months | 0.40% | - | -
27 | Giralgaon | Abadev Baburao Vanve | 64,46,695 | 31-10-2022 | 15 Months | 0.29% | - | -

## Slide 6: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
28 | Wangi (Bk) | Gopal Construction | 56,25,367 | 06-10-2022 | 15 Months | 0.26% | - | -
29 | Andrud | Ms Aditya Construction | 1,15,38,061 | 25-01-2023 | 15 Months | 0.26% | - | -
30 | Jelja | Ms Sayeem Construction | 63,94,312 | 28-10-2022 | 15 Months | 0.20% | - | -
31 | Ralesangavi | Vanve Abadev Baburao | 66,93,197 | 14-10-2022 | 15 Months | 0.15% | - | -
32 | Ida Pida | Abadev Baburao Vanve | 1,07,24,499 | 14-10-2022 | 15 Months | 0.07% | - | -
33 | Jotibachiwadi | Ms Aditya Construction | 77,02,622 | 15-02-2023 | 15 Months | 0.06% | - | -
Kalamb Taluka | Kalamb Taluka |  |  |  |  |  |  | 
34 | Kherda | Ms Jaibhavni Construction | 55,77,213 | 28-10-2022 | 15 Months | 88.38% | - | -
35 | Bangarwadi | Ms D.S.L. Infra | 63,72,482 | 29-12-2022 | 15 Months | 74.67% | - | -
36 | Hasegaon(Shirdhon) | Aditya Construction | 33,26,826 | 12-10-2022 | 15 Months | 61.08% | 48.97% | 16.29
37 | Deolali | Aditya Construction | 68,83,117 | 27-09-2022 | 15 Months | 61.05% | - | -
38 | Wathwada | Bharat Laxman Ingale | 53,27,367 | 19-08-2022 | 18 Months | 60.70% | 58.41% | 31.12
39 | Uplai | Aditya Construction | 76,89,983 | 10-06-2022 | 18 Months | 57.04% | 56.84% | 43.71
40 | Bhosa | Syed Rashid Sartaj | 16,28,252 | 03-06-2022 | 18 Months | 43.96% | - | -

## Slide 7: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
41 | Yerangaon | Syed Rashid Sartaj | 13,73,788 | 03-06-2022 | 18 Months | 37.18% | - | -
42 | Haldgaon | Kazi Soheluddin Sadik Hussain | 19,69,588 | 10-06-2022 | 15 Months | 29.16% | - | -
43 | Nipani | Ch. Sanvi M S S | 15,41,307 | 03-06-2022 | 18 Months | 27.69% | - | -
44 | Borda | Siddheswar Construction | 69,45,926 | 28-10-2022 | 15 Months | 24.73% | - | -
45 | Athardi | Ms Dattaprasad Construction | 40,13,834 | 22-10-2022 | 15 Months | 23.77% | - | -
46 | Bhogaji | Om Construction | 39,13,744 | 29-06-2022 | 18 Months | 19.55% | - | -
47 | Bhat Sangvi | Che. Mesaai M.S.S.S | 11,80,029 | 05-01-2023 | 15 Months | 18.54% | - | -
48 | Padoli | Sudarshan Baburao Salunke | 26,28,071 | 21-02-2023 | 15 Months | 13.86% | - | -
49 | Bhat Shirapura | Ganesh Samb Vharkat | 63,41,114 | 11-01-2023 | 15 Months | 13.80% | - | -
50 | Wadgaon Shirdhon | Pravin Anandrao Gadle | 81,09,045 | 27-12-2022 | 15 Months | 13.36% | - | -
51 | Tandulwadi | Ms Jaibhavni Construction | 40,65,088 | 28-10-2022 | 15 Months | 11.79% | - | -
52 | Ratnapur | Ganesh Samb Vharkat | 59,73,639 | 11-01-2023 | 15 Months | 9.54% | - | -
53 | Babhalgaon | Sujata Construction | 70,63,443 | 11-01-2023 | 15 Months | 8.99% | - | -
54 | Bahula | Ramrao Shrirang Argade | 34,05,362 | 21-10-2022 | 15 Months | 7.61% | - | -

## Slide 8: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
55 | Malkaranja | Vaishnavi Balaji Gawli | 1,02,84,569 | 31-01-2023 | 15 Months | 5.90% | - | -
56 | Hasegaon (Kej) | M.D.S.L.Infra.Devlopers. | 99,59,783 | 14-10-2022 | 15 Months | 3.67% | - | -
57 | Hingangaon | R D Construction | 37,67,653 | 11-01-2023 | 15 Months | 3.15% | - | -
58 | Khadaki | Ganesh Samb Vharkat | 61,60,596 | 31-01-2023 | 15 Months | 1.15% | - | -
59 | Deodhanora | Ms Siddheshwar Construction | 1,12,39,403 | 14-03-2023 | 15 Months | 0.53% | - | -
60 | Massa (Kh) | Vaishnavi Balaji Gawli | 1,22,80,701 | 31-01-2023 | 15 Months | 0.00% | - | -
61 | Wagholi | Aditya Construction | 48,57,457 | 10-09-2022 | 18 Months | 0.00% | - | -
Lohara Taluka | Lohara Taluka |  |  |  |  |  |  | 
62 | Achaler | Ganesh Engineers And Associates | 1,47,06,061 | 12-01-2023 | 15 Months | 43.26% | - | -
63 | Khed | R.D. Construction | 1,59,18,270 | 27-09-2022 | 15 Months | 42.07% | 32.84% | 52.28
64 | Wadiwadgaon | Suraj Rajendra Devkar | 23,81,363 | 06-10-2022 | 15 Months | 31.60% | 29.84% | 7.11
65 | Bhatangali | Ganesh Engineers And Associates | 1,36,41,940 | 12-01-2023 | 15 Months | 25.22% | 19.64% | 26.79
66 | Toramba | Raghunath Shrinivas Shinde | 47,13,121 | 19-10-2022 | 15 Months | 0.02% | - | -

## Slide 9: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
Omerga Taluka | Omerga Taluka |  |  |  |  |  |  | 
67 | Koral | Amardeep Construction | 1,11,17,851 | 28-10-2022 | 15 Months | 28.93% | 19.61% | 21.80
68 | Kothali | Krushnai Construction | 1,33,37,832 | 21-10-2022 | 15 Months | 26.27% | 26.15% | 34.88
69 | Ekurgawadi | Ganesh Samb Vharkat | 39,26,051 | 29-12-2022 | 15 Months | 22.25% | 15.72% | 6.17
70 | Malikwadi | Ms Patel Construction | 64,53,609 | 31-10-2022 | 15 Months | 20.93% | - | -
71 | Chinchkota | Darshana Shivaji Chavan | 54,10,809 | 19-01-2023 | 15 Months | 19.98% | 16.20% | 8.77
72 | Dabka | Alim Abdul Vijapure | 87,79,195 | 31-10-2022 | 15 Months | 19.68% | - | -
73 | Kadmapur | Pravin Mohanrao Kamble | 43,89,735 | 29-12-2022 | 15 Months | 19.18% | 18.00% | 7.90
74 | Dudhanal | Ch. Hanuman M S S | 21,61,813 | 21-11-2022 | 15 Months | 18.58% | - | -
75 | Kanhali | Ms Patel Construction | 91,88,941 | 31-10-2022 | 15 Months | 18.23% | 14.26% | 13.10
76 | Wagdari | Pruthviraj Shivaji Chavan | 93,14,836 | 18-01-2023 | 15 Months | 17.90% | 16.47% | 15.34
77 | Mahalingraiwadi | Pruthviraj Shivaji Chavan | 68,86,926 | 29-12-2022 | 15 Months | 14.26% | 12.70% | 8.75
78 | Murali | Amardeep Construction | 82,20,403 | 28-10-2022 | 15 Months | 12.63% | - | -
79 | Chandkal | Alim Abdul Vijapure | 37,70,369 | 27-01-2023 | 15 Months | 10.98% | - | -
80 | Malagiwadi | Alim Abdul Vijapure | 51,50,724 | 21-10-2022 | 15 Months | 10.72% | - | -

## Slide 10: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
81 | Dhanora Dagad | Alim Abdul Vijapure | 96,29,179 | 31-10-2022 | 15 Months | 10.64% | - | -
82 | Kesar Jawalga | Krushnai Construction | 1,70,90,550 | 21-10-2022 | 15 Months | 10.45% | 9.45% | 16.15
83 | Kantekur | Ganesh Engineers And Associates | 78,65,585 | 03-11-2022 | 15 Months | 9.51% | - | -
84 | Bhikar Sangvi | Krushnai Construction | 1,07,70,094 | 28-10-2022 | 15 Months | 2.53% | 1.29% | 1.39
Osmanabad Taluka | Osmanabad Taluka |  |  |  |  |  |  | 
85 | Vittalwadi | Khatake Shankar Shesherao | 8,80,114 | 27-07-2022 | 6 Months | 98.55% | - | -
86 | Gaudgaon | Vaishnavi Balaji Gawli | 20,36,692 | 06-03-2022 | 18 Months | 95.76% | 46.25% | 9.42
87 | Mhadewadi | Sarpach/Gramsewak | 5,49,310 | 31-03-2022 | 3 Months | 66.20% | 65.22% | 3.58
88 | Khamaswadi | Ch. Krishna Majur Sahkari Sanstha | 17,39,375 | 03-06-2022 | 18 Months | 57.54% | 36.53% | 6.35
89 | Mulewadi | Swapnil Navnath Naikwadi | 21,21,640 | 03-06-2022 | 18 Months | 53.46% | 46.48% | 9.86
90 | Bhandari | Ms. S A Group Developers | 19,91,008 | 29-06-2022 | 18 Months | 52.18% | - | -
91 | Toramba | Pawan Prakash Swami | 21,16,826 | 23-06-2022 | 18 Months | 46.17% | - | -
92 | Uttami Kayapur | Ch. Krishna Majur Sahkari Sanstha | 17,14,119 | 03-06-2022 | 18 Months | 44.57% | 42.71% | 7.32
93 | Gogaon | Khatake Shankar Shesherao | 8,43,826 | 23-08-2022 | 15 Months | 40.13% | - | -

## Slide 11: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
94 | Ansurda | Ch. Kashtkari M S S | 20,80,646 | 03-05-2022 | 18 Months | 32.62% | - | -
95 | Dakwadi | Ms. S A Group Developers | 12,38,070 | 25-07-2022 | 18 Months | 29.15% | - | -
96 | Takali (B) | Ganesh Samb Vharkat | 44,83,922 | 07-09-2022 | 12 Months | 27.80% | - | -
97 | Walgud | Vinayak Vishwanath Khadke | 21,13,651 | 10-06-2022 | 18 Months | 25.91% | - | -
98 | Pohner | Prashant Prabhakar Mule | 20,50,660 | 05-08-2022 | 18 Months | 17.52% | - | -
99 | Kond | Ch Sangvi M S S | 19,91,075 | 03-06-2022 | 18 Months | 16.17% | - | -
100 | Gopalwadi | Swapnil Navnath Naikwadi | 21,59,692 | 18-06-2022 | 18 Months | 7.58% | - | -
101 | Bamni | Ch. Kashtkari M S S | 21,53,559 | 03-06-2022 | 18 Months | 5.63% | - | -
102 | Bavi | Amrut Pandurang Pawar | 74,84,787 | 14-10-2022 | 15 Months | 1.80% | - | -
103 | Waruda | Ms Jaibhavni Construction | 56,92,147 | 28-10-2022 | 15 Months | 1.54% | - | -
104 | Umaregavhan | Ms N. K. Construction | 73,55,955 | 27-01-2023 | 15 Months | 1.24% | - | -
105 | Patoda | Ghodke Namdev Muralidhar | 1,03,49,589 | 11-01-2023 | 15 Months | 1.20% | - | -
106 | Begada | N.K.Construction | 62,77,054 | 07-10-2022 | 15 Months | 1.20% | - | -
107 | Wagholi | N. D. Construction | 1,53,36,210 | 07-10-2022 | 15 Months | 1.01% | - | -

## Slide 12: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
Parandha Taluka | Parandha Taluka |  |  |  |  |  |  | 
108 | Andori | Sandipan Shahuraj Gund | 21,60,043 | 03-06-2022 | 18 Months | 91.53% | 80.93% | 17.48
109 | Kapilapuri | Atul Bhalchandra Khule | 32,62,706 | 06-10-2022 | 15 Months | 63.34% | 55.41% | 18.08
110 | Bodkha | Ch Dalitoddhar M S S | 17,07,762 | 03-06-2022 | 18 Months | 49.58% | 38.41% | 6.56
111 | Domegaon | Soham Construction | 1,36,68,313 | 21-10-2022 | 15 Months | 44.29% | 32.70% | 44.70
112 | Chinchpur | Ms. Krushnai Construction | 94,53,895 | 12-10-2022 | 15 Months | 38.66% | 32.03% | 30.28
113 | Takmodwadi | Eagle Infra | 29,64,623 | 04-11-2022 | 15 Months | 36.31% | - | -
114 | Kumbheja | Soham Construction | 43,66,627 | 21-10-2022 | 15 Months | 34.78% | - | -
115 | Arangaon | Atul Bhalchandra Khule | 54,49,965 | 19-01-2023 | 15 Months | 28.36% | - | -
116 | Undegaon | Ganesh Samb Vharkat | 54,09,011 | 14-10-2022 | 15 Months | 21.58% | - | -
117 | Pimparkhed | Ms. Krushnai Construction | 56,04,680 | 12-10-2022 | 15 Months | 21.48% | - | -
118 | Lonarwadi | Soham Construction | 48,28,729 | 04-11-2022 | 15 Months | 20.28% | - | -
119 | Malkapur | Ch Dalitoddhar M S S | 21,51,407 | 03-06-2022 | 18 Months | 19.00% | - | -
120 | Pachpimpla | Soham Construction | 54,45,877 | 29-12-2022 | 15 Months | 18.65% | - | -

## Slide 13: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
121 | Bhandgaon | Sayim Construction | 56,19,155 | 10-10-2022 | 15 Months | 15.39% | - | -
122 | Wakadi | Krushnai Construction | 1,01,50,374 | 14-10-2022 | 15 Months | 14.92% | - | -
123 | Rajuri | Soham Construction | 57,81,097 | 31-01-2023 | 15 Months | 13.24% | - | -
124 | Aleshwar | Soham Construction | 61,36,649 | 18-08-2022 | 18 Months | 11.09% | - | -
125 | Rui | Atul Bhalchandra Khule | 55,95,256 | 29-12-2022 | 15 Months | 7.31% | - | -
126 | Wadner | R.D.Construction | 55,96,063 | 10-06-2022 | 15 Months | 3.01% | - | -
127 | Sawardarwadi | Che. Dnyaneshwar Mauli Mss | 23,55,105 | 10-06-2022 | 15 Months | 1.68% | - | -
128 | Yenegaon | Saeem Constrction | 40,40,418 | 26-09-2022 | 15 Months | 1.42% | - | -
129 | Shelgaon | Ms. S A Group Developers | 42,49,986 | 01-02-2023 | 15 Months | 1.33% | - | -
130 | Kukkadgaon | Krushnai Construction | 95,06,141 | 25-01-2023 | 18 Months | 0.80% | - | -
131 | Pandharewadi | Soham Construction | 1,40,88,376 | 19-08-2022 | 15 Months | 0.80% | - | -
132 | Karla | Siddheshwar Construction Company | 36,92,012 | 19-09-2022 | 15 Months | 0.67% | - | -
133 | Dhagpimpri | Vanve Abadev Baburao | 41,99,130 | 14-10-2022 | 15 Months | 0.61% | - | -
134 | Hingangaon Bk | Soham Construction | 1,05,47,414 | 21-10-2022 | 15 Months | 0.50% | - | -

## Slide 14: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
135 | Sakat Bk. | Che. Dnyaneshwar Mauli Mss | 23,88,525 | 10-06-2022 | 15 Months | 0.43% | - | -
136 | Pistamwadi | Ms. Krushnai Construction | 41,39,247 | 17-02-2023 | 15 Months | 0.02% | - | -
137 | Ratnapur | Sachin Kailas Darwase | 60,49,183 | 16-01-2023 | 15 Months | 0.02% | - | -
138 | Kaudgaon | Ravikiran Popat Fuke | 1,12,69,014 | 31-01-2023 | 15 Months | 0.01% | - | -
Tuljapur Taluka | Tuljapur Taluka |  |  |  |  |  |  | 
139 | Wadgaon | Laxman Rangnath Pawar | 21,75,858 | 23-06-2022 | 18 Months | 80.73% | 25.97% | 5.65
140 | Ramtirth | Aditya Construction | 45,27,027 | 07-10-2022 | 15 Months | 65.92% | 64.41% | 29.16
141 | Kadamwadi | Shrikant Ramesh Soni | 34,17,066 | 21-09-2022 | 18 Months | 55.61% | 50.58% | 17.28
142 | Barul | Ms. Siddheshwar Construction Company | 68,19,282 | 03-06-2022 | 18 Months | 52.61% | 33.84% | 23.08
143 | Korewadi | Ch. Kashtakari M S S | 19,55,848 | 18-08-2022 | 18 Months | 44.06% | 21.03% | 4.11
144 | Itkal | Ms. Siddheshwar Construction Company | 49,15,770 | 03-06-2022 | 18 Months | 44.03% | 14.50% | 7.13
145 | Pimpla Bk | Laxman Rangnath Pawar | 20,65,858 | 10-06-2022 | 18 Months | 42.35% | - | -
146 | Arbali | Ms. Siddheshwar Construction Company | 51,65,560 | 09-02-2022 | 18 Months | 40.56% | 4.65% | 2.40
147 | Yamgarwadi | Vishal Construction | 30,71,872 | 03-11-2022 | 15 Months | 36.83% | 10.71% | 3.29

## Slide 15: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
148 | Fulwadi | Ch Dalitoddhar M S S | 21,17,345 | 10-06-2022 | 18 Months | 36.21% | 17.43% | 3.69
149 | Chincholi | Ch Nagraj M S S | 28,14,409 | 31-10-2022 | 15 Months | 28.52% | 21.75% | 6.12
150 | Yewati | Nikhil Nitin Paprikar | 82,87,184 | 29-12-2022 | 15 Months | 27.08% | - | -
151 | Dhangarwadi | Ganesh Samb Vharkat | 75,46,006 | 31-10-2022 | 15 Months | 25.31% | 24.39% | 18.40
152 | Jawalga Mesai | Shrikant Ramesh Soni | 69,88,726 | 21-09-2022 | 15 Months | 25.30% | 11.51% | 8.04
153 | Ghattewadi | Amit Babasaheb Mogarkar | 12,35,236 | 21-07-2022 | 12 Months | 23.45% | - | -
154 | Baswantwadi | Shrikant Ramesh Soni | 92,40,493 | 21-09-2022 | 15 Months | 24.39% | 23.71% | 21.91
155 | Kakrambawdi | Ch Nagraj M S S | 27,75,403 | 21-10-2022 | 15 Months | 14.58% | 8.71% | 2.42
156 | Arali (Kh) | Ms. Siddheshwar Construction | 94,67,506 | 19-01-2023 | 15 Months | 14.45% | 11.01% | 10.42
157 | Jalkotwadi(S) | Shubham Kisan Jadhav | 68,66,833 | 29-12-2022 | 15 Months | 14.42% | - | -
158 | Khanapur | Tejas Agro Irrigation Systrm Pvtltd | 73,69,041 | 31-10-2022 | 15 Months | 14.39% | - | -
159 | Gandhora | Ms. Siddheshwar Construction Company | 74,14,848 | 03-06-2022 | 18 Months | 13.12% | 12.25% | 9.08
160 | Dindegaon | Siddheshwar Construction | 62,88,388 | 21-10-2022 | 15 Months | 12.56% | 12.49% | 7.85
161 | Masla Kh. | Ms. Nirmala Infrastructure | 1,29,11,832 | 14-10-2022 | 15 Months | 12.23% | - | -

## Slide 16: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
162 | Nilegaon | Ms. Siddheshwar Construction Company | 51,43,066 | 03-06-2022 | 18 Months | 12.18% | 6.47% | 3.33
163 | Bornadiwadi | Vaishnavi Balaji Gawli | 82,39,073 | 29-12-2022 | 15 Months | 11.73% | - | -
164 | Gondhalwadi | Shrikant Ramesh Soni | 66,69,789 | 14-10-2022 | 15 Months | 9.83% | - | -
165 | Devsinga | Ms. N K Construction | 80,62,490 | 25-01-2023 | 15 Months | 9.61% | - | -
166 | Wagdari | Ms.N K Construction | 46,50,268 | 19-01-2023 | 15 Months | 7.59% | - | -
167 | Keshegaon | Ms. Siddheshwar Construction Company | 77,53,821 | 03-06-2022 | 18 Months | 6.76% | - | -
168 | Gulhalli | Ms. Siddheshwar Construction Company | 34,38,190 | 03-06-2022 | 18 Months | 1.22% | - | -
169 | Shahapur | Ganesh Samb Vharkat | 94,05,013 | 30-01-2023 | 15 Months | 0.87% | - | -
170 | Gavalewadi | Sonam Kisan Jadhav | 29,14,108 | 25-01-2023 | 15 Months | 0.82% | - | -
171 | Chikundra | Ganesh Samb Vharkat | 1,32,64,503 | 25-01-2023 | 15 Months | 0.75% | - | -
172 | Borgaon | Ms. N K Construction | 65,55,727 | 19-01-2023 | 15 Months | 0.59% | - | -
173 | Katri | Ganesh Samb Vharkat | 67,93,669 | 19-01-2023 | 15 Months | 0.30% | - | -
174 | Sarati | Nitin Nikhil Paprikar | 74,31,354 | 28-10-2022 | 15 Months | 0.30% | - | -
175 | Salgara Maddi | Nitin Nikhil Paprikar | 91,72,591 | 19-01-2023 | 15 Months | 0.27% | - | -

## Slide 17: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
Washi Taluka | Washi Taluka |  |  |  |  |  |  | 
176 | Shendi | Che.Mesai M S S | 28,88,604 | 06-10-2022 | 15 Months | 39.36% | - | -
177 | Shelgaon | Ch. Shri Ganesh M S S | 29,74,230 | 31-10-2022 | 15 Months | 32.04% | - | -
178 | Kanheri | Dalitoddhar M S S | 29,34,149 | 26-09-2022 | 15 Months | 27.74% | - | -
179 | Sonegaon | Ch. Yashwant M S S | 30,49,464 | 28-10-2022 | 15 Months | 26.68% | - | -
180 | Selu | Pravin Anandrao Gadle | 37,00,032 | 15-11-2022 | 15 Months | 21.28% | - | -
181 | Sarola | Vaishnavi Balaji Gawli | 25,95,528 | 23-09-2022 | 15 Months | 13.60% | - | -
182 | Pimpalgaon (K) | B. B. Lahamge | 71,81,703 | 03-10-2022 | 15 Months | 9.23% | - | -
183 | Pimpalgaon (Kamaleshwari) | Mukesh Ankush Ghumre | 64,38,432 | 27-12-2022 | 15 Months | 8.76% | 7.09% | 4.56
184 | Izora | Bharat Laxman Ingale | 42,60,217 | 25-01-2023 | 15 Months | 5.86% | - | -
185 | Fakrabad | Vaishnavi Balaji Gawli | 71,82,638 | 19-10-2022 | 15 Months | 5.77% | - | -
186 | Dahiphal | Ms Siddheshwar Construction | 46,59,986 | 31-01-2023 | 15 Months | 4.84% | - | -
187 | Isrup | Bharat Laxman Ingale | 43,73,423 | 27-01-2023 | 15 Months | 0.59% | - | -
188 | Lonkhas | Ch. Yashwant M S S | 27,53,792 | 19-09-2022 | 15 Months | 0.32% | - | -

## Slide 18: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
189 | Jawalka | Paarth Construction | 45,35,463 | 13-01-2023 | 15 Months | 0.30% | - | -
190 | Bramhagaon | Ms.S.V. Bhoite | 35,44,068 | 28-10-2022 | 15 Months | 0.18% | - | -

## Slide 19: Abstract of Schemes – Work in Progress Category – “New”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
Bhoom Taluka | Bhoom Taluka |  |  |  |  |  |  | 
1 | Ashtewadi | Rajkumar Shrimant Ghrat | 71,39,842 | 13-01-2023 | 15 Months | 13.74% | - | -
2 | Rameshwar | Vanve Abadev Baburao | 75,01,972 | 27-01-2023 | 12 Months | 1.96% | - | -
3 | Krishnapur | Ms. S A Group Developers | 39,77,861 | 19-01-2023 | 15 Months | 0.79% | - | -
4 | Gosaviwadi | Tejas Agro Irrigtion System Lt | 49,34,445 | 29-12-2022 | 15 Months | 0.59% | - | -
5 | Ramkund | Namdev Murlidhar Ghodake | 77,55,591 | 25-01-2023 | 15 Months | 0.54% | - | -
6 | Sawargaon | Sharad Pandit Karle | 60,39,324 | 25-01-2023 | 15 Months | 0.44% | - | -
7 | Antargaon | Rajkumar Shrimant Ghrat | 51,55,490 | 18-01-2023 | 15 Months | 0.33% | - | -
8 | Dokewadi | Ms. S V Bhoite | 1,39,13,394 | 31-10-2022 | 15 Months | 0.31% | - | -
9 | Nali | Tejas Agro Irrigtion System Lt | 50,82,600 | 29-12-2022 | 15 Months | 0.18% | - | -
10 | Bhawanwadi | Abadev Baburao Vanve | 93,83,782 | 18-01-2023 | 15 Months | 0.06% | - | -
Kalamb Taluka | Kalamb Taluka |  |  |  |  |  |  | 
11 | Karanjkalla | R D Construction | 31,86,425 | 03-06-2022 | 18 Months | 74.23% | 73.57% | 23.44
12 | Ekurka | R D Construction | 1,00,36,171 | 29-09-2022 | 15 Months | 47.28% | - | -

## Slide 20: Abstract of Schemes – Work in Progress Category – “New”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
13 | Saudana (Dhoki) | Sayyad Naushad Shabbir | 37,06,588 | 21-10-2022 | 15 Months | 45.44% | - | -
14 | Mangrul | Krushnai Construction | 1,31,42,935 | 03-11-2022 | 15 Months | 34.01% | - | -
15 | Jawala (Kh) | Bharat Laxman Ingale | 79,68,437 | 26-09-2022 | 15 Months | 32.18% | - | -
16 | Lohata (W) | Aditya Construction | 37,59,400 | 06-10-2022 | 15 Months | 23.42% | - | -
17 | Kanherwadi | M.D.S.L.Infra.Devlopers. | 73,50,966 | 29-12-2022 | 15 Months | 10.26% | - | -
18 | Shelgaon Divani | Vaishnavi Balaji Gawli | 63,06,370 | 29-12-2022 | 15 Months | 1.39% | - | -
19 | Govindpur | Aditya Construction | 92,64,593 | 25-01-2023 | 15 Months | 0.84% | - | -
20 | Shelgaon (J) | Bharat Laxman Ingale | 85,88,408 | 21-09-2022 | 12 Months | 0.81% | - | -
Lohara Taluka | Lohara Taluka |  |  |  |  |  |  | 
21 | Mogha (Bk) | Darshana Shivaji Chavan | 82,46,693 | 19-01-2023 | 15 Months | 14.33% | - | -
Omerga Taluka | Omerga Taluka |  |  |  |  |  |  | 
22 | Jagadalwadi | Alim Abdul Vijapure | 88,55,106 | 31-10-2022 | 15 Months | 27.94% | - | -
23 | Dayanand | Paras Construction | 38,03,417 | 25-01-2023 | 15 Months | 23.68% | - | -
24 | Rampur | Amardeep Construction | 73,67,120 | 18-10-2022 | 15 Months | 19.84% | 15.78% | 11.63

## Slide 21: Abstract of Schemes – Work in Progress Category – “New”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
25 | Katewadi | Alim Abdul Vijapure | 73,67,167 | 27-01-2023 | 15 Months | 16.80% | - | -
26 | Babalsur | Darshana Shivaji Chavan | 88,69,640 | 19-01-2023 | 15 Months | 13.11% | 10.46% | 9.28
27 | Matola Kh | Paras Construction | 1,12,28,769 | 25-01-2023 | 15 Months | 0.96% | - | -
Osmanabad Taluka | Osmanabad Taluka |  |  |  |  |  |  | 
28 | Mohatarwadi | Tejas Superstructure Pvt Ltd. | 43,29,240 | 03-06-2022 | 18 Months | 99.43% | 58.18% | 25.19
29 | Samudrawani | Ms. S A Group Developers | 27,67,221 | 23-06-2022 | 18 Months | 46.73% | 46.23% | 12.79
30 | Sarola (Bk) | Ms. Siddheshwar Construction | 89,42,733 | 29-07-2022 | 18 Months | 40.16% | 15.67% | 14.01
31 | Bhikar Sarola | Ms. S A Group Developers | 1,19,15,106 | 29-12-2022 | 15 Months | 36.81% | - | -
32 | Surdi | Amrut Pandurang Pawar | 44,60,810 | 14-10-2022 | 15 Months | 32.99% | - | -
33 | Kawalewadi | Ms. S A Group Developers | 46,07,430 | 03-11-2022 | 15 Months | 27.60% | - | -
34 | Pimpri | Bharat Laxman Ingale | 49,29,745 | 21-09-2022 | 15 Months | 25.79% | - | -
35 | Wadgaon (S) | Jai Bhavani Construction | 1,24,07,575 | 19-06-2022 | 18 Months | 25.15% | - | -
36 | Bukkanwadi | Ms. S A Group Developers | 52,51,029 | 16-09-2022 | 15 Months | 23.65% | - | -
37 | Hingalajwadi | Amrut Pandurang Pawar | 63,91,715 | 26-09-2022 | 15 Months | 21.14% | - | -

## Slide 22: Abstract of Schemes – Work in Progress Category – “New”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
38 | Arani | Amrut Pandurang Pawar | 93,98,123 | 03-06-2022 | 18 Months | 16.11% | - | -
39 | Mendha | Vaishnavi Balaji Gawali | 21,18,274 | 19-09-2022 | 15 Months | 2.57% | - | -
40 | Bhandarwadi | Ms. S A Group Developers | 52,95,537 | 31-10-2022 | 15 Months | 1.83% | - | -
41 | Dautpur | Ms Jaibhavani Construction | 86,13,751 | 28-10-2022 | 15 Months | 1.29% | - | -
42 | Medsinga | Bharat Laxman Ingale | 85,00,945 | 13-03-2023 | 12 Months | 1.16% | - | -
43 | Mahalingi | Prashant Prabhakar Mule | 1,02,52,880 | 25-01-2023 | 15 Months | 1.03% | - | -
44 | Chikhali | Ms Siddheshwar Construction | 1,22,57,100 | 12-01-2023 | 15 Months | 0.72% | - | -
45 | Kini | Ms Jaibhavani Construction | 1,06,40,985 | 31-10-2022 | 15 Months | 0.49% | - | -
Paranda Taluka | Paranda Taluka |  |  |  |  |  |  | 
46 | Shirala | Atul Bhalchandra Khule | 47,63,402 | 12-08-2022 | 18 Months | 90.08% | 82.66% | 39.37
47 | Kokarwadi | B. B. Lahamge | 69,36,926 | 19-09-2022 | 15 Months | 49.07% | 48.07% | 33.35
48 | Andora | Rajkumar Shrimant Gharat | 34,49,318 | 11-01-2023 | 15 Months | 39.05% | - | -
49 | Songiri | Vaishnavi Balaji Gawli | 26,66,250 | 28-10-2022 | 15 Months | 23.18% | - | -
50 | Katrabad | Atish Dattatray Harbhare | 70,78,882 | 29-12-2022 | 15 Months | 19.09% | - | -

## Slide 23: Abstract of Schemes – Work in Progress Category – “New”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
51 | Lakhi | Soham Construction | 55,03,874 | 13-01-2023 | 15 Months | 9.80% | - | -
52 | Wanewadi | Amrut Pandurang Pawar | 30,66,078 | 28-10-2022 | 15 Months | 7.69% | - | -
53 | Rohakal | Soham Construction | 75,08,366 | 18-08-2022 | 18 Months | 5.31% | - | -
54 | Takali | Amrut Pandurang Pawar | 89,90,254 | 14-10-2022 | 15 Months | 4.79% | - | -
55 | Nalgaon | Atul Bhalchandra Khule | 61,56,829 | 12-08-2022 | 18 Months | 1.37% | - | -
56 | Karanja | Amrut Pandurang Pawar | 48,20,674 | 05-01-2023 | 15 Months | 0.88% | - | -
57 | Pithapuri | Amrut Pandurang Pawar | 67,90,375 | 29-12-2022 | 15 Months | 0.73% | - | -
Tuljapur Taluka | Tuljapur Taluka |  |  |  |  |  |  | 
58 | Wanewadi | Ms. Rajharsha Construction | 75,82,147 | 03-06-2022 | 18 Months | 30.31% | 28.16% | 21.35
59 | Babhalgaon | Ms. Siddheshwar Construction Company | 40,30,109 | 03-06-2022 | 18 Months | 25.98% | 5.54% | 2.23
60 | Khotachwadi | Ch Dalitoddhar M S S | 24,99,213 | 03-06-2022 | 18 Months | 17.80% | - | -
61 | Kalegaon | Sanjay Anna Pawar | 31,15,148 | 06-06-2022 | 18 Months | 8.96% | - | -
Washi Taluka | Washi Taluka |  |  |  |  |  |  | 
62 | Dongarewadi | Sayim Construction | 50,20,905 | 26-09-2022 | 15 Months | 50.54% | - | -

## Slide 24: Abstract of Schemes – Work in Progress Category – “New”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
63 | Golegaon | Sumit Construction | 46,97,415 | 06-10-2022 | 15 Months | 36.57% | 31.66% | 14.87
64 | Sarola Mandva | B. B. Lahamge | 39,85,206 | 03-10-2022 | 15 Months | 30.01% | - | -
65 | Khamkarwadi | Mukesh Ankush Ghumre | 77,09,905 | 27-12-2022 | 15 Months | 7.18% | - | -

## Slide 25
Dashboard

## Slide 26
Dashboard
Work Status

## Slide 27
Dashboard
Progress Milestone

## Slide 28
Dashboard
Work Status – “New” Schemes
Work Status – “Retro” Schemes

## Slide 29
MS Project
Work in Progress Schemes

## Slide 30
Sample Site Visit Photos

## Slide 31
Taluka

## Slide 32
Thank You!