## Slide 1
PROGRESS REPORT
DISTRICT – CHANDRAPUR
NAGPUR REGION
MARCH, 2023

## Slide 2: District Overview
Taluka | Category | No. of Schemes |  | Work Order Issued |  | Work In Progress |  | Work Not Started | 
 |  | PMC | TSP | PMC | TSP | PMC | TSP | PMC | TSP
Ballapur | Retro | 0 | 6 | 0 | 6 | 0 | 5 | 0 | 1
 | New | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0
Bhadrawati | Retro | 60 | 19 | 54 | 19 | 19 | 14 | 35 | 5
 | New | 9 | 2 | 8 | 3 | 6 | 0 | 2 | 3
Brahmapuri | Retro | 1 | 5 | 1 | 5 | 1 | 5 | 0 | 0
 | New | 0 | 4 | 0 | 4 | 0 | 4 | 0 | 0
Chandrapur | Retro | 30 | 17 | 27 | 16 | 13 | 11 | 14 | 5
 | New | 4 | 6 | 3 | 6 | 2 | 3 | 1 | 3
Chimur | Retro | 0 | 21 | 0 | 21 | 0 | 21 | 0 | 0
 | New | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0
Gondpipri | Retro | 37 | 12 | 33 | 12 | 25 | 10 | 8 | 2
 | New | 3 | 1 | 3 | 1 | 3 | 0 | 0 | 1
Jiwati | Retro | 27 | 76 | 25 | 66 | 10 | 23 | 15 | 43
 | New | 35 | 9 | 31 | 7 | 16 | 3 | 15 | 4

## Slide 3: District Overview
Taluka | Category | No. of Schemes |  | Work Order Issued |  | Work In Progress |  | Work Not Started | 
 |  | PMC | TSP | PMC | TSP | PMC | TSP | PMC | TSP
Korpana | Retro | 30 | 28 | 29 | 25 | 14 | 10 | 15 | 15
 | New | 6 | 8 | 6 | 8 | 2 | 0 | 4 | 8
Nagbhid | Retro | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 0
 | New | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pombhurna | Retro | 6 | 18 | 6 | 18 | 4 | 16 | 2 | 2
 | New | 4 | 4 | 3 | 4 | 3 | 3 | 0 | 1
Rajura | Retro | 15 | 59 | 14 | 54 | 5 | 31 | 9 | 23
 | New | 7 | 6 | 5 | 5 | 3 | 3 | 2 | 2
Warora | Retro | 1 | 9 | 1 | 9 | 1 | 9 | 0 | 0
 | New | 0 |  |  |  | 0 | 0 | 0 | 0
Total | Retro | 207 | 272 | 190 | 253 | 92 | 157 | 98 | 96
 | New | 68 | 42 | 59 | 40 | 35 | 18 | 24 | 22
Grand Total |  | 275 | 314 | 249 | 293 | 127 | 175 | 122 | 118
 |  | 589 |  | 542 |  | 302 |  | 240 | 

## Slide 4: Executive Summary Work in Progress Schemes
Taluka | Category | No. of Schemes | No. of Schemes based on Physical Progress % |  |  |  | 
 |  |  | < 25% | 25 < 50% | 50 < 75% | 75 < 100% | Commissioned
Ballapur | Retro | 5 | 2 | 2 | 0 | 1 | 0
 | New | 1 | 1 | 0 | 0 | 0 | 0
Bhadrawati | Retro | 33 | 28 | 3 | 1 | 1 | 0
 | New | 6 | 5 | 1 | 0 | 0 | 0
Brahmapuri | Retro | 6 | 2 | 1 | 1 | 2 | 0
 | New | 4 | 2 | 2 | 0 | 0 | 0
Chandrapur | Retro | 24 | 18 | 5 | 1 | 0 | 0
 | New | 5 | 3 | 2 | 0 | 0 | 0
Chimur | Retro | 21 | 2 | 7 | 7 | 5 | 0
 | New | 1 | 1 | 0 | 0 | 0 | 0
Gondpipri | Retro | 35 | 28 | 6 | 1 | 0 | 0
 | New | 3 | 3 | 0 | 0 | 0 | 0
Jiwati | Retro | 33 | 22 | 3 | 3 | 5 | 0
 | New | 19 | 14 | 4 | 0 | 1 | 0

## Slide 5: Executive Summary Work in Progress Schemes
Taluka | Category | No. of Schemes | No. of Schemes based on Physical Progress % |  |  |  | 
 |  |  | < 25% | 25 < 50% | 50 < 75% | 75 < 100% | Commissioned
Korpana | Retro | 24 | 16 | 4 | 2 | 2 | 0
 | New | 2 | 2 | 0 | 0 | 0 | 0
Nagbhid | Retro | 2 | 1 | 1 | 0 | 0 | 0
 | New | 0 | 0 | 0 | 0 | 0 | 0
Pombhurna | Retro | 20 | 16 | 3 | 1 | 0 | 0
 | New | 6 | 6 | 0 | 0 | 0 | 0
Rajura | Retro | 36 | 25 | 5 | 4 | 2 | 0
 | New | 6 | 5 | 0 | 0 | 1 | 0
Warora | Retro | 10 | 1 | 1 | 5 | 3 | 0
 | New | 0 | 0 | 0 | 0 | 0 | 0
Total | Retro | 249 | 161 | 41 | 26 | 21 | 0
 | New | 53 | 42 | 9 | 0 | 2 | 0
Grand Total |  | 302 | 203 | 50 | 26 | 23 | 0

## Slide 6: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
Ballapur Taluka |  |  |  |  |  |  |  | 
1 | Asegaon | Abhejeet Harde | 5,84,947 | 13-06-2022 | 12 Months | 86.35% | - | -
2 | Gilbili | V W Padvaker | 30,16,011 | 03-06-2022 | 15 Months | 33.87% | - | -
3 | Manora&Vishnungar | Deepak Gonewar | 73,25,702 | 31-10-2022 | 17 Months | 28.89% | - | -
4 | Mohali Tukum | Abhijeet Harde | 33,52,848 | 24-11-2022 | 13 Months | 1.86% | - | -
5 | Kothari | P P Construction | 69,71,505 | 31-10-2022 | 17 Months | 0.14% | - | -
Bhadarwati Taluka |  |  |  |  |  |  |  | 
6 | Mohbala | K. R. Bhattad | 12,98,563 | 27-09-2022 | 11 Months | 93.50% | 63.92% | 8.30
7 | Chandankheda(Makta) | Kr Bhattad | 22,87,976 | 31-10-2022 | 11 Months | 50.29% | 40.23% | 9.20
8 | Chaparala | Rehan Ahmad Sheikh Ibrahim | 24,24,582 | 06-07-2022 | 13 Months | 40.58% | 37.52% | 9.10
9 | Ashti Kakade & Ashti Bhadrawati | M.B Construction | 49,73,762 | 01-11-2022 | 14 Months | 35.08% | - | -
10 | Takali | Jyoti Construction Company | 21,03,057 | 22-06-2022 | 15 Months | 25.74% | - | -
11 | Dongargaon | M B Construction | 49,10,852 | 01-11-2022 | 14 Months | 19.13% | 5.73% | 2.81
12 | Ghot Nimbala | Ujwal Construction | 44,97,468 | 21-04-2022 | 15 Months | 19.03% | - | -

## Slide 7: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
13 | Kudrara | Ajayanky Vadelwar | 78,31,211 | 14-12-2022 | 14 Months | 18.26% | - | -
14 | Ralegaon | Anil Gore | 32,16,429 | 07-12-2022 | 10 Months | 17.73% | - | -
15 | Chak Tirwanja | Sumit Biswas | 46,34,363 | 21-04-2022 | 15 Months | 16.23% | 5.12% | 2.37
16 | Pawana Ryyt | Sakshi Mundada | 54,83,102 | 13-01-2022 | 13 Months | 12.88% | - | -
17 | Mangli Rayyatwadi | K R Bhatted | 51,67,040 | 01-11-2022 | 11 Months | 10.45% | - | -
18 | Punwadala | Siraj Daud Shekh | 29,28,576 | 01-10-2022 | 11 Months | 8.77% | - | -
19 | Bhamdeli | Pritam Asutkar | 48,67,131 | 25-01-2023 | 11 Months | 6.86% | - | -
20 | Chalbardi Kondha | Sunil Kadam | 40,86,315 | 07-11-2022 | 15 Months | 6.64% | - | -
21 | Chalbardi Ryt | Sunil Kadam | 42,89,392 | 07-11-2022 | 15 Months | 6.09% | - | -
22 | Vislon | Prakash Construction Company | 16,72,133 | 28-09-2022 | 9 Months | 3.26% | - | -
23 | Chandankheda&3Villages | K R Bhattad | 3,22,79,626 | 31-01-2023 | 11 Months | 3.11% | - | -
24 | Kokewada Tukum | Ramdas Korade | 44,67,043 | 27-01-2023 | 11 Months | 3.11% | - | -
25 | Waigaon Tukum | Shree K R Bharad | 1,91,27,716 | 13-01-2023 | 13 Months | 2.54% | - | -
26 | Manora&Karegaon | K R Bhattad | 1,10,96,884 | 13-01-2023 | 13 Months | 2.12% | - | -

## Slide 8: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
27 | Chora | Mayur Jivtode | 46,53,779 | 01-11-2022 | 13 Months | 0.93% | - | -
28 | Chincholi | K R Bhattad | 2,26,58,751 | 01-11-2022 | 11 Months | 0.88% | - | -
29 | Kunada | New Vilsion Er And Contractor | 32,53,690 | 31-01-2023 | 11 Months | 0.80% | - | -
30 | Kinhala | Pawar Construction | 61,81,949 | 31-01-2023 | 13 Months | 0.64% | - | -
31 | Parodhi | Ujwal Construction | 60,13,923 | 31-01-2023 | 13 Months | 0.48% | - | -
32 | Sonagaon Tukum | Shree Gurudev Transport | 57,58,950 | 21-01-2023 | 12 Months | 0.44% | - | -
33 | Palasgaon | Gurudev Transport | 66,33,843 | 31-01-2023 | 15 Months | 0.36% | - | -
34 | Viloda | Shree Gurudev Transport | 84,24,927 | 25-01-2023 | 14 Months | 0.30% | - | -
35 | Kokewada Manker | Gurudev Travels | 91,10,374 | 24-01-2023 | 12 Months | 0.28% | - | -
36 | Sagara | K R Bhattad | 1,21,71,817 | 13-01-2023 | 13 Months | 0.21% | - | -
37 | Ashta | Pawar Construction | 1,53,76,632 | 31-01-2023 | 13 Months | 0.20% | - | -
38 | Patala | Ram Service | 1,53,60,001 | 27-01-2023 | 13 Months | 0.17% | - | -
Brahmapuri Taluka |  |  |  |  |  |  |  | 
39 | Bhuj Tukum | Vaibhav Gaurkar | 12,46,540 | 29-04-2022 | 8 Months | 86.65% | 85.33% | 10.64

## Slide 9: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
40 | Chak Bothli | Akshay Tidke | 13,20,822 | 11-05-2022 | 8 Months | 76.57% | - | -
41 | Bodada | Pritam Asutkar | 11,61,529 | 21-04-2022 | 8 Months | 63.17% | - | -
42 | Awalgaon | Vilas Sontakke | 1,15,75,499 | 12-10-2022 | 17 Months | 26.27% | - | -
43 | Paradgaon | Ashish N Katekhay | 18,57,428 | 27-09-2022 | 13 Months | 20.86% | - | -
44 | Kahali | Akshay Tidke | 18,17,237 | 05-05-2022 | 8 Months | 20.46% | - | -
Chandrapur Taluka |  |  |  |  |  |  |  | 
45 | Arwat | Sandeep Milmile | 94,17,384 | 08-12-2022 | 17 Months | 72.35% | - | -
46 | Lahuji Nagar | Bangade Madam | 48,99,634 | 26-12-2022 | 13 Months | 42.35% | - | -
47 | Chichpalli | Joyti Construction Company | 69,54,664 | 21-10-2022 | 15 Months | 39.29% | 21.47% | 14.93
48 | Nandgur | M.B Construction | 90,09,071 | 12-07-2022 | 17 Months | 37.23% | 16.18% | 14.58
49 | Junona Rayyatwadi | Deepak Gonewar | 80,81,724 | 11-07-2022 | 15 Months | 30.72% | - | -
50 | Waigaon Mokasa | Priyanka Madhukar Vairagade | 36,32,993 | 31-10-2022 | 15 Months | 27.70% | 17.63% | 6.40
51 | Sakharwahi | P P Construction | 68,01,757 | 31-10-2022 | 17 Months | 24.59% | - | -
52 | Matardevi | Milind Raut | 87,56,845 | 31-10-2022 | 15 Months | 24.01% | - | -

## Slide 10: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
53 | Shinnichor | Sndeep Milmile | 70,08,910 | 13-01-2023 | 13 Months | 23.96% | 18.49% | 12.96
54 | Yerur | Ajay Dhunna | 55,40,268 | 23-01-2023 | 13 Months | 22.14% | - | -
55 | Warwat | Milind Raut | 60,54,287 | 31-10-2022 | 15 Months | 19.15% | 8.55% | 5.18
56 | Sonurli Rith | Sandip Milmile | 60,69,053 | 17-01-2023 | 13 Months | 17.44% | - | -
57 | Vichoda Bu | M. B Construction | 38,43,751 | 12-07-2022 | 11 Months | 14.46% | - | -
58 | Chorgaon | D N Mogare | 57,46,731 | 17-01-2023 | 13 Months | 7.90% | - | -
59 | Karwa | Kanchan B Rohne | 30,22,476 | 31-01-2023 | 11 Months | 7.60% | - | -
60 | Lohara | Abhijeet Matte | 71,62,297 | 13-01-2023 | 13 Months | 4.20% | - | -
61 | Kitadi | Arjun Maske | 1,13,76,033 | 21-01-2023 | 13 Months | 3.72% | - | -
62 | Usgaon | M L Debnath | 84,33,321 | 31-01-2023 | 13 Months | 0.48% | - | -
63 | Wadha | Ankit Pesane | 55,30,268 |  | 13 Months | 0.40% | - | -
64 | Nagala Mahawadi | Asit Adhir Mandal | 78,47,252 | 25-01-2023 | 13 Months | 0.29% | - | -
65 | Shengaon | Eknath Kadam | 11,82,813 | 27-01-2023 | 13 Months | 0.28% | - | -
66 | Pandharwda | M L Debnath | 1,85,52,253 | 31-01-2023 | 15 Months | 0.19% | - | -

## Slide 11: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
67 | Mamla Mokasa | Prakash Engg And Construction | 43,52,132 | 13-01-2023 | 11 Months | 0.17% | - | -
68 | Bhatali | Vaibhav Gorkar | 1,20,54,951 | 31-01-2023 | 13 Months | 0.08% | - | -
Chimur Taluka |  |  |  |  |  |  |  | 
69 | Lawari | Shantaram Chaukhe | 12,22,763 | 21-04-2022 | 11 Months | 99.96% | - | -
70 | Chichala Shastri | Shantaram Chaukhe | 14,14,262 | 21-04-2022 | 8 Months | 96.51% | - | -
71 | Wahangaon | Shrikant Jaiswal | 52,41,438 | 11-11-2022 | 17 Months | 91.62% | 45.69% | 23.95
72 | Rengabodi | Shrikant Jaiswal | 39,90,043 | 11-11-2022 | 17 Months | 76.81% | 76.32% | 30.45
73 | Bothali (Wahangaon | Atul Gore | 70,00,006 | 03-10-2022 | 17 Months | 76.61% | 42.27% | 29.59
74 | Khambala | Kishor Anil Gore | 83,83,734 | 03-11-2022 | 17 Months | 69.21% | 23.82% | 19.97
75 | Khapri (Bhivkund) | Sumit Biswas | 16,58,309 | 03-06-2022 | 13 Months | 63.59% | 47.92% | 7.95
76 | Chinchghat | Shantaram Chuke | 14,14,262 | 21-04-2022 | 8 Months | 62.90% | - | -
77 | Khadsangi | Kishor Gore | 1,38,38,864 | 31-10-2022 | 17 Months | 61.49% | 21.57% | 29.85
78 | Shivpur & Bandar | Shrikant Jaiswal | 79,83,444 | 07-11-2022 | 17 Months | 57.31% | 26.67% | 21.29
79 | Navegaon Peth | Shrikant Jaiswal | 60,06,920 | 11-11-2022 | 17 Months | 54.60% | 39.15% | 23.52

## Slide 12: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
80 | Kolara Tukum | Shree. Gajanan Somaji Udapure | 72,13,547 | 01-11-2022 | 17 Months | 50.52% | - | -
81 | Palasgaon | Shrikant Jaiswal | 1,05,03,488 | 07-11-2022 | 17 Months | 36.48% | 26.23% | 27.55
82 | Wadsi | Shrikant Gopal Jayswal | 61,96,384 | 07-11-2022 | 17 Months | 32.33% | - | -
83 | Jamani | Milind Raut | 34,97,955 | 31-10-2022 | 15 Months | 32.02% | 9.56% | 3.34
84 | Masal Bu | Gajanan Udapure | 84,60,435 | 27-05-2022 | 21 Months | 28.01% | 9.32% | 7.89
85 | Gadgaon | Abhejeet Harde | 33,94,772 | 13-06-2022 | 15 Months | 27.00% | 18.90% | 6.42
86 | Piparda | Shrikant Jaiswal | 77,50,867 | 11-11-2022 | 17 Months | 26.89% | 17.73% | 13.74
87 | Gondeda | Shrikant Gopal Jayswal | 68,86,903 | 11-11-2022 | 15 Months | 26.55% | 15.86% | 10.92
88 | Yerkheda | Shrikant Jaiswal | 31,74,786 | 11-11-2022 | 17 Months | 21.72% | 19.76% | 6.27
89 | Sawarla | Sumit Gowardhan | 52,43,585 | 31-10-2022 | 15 Months | 13.33% | - | -
Gondpipri Taluka |  |  |  |  |  |  |  | 
90 | Undirgaon Rayyyt | Murlidhar Dhadse | 40,58,908 | 04-12-2022 | 11 Months | 61.81% | 33.50% | 13.60
91 | Tarda | Sumit Nilkhant Pulgamkar | 44,01,782 | 21-12-2022 | 11 Months | 47.84% | - | -
92 | Surgaon | Sumit Nilkanth Pulgamkar | 34,00,032 | 24-06-2022 | 13 Months | 46.30% | 26.48% | 9.00

## Slide 13: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
93 | Karanji | Sumit More | 1,40,66,873 | 21-04-2022 | 20 Months | 40.84% | 21.48% | 30.22
94 | Chek Somanpalli | Murlidhar Dhadse | 30,39,724 | 07-12-2022 | 10 Months | 38.91% | 38.46% | 11.69
95 | Check Berdi | Kaushik Yashwantrao Kale | 63,63,226 | 13-12-2022 | 15 Months | 36.20% | - | -
96 | Parsodi | Tarachand Ramchand Deurmalle | 82,75,252 | 21-12-2022 | 15 Months | 31.35% | - | -
97 | Check Pellur | Sairam Infratach | 39,08,965 | 17-01-2023 | 11 Months | 23.46% | - | -
98 | Chak Navegaon And Kirmiri | Sorab Veragade | 93,94,267 | 07-12-2022 | 13 Months | 18.29% | - | -
99 | Chak Gojoli&Gojoli Makta | Ramendra Repti Bala | 1,04,49,202 | 27-01-2023 | 13 Months | 12.75% | - | -
100 | Ganesh Pipri | Ganesh Khardiwar | 82,61,306 | 13-01-2023 | 13 Months | 10.27% | - | -
101 | Bhagarpeth | K R Chintawar | 66,30,912 | 12-01-2023 | 15 Months | 9.99% | - | -
102 | Adegaon | Manish Borkute | 58,91,088 | 08-12-2022 | 15 Months | 9.90% | - | -
103 | Kultha | Sairam Infratach | 35,91,794 | 21-01-2023 | 13 Months | 9.41% | - | -
104 | Sukwashi | Ramendra Repti Bala | 94,97,340 | 31-01-2023 | 13 Months | 8.96% | - | -
105 | Dhamanpeth | Kaushik Yashwantrao Kale | 59,74,529 | 25-01-2023 | 13 Months | 8.25% | - | -
106 | Wejgaon | Murlidhar Chintaman Dhudse | 81,39,310 | 13-01-2023 | 13 Months | 6.12% | - | -

## Slide 14: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
107 | Dhaba&3Villages | Vilas Sontakke | 2,31,06,934 | 21-01-2023 | 11 Months | 5.98% | - | -
108 | Vithal Wada&5 Villages | Anil Narayan Gore | 4,56,97,594 | 31-01-2023 | 15 Months | 5.12% | - | -
109 | Vihirgaon | Sumit Nilkanth Pulgamkar | 44,95,244 | 26-12-2022 | 11 Months | 4.75% | - | -
110 | Kudenandgaon | Sumit Pulgamkar | 46,72,509 | 25-01-2023 | 11 Months | 4.60% | - | -
111 | Salezari | Ramendra Rapti Bala | 90,02,136 | 31-01-2023 | 13 Months | 4.54% | - | -
112 | Bhanareti | Ramendra Bala | 65,38,976 | 31-01-2023 | 13 Months | 2.29% | - | -
113 | Dhannapur&Vyankatpur Chak | Kaushik Kale | 1,04,33,515 | 13-01-2023 | 13 Months | 2.24% | - | -
114 | Chak Likhitwada | Payal Construction | 1,30,77,688 | 31-01-2023 | 13 Months | 1.42% | - | -
115 | Chak Pipri | Ganesh Khardiwar | 78,73,217 | 13-01-2023 | 13 Months | 0.89% | - | -
116 | Nandwardhan | Sai Telicomunication & Construction | 44,957 | 31-01-2023 | 14 Months | 0.73% | - | -
117 | Arvi | Krishna Ramprakash Pipare | 44,903 | 08-12-2023 | 9 Months | 0.66% | - | -
118 | Darur | Murlidhar Chintaman Dhudse | 75,24,642 | 25-01-2023 | 13 Months | 0.45% | - | -
119 | Dubarpeth&Chiwanda | Mohan Namanwar | 84,17,598 | 31-01-2023 | 13 Months | 0.41% | - | -
120 | Chak Darur | Pawar Construction | 1,10,02,169 | 27-01-2023 | 15 Months | 0.28% | - | -

## Slide 15: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
121 | Somanpalli | Kaushik Kale | 1,15,86,040 | 27-01-2023 | 15 Months | 0.27% | - | -
122 | Tarsa Kh | R. G. Deshmukh | 1,68,42,597 | 31-01-2023 | 13 Months | 0.21% | - | -
123 | Panora | Ganesh Khardiwar | 51,30,102 | 13-01-2023 | 13 Months | 0.14% | - | -
124 | Lathi&3Villages | Murlidhar Chintaman | 3,31,66,933 | 31-01-2023 | 13 Months | 0.08% | - | -
Jiwati Taluka |  |  |  |  |  |  |  | 
125 | Lambhori | L. D. Chauhan | 33,63,194 | 21-04-2022 | 15 Months | 98.94% | 79.99% | 26.90
126 | Dhondaarjuni & Gondguda | L. D. Chauhan | 56,01,400 | 21-04-2022 | 17 Months | 97.47% | 67.12% | 37.60
127 | Mahapandharwani | Gangai Construction | 20,28,129 | 21-04-2022 | 15 Months | 93.03% | 26.35% | 5.34
128 | Bhoksapur | Dhondiba Vitthal Shinde | 19,15,886 | 21-04-2022 | 6 Months | 91.67% | 46.28% | 8.87
129 | Devalguda | L. D. Chauhan | 16,04,647 | 21-04-2022 | 9 Months | 89.60% | 84.19% | 13.51
130 | Gadpandharwani | L D Chavan | 70,42,029 | 25-01-2023 | 13 Months | 73.54% | - | -
131 | Krankondi | L D Chauhan | 23,17,584 | 16-01-2023 | 9 Months | 57.10% | - | -
132 | Sitaguda | Dharmsingh Construction | 28,01,100 | 07-12-2022 | 9 Months | 51.04% | 31.52% | 8.83
133 | Ambezari & Hatkarguda | Tarachand Ramdas Deurmalle | 58,55,584 | 29-04-2022 | 19 Months | 43.78% | 42.79% | 25.06

## Slide 16: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
134 | Khadki Hirapur | Balaji Jadhav | 7,99,918 | 21-04-2022 | 3 Months | 40.86% | 21.19% | 1.70
135 | Pataguda | Prasad Narote | 11,85,078 | 09-12-2022 | 6 Months | 26.40% | - | -
136 | Nagapur | Gangai Construction | 28,07,881 | 14-12-2022 | 9 Months | 16.51% | - | -
137 | Loldoh | Balaji Ramu Jadhav | 13,15,544 | 27-05-2022 | 9 Months | 13.31% | 10.29% | 1.35
138 | Labhanguda | L D Chavhan | 35,30,296 | 13-01-2023 | 11 Months | 13.06% | - | -
139 | Anadguda | Shree. Balaji Ramu Jadhav | 17,21,595 | 11-05-2022 | 9 Months | 9.27% | - | -
140 | Asapur | Pritam Asutkar | 35,03,936 | 07-12-2022 | 11 Months | 8.14% | - | -
141 | Pochuguda | Dhodimba V Shinde | 26,09,255 | 09-12-2022 | 9 Months | 7.83% | - | -
142 | Rangharguda | Dhodimba V Shinde | 47,41,930 | 09-12-2022 | 11 Months | 7.27% | - | -
143 | Hatkarguda | Sangmeshwar Earthmovers And Construction | 29,07,017 | 21-01-2023 | 9 Months | 6.76% | - | -
144 | Tadhirapur | Sartaj Construction | 77,22,063 | 08-12-2022 | 14 Months | 5.87% | - | -
145 | Kotha | Gangai Construction | 37,38,418 | 03-06-2022 | 15 Months | 5.15% | - | -
146 | Kolamguda & Lachmaguda | Dhodimba V Shinde | 46,30,594 | 09-11-2022 | 11 Months | 4.77% | - | -
147 | Tumriguda | Pritam Asutkar | 30,95,888 | 07-12-2022 | 11 Months | 4.74% | - | -

## Slide 17: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
148 | Jondleguda | Dhondiba Shinde | 15,04,291 | 31-01-2023 | 9 Months | 4.30% | - | -
149 | Gondguda | Amar Rajur Bhoyar | 30,64,167 | 17-01-2023 | 11 Months | 3.44% | - | -
150 | Belgaon | Sheshrao Maharaj Enterprizes | 54,74,848 | 09-12-2022 | 11 Months | 2.61% | - | -
151 | Yellapur And Yellapur Khurd | Pundalik Girmare | 1,15,15,497 | 31-01-2023 | 13 Months | 2.26% | - | -
152 | Kamlapur | L.D Chauhan | 23,41,262 | 16-01-2023 | 9 Months | 2.18% | - | -
153 | Ghanpather | L D Chavhan | 53,15,889 | 25-01-2023 | 13 Months | 1.89% | - | -
154 | Bhari (Gonguda) | Jagam M Ghule | 33,27,508 | 07-11-2022 | 11 Months | 1.70% | - | -
155 | Kakban | Sangameshwaar Earh Movers And Construction | 30,63,982 | 03-10-2022 | 11 Months | 1.35% | - | -
156 | Chalpatguda | Gangai Construction | 19,22,409 | 27-01-2023 | 9 Months | 1.35% | - | -
157 | Bhimnagar | Shri R.G Desmukh | 70,24,643 | 31-01-2023 | 13 Months | 0.50% | - | -
Korpana Taluka |  |  |  |  |  |  |  | 
158 | Mandwa | Pundalik S Girmaji | 50,76,056 | 03-10-2022 | 15 Months | 86.82% | 85.84% | 43.57
159 | Borgaon | Sandeep Milmile | 43,10,627 | 24-06-2022 | 15 Months | 76.94% | 74.51% | 32.12
160 | Maikalguda | Pritam Asutkar | 11,05,645 | 13-01-2023 | 9 Months | 72.93% | - | -

## Slide 18: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
161 | Kukudbodi | Shiraj Sheikh | 14,71,986 | 01-08-2022 | 8 Months | 72.90% | 22.46% | 3.31
162 | Borgaon Khu | Sandeep Milmile | 43,10,627 | 24-06-2022 | 15 Months | 38.62% | - | -
163 | Dhopatola | Sumit More | 1,22,27,090 | 13-01-2023 | 13 Months | 35.01% | 30.66% | 37.49
164 | Antargaon Bk | `Dhanashree Construction | 48,52,436 | 13-12-2022 | 11 Months | 34.98% | 18.87% | 9.16
165 | Hatloni (Kukudbodi) | Runal M Asutkar | 40,48,242 | 12-07-2022 | 10 Months | 27.08% | - | -
166 | Asan Khurd & Borinavegaon | Ram Services | 94,77,936 | 21-12-2022 | 15 Months | 9.74% | - | -
167 | Kothoda Bk | Shubham Gayakwad | 1,38,94,103 | 31-01-2023 | 13 Months | 9.43% | - | -
168 | Sonurli & Gadgegaon | Jyoti Construction Company | 1,03,84,719 | 19-12-2022 | 17 Months | 7.35% | - | -
169 | Wadgaon | Ram Services | 72,05,137 | 05-08-2022 | 15 Months | 7.32% | - | -
170 | Belgaon | Sumit Jagdish Gowardhan | 15,11,191 | 31-01-2023 | 9 Months | 7.13% | - | -
171 | Parsoda&3 Villages | Shubham Gayakwad | 2,29,15,890 | 27-01-2023 | 13 Months | 6.89% | - | -
172 | Sonurli Wansad | Sandeep Milalile | 1,42,04,160 | 27-01-2023 | 13 Months | 6.20% | - | -
173 | Durgadi | Lokesh Milind Kotrange | 46,87,495 | 12-10-2022 | 17 Months | 4.77% | - | -
174 | Ekodi | Murlidhar Dhulase | 41,51,932 | 27-01-2023 | 11 Months | 3.65% | - | -

## Slide 19: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
175 | Chincholi | Summit Jagdish Gowardhan | 40,84,721 | 27-01-2023 | 11 Months | 2.86% | - | -
176 | Bharosa | Jyoti Construction | 47,23,830 | 31-01-2023 | 11 Months | 2.12% | - | -
177 | Kadholi Kh | Tirth Infotech Services | 66,69,758 | 31-01-2023 | 13 Months | 1.54% | - | -
178 | Jaitapur | Amol Anil Ramteke | 66,33,746 | 31-01-2023 | 13 Months | 1.08% | - | -
179 | Pimpalgaon | Vishal Construction | 1,14,39,657 | 31-01-2023 | 15 Months | 0.62% | - | -
180 | Nokari Pal | Vishal Construction | 1,06,13,964 | 31-01-2023 | 13 Months | 0.34% | - | -
181 | Hirapur | Vishal Construction | 87,05,251 | 31-01-2023 | 13 Months | 0.08% | - | -
Nagbhid Taluka |  |  |  |  |  |  |  | 
182 | Pardi Thawre | Deepak Gonewal | 94,08,977 | 28-07-2022 | 17 Months | 33.53% | - | -
183 | Bikli | Kamlesh Building Material | 19,51,951 | 13-05-2022 | 11 Months | 21.88% | - | -
Pombhurana Taluka |  |  |  |  |  |  |  | 
184 | Umari Potdar & Tukum | Tarachand Deurmalle | 71,95,895 | 29-04-2022 | 19 Months | 54.90% | - | -
185 | Ashta | Vinod Diwse | 29,97,520 | 13-05-2022 | 15 Months | 41.25% | 30.18% | 9.05
186 | Borda Zullurwar | Sumit More | 25,58,340 | 07-11-2022 | 10 Months | 37.75% | - | -

## Slide 20: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
187 | Chintaldhaba | Kaushik Kale | 38,99,567 | 01-06-2022 | 15 Months | 27.54% | 21.93% | 8.55
188 | Chak Ballarpur | Parasnath S.Alone | 28,32,761 | 27-05-2022 | 11 Months | 24.98% | - | -
189 | Dewada | Prajat Burabe | 25,36,916 | 07-06-2022 | 15 Months | 23.01% | - | -
190 | Ambedhanora | Sourav Wairagade | 49,13,205 | 26-12-2022 | 15 Months | 20.10% | 18.10% | 8.89
191 | Pipri Deshpande | Kaushik Kale | 1,25,19,412 | 27-01-2023 | 13 Months | 13.02% | - | -
192 | Chek Hattibodi | Tarachand Deurmalle | 53,95,997 | 21-12-2022 | 11 Months | 7.39% | - | -
193 | Dewai | M K Vairagade | 66,41,922 | 25-01-2023 | 13 Months | 6.08% | - | -
194 | Dongarhaldi Mal Lachmapur | Dhananjay Khade | 48,62,664 | 23-01-2023 | 14 Months | 5.85% | - | -
195 | Satara Komti | Kaushak Kade | 15,94,927 | 01-06-2022 | 9 Months | 4.36% | - | -
196 | Chekthana & Thana Wasana Mal | Sumit More | 1,43,11,885 | 13-01-2023 | 13 Months | 4.10% | - | -
197 | Ghanoti 2 | Avinash Maska | 10,54,254 | 07-11-2022 | 9 Months | 1.58% | - | -
198 | Sonapur | Swapnil Kade | 45,61,351 | 13-01-2023 | 11 Months | 0.70% | - | -
199 | Jungaon | T K Construction | 57,81,582 | 01-08-2022 | 15 Months | 0.44% | - | -
200 | Gangapur Navin | Tarachand Deurmale | 62,12,325 | 21-12-2022 | 13 Months | 0.37% | - | -

## Slide 21: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
201 | Dighori | Kaushik Kade | 1,31,64,103 | 27-01-2023 | 13 Months | 0.23% | - | -
202 | Dongarhaldi Tukum | Tanmay Shetey | 1,07,98,770 | 31-01-2023 | 14 Months | 0.21% | - | -
203 | Ghanoti Tukum | Swapniil Kade | 64,86,180 | 13-01-2023 | 13 Months | 0.07% | - | -
Rajura Taluka |  |  |  |  |  |  |  | 
204 | Sirsi | Gajanan Somaji Udapur | 5,82,146 | 25-08-2022 | 5 Months | 97.46% | - | -
205 | Dhidshi | Rakesh Paradkar | 5,24,096 | 28-09-2022 | 6 Months | 79.76% | - | -
206 | Hardona Bu | Dharmasingh Parsuram | 15,94,988 | 24-06-2022 | 11 Months | 71.06% | 67.62% | 10.79
207 | Goyegaon | Pravin Khadse | 8,24,693 | 23-11-2022 | 8 Months | 69.57% | - | -
208 | Chincholi Bk | Shree. Dattu Shankar Chafle | 26,47,730 | 31-10-2022 | 11 Months | 62.19% | - | -
209 | Siddheshwar | Sanjay Daud | 6,98,899 | 28-09-2022 | 8 Months | 54.18% | 52.69% | 3.68
210 | Dhanora | Dharmasingh Parsuram | 22,50,977 | 24-06-2022 | 13 Months | 41.58% | 40.78% | 9.18
211 | Murti | Dattu Chafale | 2765931 | 11-10-2022 | 13 Months | 40.52% | - | -
212 | Sakhari | Deepak Gonewar | 1035129 | 23-08-2022 | 8 Months | 37.65% | - | -
213 | Subbai | Datta Chapale | 19,01,362 | 13-01-2023 | 13 Months | 36.02% | - | -

## Slide 22: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
214 | Chincholi Khu | Mayur Jiwtode | 1448448 | 01-09-2022 | 9 Months | 29.05% | - | -
215 | Aheri |  | 12359641 | 31-01-2023 | 13 Months | 10.24% | - | -
216 | Virur | K.R Bhattad | 13822218 | 31-10-2022 | 19 Months | 9.91% | 9.60% | 13.27
217 | Bhendavi | Omkar Aswale | 2441425 | 10-08-2022 | 11 Months | 9.62% | - | -
218 | Mathra | K M Dev | 7512169 | 31-01-2023 | 13 Months | 7.63% | - | -
219 | Kawadagondi | Jagan Ghule | 2001949 | 03-10-2022 | 12 Months | 7.43% | - | -
220 | Chunala | S D Construction | 16,09,545 | 05-12-2022 | 11 Months | 6.90% | - | -
221 | Arvi | Sandip Milmile | 11668567 | 24-01-2023 | 13 Months | 6.84% | - | -
222 | Tummaguda Kh | Datta Chaple | 1901362 | 13-01-2023 | 11 Months | 6.82% | - | -
223 | Antargaon | Shambhukumar Khedekar | 6570221 | 27-01-2023 | 13 Months | 6.09% | - | -
224 | Satri | Sandeep Milmile | 3457465 | 27-01-2023 | 11 Months | 5.67% | - | -
225 | Warud Road | Santosh Pawde | 8529360 | 27-01-2023 | 13 Months | 4.31% | - | -
226 | Bailampur | L D Chauhan Construction | 3934292 | 24-01-2023 | 11 Months | 4.20% | - | -
227 | Khambada | Kk Construction | 9303393 | 31-01-2023 | 13 Months | 3.59% | - | -

## Slide 23: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
228 | Chichbodi | Rahul Betwar | 6800119 | 27-01-2023 | 13 Months | 2.94% | - | -
229 | Jamani | Kk Construction | 6551397 | 27-01-2023 | 13 Months | 2.70% | - | -
230 | Bhendala | K K Construction | 7164440 | 27-01-2023 | 13 Months | 2.64% | - | -
231 | Chandanwahi&Naiknagar | M K Dev | 9666049 | 31-01-2023 | 13 Months | 2.37% | - | -
232 | Bamanwada | K R Bhattad | 23562971 | 31-01-2023 | 15 Months | 2.18% | - | -
233 | Sonurli | Shubhamkumar Khedekar | 13640505 | 27-01-2023 | 13 Months | 1.82% | - | -
234 | Koshtala | Dhsneshree Construction | 5046253 | 31-01-2023 | 13 Months | 1.57% | - | -
235 | New Beradi | Bhanupratap Enterprices | 4646641 | 31-01-2023 | 11 Months | 1.29% | - | -
236 | Kalamana | Kk Construction | 7329374 | 27-01-2023 | 13 Months | 1.08% | - | -
237 | Chanakha | A K Construction | 7294815 | 23-11-2022 | 15 Months | 0.84% | - | -
238 | Muthra | Kk Construction | 69,09,987 | 27-01-2023 | 13 Months | 0.42% | - | -
239 | Pachgaon | Mangesh Dongare | 14712686 | 31-01-2023 | 15 Months | 0.30% | - | -
Warora Taluka |  |  |  |  |  |  |  | 
240 | Ajangaon | Nikhil Thakre | 18,61,010 | 21-04-2022 | 9 Months | 91.93% | 48.89% | 9.1

## Slide 24: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
241 | Mohabala | Vilas Sontakke | 52,78,156 | 03-10-2022 | 15 Months | 80.68% | - | -
242 | Waghnakh | Nikhil Thakre | 36,66,505 | 17-06-2022 | 11 Months | 75.90% | 48.28% | 17.7
243 | Marda | Sorabh Veragade | 32,43,692 | 03-10-2022 | 11 Months | 71.15% | 39.79% | 12.91
244 | Nagri | Nikhil Thakre | 39,65,505 | 20-06-2022 | 11 Months | 60.48% | 44.03% | 17.46
245 | Belgaon | Nikhil Thakre | 18,88,754 | 11-05-2022 | 9 Months | 57.30% | 45.95% | 8.68
246 | Barwha | Pawan Bopanwar | 41,41,878 | 24-11-2022 | 14 Months | 54.45% | 49.89% | 20.66
247 | Arjuni | Nikhil Thakare | 20,77,744 | 03-10-2022 | 11 Months | 50.35% | - | -
248 | Wadgaon Arvi | Nikhil Thakare | 18,33,040 | 24-05-2022 | 9 Months | 48.25% | - | -
249 | Atmurdi | Sumit Pulgamkar | 29,18,644 | 28-12-2022 | 11 Months | 21.07% | - | -

## Slide 25: Abstract of Schemes – Work in Progress Category – “New”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
Ballapur Taluka |  |  |  |  |  |  |  | 
1 | Katoli Bamni | Pp Construction | 69,71,505 | 31-10-2022 | 17 Months | 8.82% | - | -
Bhadarwati taluka |  |  |  |  |  |  |  | 
2 | Kawadi | Ram Services | 54,56,487 | 24-01-2023 | 13 Months | 48.29% | - | -
3 | Nandori Kh | Ramdas Korade | 90,30,440 | 25-01-2023 | 13 Months | 0.77% | - | -
4 | Belora | Rahim Shekh | 33,79,140 | 25-01-2023 | 10 Months | 0.65% | - | -
5 | Telwasa | New Vision Engg And Cinstruction | 42,61,168 | 31-01-2023 | 11 Months | 0.53% | - | -
6 | Nandori Bk(Indiranagar) | Ashutosh Kale | 1,49,65,812 | 31-01-2023 | 13 Months | 0.17% | - | -
7 | Katwal Bhagat | Gurudav Transport | 89,44,660 | 21-01-2023 | 17 Months | 0.09% | - | -
8 | Padmapur | Amol M Sukare | 31,18,658 | 17-06-2022 | 17 Months | 36.49% | 35.62% | 11.11
9 | Ekara | Asit Adit Mandal | 85,91,380 | 13-09-2022 | 16 Months | 28.30% | - | -
10 | Chincholi (Bk) | Shilesh Jayshwal | 1,17,83,108 | 31-10-2022 | 19 Months | 23.02% | - | -
11 | Navegaon Makta | Shailesh Jaiswal | 79,03,957 | 31-10-2022 | 19 Months | 11.98% | - | -

## Slide 26: Abstract of Schemes – Work in Progress Category – “New”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
Chandrapur Taluka |  |  |  |  |  |  |  | 
12 | Ajaypur | Joiti Construction Company | 64,95,585 | 31-10-2022 | 15 Months | 38.08% | 34.01% | 22.09
13 | Anturla | Lokesh Kotrange | 53,30,727 | 01-11-2022 | 14 Months | 32.11% | - | -
14 | Lakhmapur | Sumit More | 1,52,20,540 | 07-11-2022 | 17 Months | 15.92% | - | -
15 | Masala Tukum | Kanchan B Rohne | 33,22,896 | 31-01-2023 | 11 Months | 0.63% | - | -
16 | Navin& Payali | Sumit More | 11,50,27,785 | 31-01-2023 | 13 Months | 0.17% | - | -
Chimur Taluka |  |  |  |  |  |  |  | 
17 | Bhivkund | Shrikant Jaiswal | 41,95,305 | 11-11-2022 | 17 Months | 14.06% | - | -
Gondpipri Taluka |  |  |  |  |  |  |  | 
18 | Navin Podsa | Manisha P Borkute | 51,83,285 | 13-01-2023 | 13 Months | 21.21% | - | -
19 | Korambi | Ramendra Repti Bala | 68,67,731 | 31-01-2023 | 13 Months | 7.55% | - | -
20 | Gadholi | K. R. Chintawar | 82,14,640 | 31-01-2023 | 13 Months | 0.36% | - | -
Jiwati Taluka |  |  |  |  |  |  |  | 
21 | Sonerguda | L.D Chavhan | 10,87,423 | 13-01-2023 | 11 Months | 99.13% | - | -
22 | Wani | `Sangameshwar Earth Movers | 65,29,960 | 13-01-2023 | 13 Months | 41.89% | - | -

## Slide 27: Abstract of Schemes – Work in Progress Category – “New”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
23 | Kamatguda(Chikali Khurd) | Gangai Construction | 35,61,440 | 14-12-2022 | 11 Months | 37.08% | - | -
24 | Gattedsguda | Shri Balalji Ramu Jadhav | 21,39,775 | 27-01-2023 | 9 Months | 30.60% | - | -
25 | Dharmaram | Shri Balaji Ammu Jadhav | 29,60,228 | 21-01-2023 | 9 Months | 25.71% | - | -
26 | Gondguda Kolamguda | Gangai Construction | 34,53,150 | 27-01-2023 | 11 Months | 24.48% | - | -
27 | Mangguda | Gangai Construction | 35,66,799 | 30-01-2023 | 13 Months | 15.46% | - | -
28 | Lakhmapur | Gangai Construction | 20,04,358 | 31-01-2023 | 17 Months | 14.36% | - | -
29 | Malguda | Gangai Construction | 64,34,519 | 27-01-2023 | 13 Months | 12.29% | - | -
30 | Babapur | Sangmeswar Earthmovers And Construction | 41,37,796 | 21-01-2023 | 11 Months | 6.12% | - | -
31 | Gondpur | Dhodimba Shinde | 39,69,934 | 09-12-2022 | 10 Months | 5.63% | - | -
32 | Chopanguda | Dhodimbe Shinde | 34,01,635 | 27-01-2023 | 11 Months | 5.30% | - | -
33 | Macchiguda(Bhari) | Gangai Constructon | 18,67,617 | 27-01-2023 | 13 Months | 4.66% | - | -
34 | Rahpalli | Jagan Ghule | 54,08,787 | 27-01-2023 | 13 Months | 2.98% | - | -
35 | Shedwahi | Eknath Namdev Kadam | 52,88,081 | 27-01-2023 | 13 Months | 2.97% | - | -
36 | Chinnuoatilguda | L D Chavhan | 64,66,202 | 25-01-2023 | 13 Months | 2.48% | - | -

## Slide 28: Abstract of Schemes – Work in Progress Category – “New”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
37 | Punaguda | Sheshnag Maharaj Enterprizes | 57,88,550 | 21-11-2022 | 15 Months | 2.20% | - | -
38 | Khadki Raipur | Gangai Construction | 26,55,137 | 27-01-2023 | 9 Months | 1.65% | - | -
39 | Buddagudda | Shri Jagan Madhulkar Ghule | 44,37,013 | 26-12-2022 | 11 Months | 0.70% | - | -
Korpana Taluka |  |  |  |  |  |  |  | 
40 | Mehandi | Dhaneshree Construction | 11,02,767 | 16-01-2023 | 12 Months | 9.10% | - | -
41 | Chopan | Dhaneshree Construction | 56,18,106 | 31-01-2023 | 11 Months | 5.95% | - | -
Pombhurana Taluka |  |  |  |  |  |  |  | 
42 | Chek Khapri | Koshik Kade | 93,74,956 | 13-12-2022 | 15 Months | 19.32% | - | -
43 | Gangapur Chak | Vinod Diwase | 49,93,823 | 21-01-2023 | 15 Months | 12.09% | - | -
44 | Chak Borgaon Rith | Tarachand Durmare | 60,23,327 | 27-01-2023 | 15 Months | 10.07% | - | -
45 | Chak Bamani | Pawar Construction | 52,21,263 | 16-01-2023 | 13 Months | 8.56% | - | -
46 | Bhimni | Jyoti Construction Company | 1,00,31,568 | 13-12-2022 | 15 Months | 8.08% | - | -
47 | Ambai Tukum | Savita Bhurse | 43,58,460 | 13-12-2022 | 11 Months | 0.50% | - | -

## Slide 29: Abstract of Schemes – Work in Progress Category – “New”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
Rajura Taluka |  |  |  |  |  |  |  | 
48 | Amrutguda | Datta Chafle | 8,69,008 | 31-01-2023 | 9 Months | 86.14% | - | -
49 | Janguguda | Sana Constructiom | 4804239 | 31-01-2023 | 11 Months | 20.64% | - | -
50 | Shantinagar | V W Padvrkar | 1588097 | 17-01-2023 | 11 Months | 16.12% | - | -
51 | Navegaon | Dharma Singh Uike | 2887258 | 25-01-2023 | 9 Months | 4.59% | - | -
52 | Botgaon | Kk Construction | 7625111 | 31-01-2023 | 13 Months | 3.16% | - | -
53 | Saleguda&Balegaon | A K Construction | 6369254 | 27-01-2023 | 13 Months | 3.11% | - | -

## Slide 30
Dashboard

## Slide 31
Dashboard
Work Status

## Slide 32
Dashboard
Progress Milestone

## Slide 33
Dashboard
Work Status – “New” Schemes
Work Status – “Retro” Schemes

## Slide 34
MS Project
Work in Progress Schemes

## Slide 35
Sample Site Visit Photos

## Slide 36
Taluka

## Slide 37
Thank You!