## Slide 1
PROGRESS REPORT
DISTRICT –
REGION
, 2023

## Slide 2: District Overview
Taluka | Category | No. of Schemes |  | Work Order Issued |  | Work In Progress |  | Work Not Started | 
 |  | PMC | TSP | PMC | TSP | PMC | TSP | PMC | TSP
 | Retro |  |  |  |  |  |  |  | 
 | New |  |  |  |  |  |  |  | 
 | Retro |  |  |  |  |  |  |  | 
 | New |  |  |  |  |  |  |  | 
 | Retro |  |  |  |  |  |  |  | 
 | New |  |  |  |  |  |  |  | 
 | Retro |  |  |  |  |  |  |  | 
 | New |  |  |  |  |  |  |  | 
 | Retro |  |  |  |  |  |  |  | 
 | New |  |  |  |  |  |  |  | 
Total | Retro |  |  |  |  |  |  |  | 
 | New |  |  |  |  |  |  |  | 
Grand Total |  |  |  |  |  |  |  |  | 

## Slide 3: Executive Summary Work in Progress Schemes
Taluka | Category | No. of Schemes | No. of Schemes based on Physical Progress % |  |  |  | 
 |  |  | < 25% | 25 < 50% | 50 < 75% | 75 < 100% | Commissioned
 | Retro |  |  |  |  |  | 
 | New |  |  |  |  |  | 
 | Retro |  |  |  |  |  | 
 | New |  |  |  |  |  | 
 | Retro |  |  |  |  |  | 
 | New |  |  |  |  |  | 
 | Retro |  |  |  |  |  | 
 | New |  |  |  |  |  | 
 | Retro |  |  |  |  |  | 
 | New |  |  |  |  |  | 
Total | Retro |  |  |  |  |  | 
 | New |  |  |  |  |  | 
Grand Total |  |  |  |  |  |  | 

## Slide 4: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
Ambad Taluka | Ambad Taluka |  |  |  |  |  |  | 
1 | Dawargaon | Sameer Construction | 14,44,487 | 01-07-2022 | 6 Months | 99.62% | 63.65% | 9.19
2 | Awa | C. Jambuwant Mss | 22,81,708 | 28-03-2022 | 12 Months | 96.76% | 70.45% | 16.07
3 | Sadeswangi | Sahdev Rajesh Raut | 14,79,400 | 02-03-2022 | 12 Months | 92.45% | 75.17% | 11.12
4 | Kothala Kh | Sahdev Rajesh Raut Construction | 14,30,940 | 02-02-2022 | 12 Months | 90.64% | - | -
5 | Kolisrasgaon | Sandipan Ghare | 14,27,121 | 27-01-2022 | 6 Months | 89.26% | - | -
6 | Domalgaon | Sachin Enterprises | 9,92,599 |  | 6 Months | 88.52% | - | -
7 | Ghungarde Hadgaon | Sahadev Rajesh Raut | 14,28,377 | 15-01-2022 | 12 Months | 80.13% | - | -
8 | Dodadgaon | Lahamage | 20,47,938 | 11-08-2022 | 12 Months | 77.72% | 32.42% | 6.64
9 | Kauchalwadi Ambad | Ramprasad Madanrao Khandare | 22,57,457 | 29-04-2022 | 12 Months | 71.43% | - | -
10 | Gangramwadi | Ajinkya Ramrao Rathod | 14,94,864 |  | 6 Months | 67.36% | - | -
11 | Soundalgaon (Azimnagar) | Shivprasad Giram | 21,44,879 | 23-06-2022 | 12 Months | 63.10% | 41.98% | 9.00
12 | Antarwala | Ram Prasad Madanrao Khandare | 12,62,800 | 14-08-2022 | 6 Months | 59.14% | - | -
13 | Chikangaon | Sahdev Rajesh Raut | 14,74,000 | 14-09-2022 | 12 Months | 56.67% | - | -

## Slide 5: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
14 | Dadhegaon | Ajinkya Ramrao Rathod | 62,19,469 | 14-10-2022 | 18 Months | 55.85% | - | -
15 | Dhangarpimpri | Ajinkya Ramrav Ratod | 54,06,395 | 12-08-2022 | 18 Months | 53.87% | - | -
16 | Kingaonwadi | Matsyodari Mss | 17,56,285 | 06-02-2022 | 12 Months | 46.22% | - | -
17 | Dahipuri | Sachin Enterprises | 22,46,740 | 16-06-2022 | 12 Months | 45.12% | 38.49% | 8.65
18 | Mardi | Krushna Kuntimal | 22,35,116 | 03-10-2022 | 12 Months | 34.10% | - | -
19 | Vitthal Wadi | Shital Rustom Rathod | 36,00,699 | 20-10-2022 | 18 Months | 32.05% | - | -
20 | Bhanang Jalgaon | Mayur Construction | 57,82,106 | 16-09-2022 | 18 Months | 30.28% | - | -
21 | Harakheda | C. Samarth | 23,08,427 | 20-04-2022 | 12 Months | 27.93% | - | -
22 | Narayangaon | Sameer Construction | 7,71,369 | 16-03-2022 | 12 Months | 25.41% | - | -
23 | Malyachiwadi & Bhokarwadi | S.V Kale | 22,22,849 | 02-06-2022 | 12 Months | 23.80% | - | -
24 | Kuran | Ajinkya Ramrao Rathod | 16,20,353 | 10-03-2022 | 12 Months | 16.21% | - | -
25 | Bhivandi Bodkha | Sahdev Rajesh Raut | 14,47,624 | 15-02-2022 | 12 Months | 14.56% | - | -
26 | Maher Bhaigaon | Sandipan Ghare | 74,87,740 | 16-06-2022 | 12 Months | 13.69% | - | -
27 | Rewalgaon | Sameer Construction | 14,26,643 | 14-09-2022 | 6 Months | 12.21% | - | -

## Slide 6: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
28 | Ramgavhan Bk | Kailash Ubale | 83,83,371 | 13-09-2022 | 18 Months | 10.36% | - | -
29 | Mahakala | Mangesh Enterprises | 3,88,61,073 | 06-01-2023 | 15 Months | 10.06% | - | -
30 | Bantakali | S.D Ghare | 22,70,913 | 10-05-2022 | 12 Months | 9.60% | - | -
31 | Belgaon | Kailash Laxmanrao Ubale | 64,66,808 | 21-09-2022 | 18 Months | 8.80% | - | -
32 | Hasnapur | Ajinkya Ramrao Rathod | 75,31,117 | 12-09-2022 | 18 Months | 7.81% | - | -
33 | Naggonyachiwadi | C. Jabuwant Mss | 19,03,038 | 06-04-2022 | 12 Months | 5.06% | - | -
34 | Domegaon Ambad | Kailash Ubale | 76,52,885 | 22-08-2022 | 18 Months | 4.31% | - | -
35 | Taka | Mayur Construction | 86,89,021 | 04-01-2023 | 15 Months | 3.83% | - | -
36 | Kukadgaon Ambad | Kailash Ubale | 60,42,303 | 14-09-2022 | 18 Months | 3.46% | - | -
37 | Indalgaon | Gauri Construction | 14,28,505 | 14-10-2021 | 6 Months | 2.82% | - | -
38 | Khadkeshwar | Sahdev Rajesh Raut | 8,23,256 | 01-06-2022 | 6 Months | 2.31% | - | -
39 | Dudhpuri & Dudhpuri Tanda | Kailash Ubale | 58,77,614 | 05-09-2022 | 18 Months | 2.26% | - | -
40 | Mathpimpalgaon & Gola | Kailash Ubale | 63,87,142 | 13-09-2022 | 18 Months | 2.11% | - | -
41 | Nihalsingwadi | S.R Raut | 41,89,131 | 14-09-2022 | 18 Months | 1.98% | - | -

## Slide 7: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
42 | Sarangpur | N.N Nannaware | 46,77,677 | 11-08-2022 | 18 Months | 1.79% | - | -
43 | Sadegaon | B.N Udhan | 86,66,699 | 05-12-2022 | 15 Months | 1.75% | - | -
44 | Shiradhon | Chairmen Jabuwant Mss | 29,27,022 | 28-09-2022 | 12 Months | 0.59% | - | -
45 | Nandi | D.R Jarhad | 71,13,969 | 21-09-2022 | 18 Months | 0.30% | - | -
46 | Sukhapuri | D.R. Jargad | 1,11,39,885 | 22-08-2022 | 18 Months | 0.23% | - | -
47 | Bhalgaon Ambad | C.Yamuna Mss | 23,65,279 | 17-05-2022 | 12 Months | 0.20% | - | -
48 | Lakhmapuri Ambad | S.V Kale | 20,87,198 | 26-05-2022 | 12 Months | 0.09% | - | -
49 | Bhardi | Kailash Laxmanrao Ubale | 80,86,545 | 22-08-2022 | 18 Months | 0.07% | - | -
Badnapur Taluka | Badnapur Taluka |  |  |  |  |  |  | 
50 | Chikhali | N.N Nannaware | 20,91,018 | 02-06-2022 | 12 Months | 85.69% | 80.73% | 16.88
51 | Rala | Adinath Janardhan Dale | 14,28,495 | 17-11-2022 | 6 Months | 66.91% | - | -
52 | Chitoda | Sameer Construction | 9,50,579 | 11-01-2022 | 6 Months | 62.91% | - | -
53 | Shirasgaon Ghati | Samarth Mss | 20,79,200 | 12-07-2022 | 12 Months | 52.86% | - | -
54 | Bharadkheda | Mayur Construction | 68,19,209 | 25-08-2022 | 18 Months | 44.14% | - | -

## Slide 8: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
55 | Ghotan | Ajinkya Ramrao Rathod | 48,08,124 | 14-10-2022 | 18 Months | 34.65% | - | -
56 | Hiwara Dabhadi | Sameer Construction | 13,68,630 | 22-08-2022 | 3 Months | 30.53% | - | -
57 | Ranjangaon | S.B Sirsaat | 23,71,802 | 20-04-2022 | 12 Months | 24.13% | - | -
58 | Malegaon Kh | Sandipan Ghare | 41,55,571 | 16-09-2022 | 18 Months | 21.34% | - | -
59 | Waiha | Sandipan Ghare | 85,02,830 | 09-12-2022 | 18 Months | 17.67% | - | -
60 | Ambadgaon | D.R Jarhad | 67,39,028 | 14-09-2022 | 18 Months | 12.13% | - | -
61 | Hiwara | Yamuna Mss | 23,55,020 | 16-09-2022 | 12 Months | 9.83% | - | -
62 | Kajala Pankheda Bad | D.R. Jarhad | 1,88,40,624 | 14-10-2022 | 18 Months | 9.59% | - | -
63 | Nikalak | N.N. Nannaware | 64,25,327 | 12-09-2022 | 18 Months | 5.27% | - | -
64 | Padli | N.N. Nannaware | 49,52,045 | 12-09-2022 | 18 Months | 5.11% | - | -
65 | Deogaon | Sambhaji Sirsath | 94,39,579 | 16-09-2022 | 18 Months | 4.46% | - | -
66 | Kasturwadi | Shivneri Mss | 23,80,060 | 12-07-2022 | 12 Months | 4.38% | - | -
67 | Pathar Deolgaon Bad | Sambhaji Sirsat | 1,34,40,346 | 21-09-2022 | 18 Months | 3.26% | - | -
68 | Gokulwadi | Sachin Enterprises | 41,55,923 | 21-09-2022 | 18 Months | 3.15% | - | -

## Slide 9: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
69 | Butegaon Bad | Amrut Pandurang Pawar | 59,22,180 | 27-09-2022 | 18 Months | 3.05% | - | -
70 | Bhilpuri Kh | C.Shivneri Mss | 23,07,487 | 12-07-2022 | 12 Months | 2.66% | - | -
71 | Kandhari Bk Bad | Sandipan Ghare | 77,48,251 | 10-12-2022 | 18 Months | 1.91% | - | -
72 | Rajewadi Shelgaon | N.N. Nannawre | 80,76,153 | 22-09-2022 | 18 Months | 1.72% | - | -
73 | Kandhari Kh Bad | Sameer Construction | 1,20,58,764 | 14-10-2022 | 18 Months | 1.43% | - | -
74 | Chanegaon | Sambhaji Sirasath | 89,22,438 | 18-08-2022 | 18 Months | 1.19% | - | -
75 | Sindhi Pimpalgaon | Sambhaji Sirsath | 66,53,800 | 12-09-2022 | 18 Months | 1.17% | - | -
76 | Keligavhan | O. B Sanap | 1,00,38,429 | 17-11-2022 | 18 Months | 0.81% | - | -
77 | Bavne Pangri | Sambhaji Bhausaheb Sirsath | 65,14,031 | 05-12-2022 | 18 Months | 0.62% | - | -
78 | Dawargaon | Sambhaji Sirsath | 93,57,346 | 23-12-2022 | 15 Months | 0.36% | - | -
79 | Bajar Wahegaon | Sandipan Ghare | 57,69,540 | 02-01-2023 | 15 Months | 0.33% | - | -
80 | Dabhadi | Sameer Construction | 1,33,94,775 | 03-01-2023 | 15 Months | 0.22% | - | -
81 | Manjargaon | N.N. Nannaware | 89,58,874 | 21-09-2022 | 18 Months | 0.16% | - | -
82 | Dhasla | Sameer Construction | 1,50,00,346 | 21-09-2022 | 18 Months | 0.08% | - | -

## Slide 10: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
83 | Nandkheda Bad | Sameer Construction | 88,78,087 | 20-10-2022 | 18 Months | 0.01% | - | -
Bhokardan Taluka | Bhokardan Taluka |  |  |  |  |  |  | 
84 | Kolegaon | Nandani Construction | 92,88,135 | 26-08-2022 | 18 Months | 68.77% | - | -
85 | Manapur | Nandini Construction | 67,44,357 | 15-12-2022 | 15 Months | 62.92% | - | -
86 | Kotha Jahagir | Mangesh Shalikrao Kolhe | 47,72,893 | 23-12-2022 | 15 Months | 42.51% | - | -
87 | Chorala | Nandini Construction | 50,55,173 | 28-11-2022 | 18 Months | 38.91% | - | -
88 | Malegaon | Nandini Construction | 1,09,35,380 | 28-11-2022 | 18 Months | 37.36% | - | -
89 | Viregaon | Nandini Construction | 1,01,30,999 | 14-10-2022 | 18 Months | 35.23% | - | -
90 | Khaparkheda | Nandini Construction | 64,96,877 | 16-09-2022 | 18 Months | 22.94% | 9.30% | 6.04
91 | Gavhan Sangmeshwar | Nandani Construction | 23,59,857 | 09-06-2022 | 12 Months | 19.42% | - | -
92 | Masanpur | Sanjay Raghunath Bhandare | 23,23,348 | 23-12-2022 | 15 Months | 17.21% | - | -
93 | Vizora | Nandini Construction | 57,41,773 | 28-11-2022 | 18 Months | 13.48% | - | -
94 | Khadgaon | Nandini Construction | 58,70,187 | 28-11-2022 | 18 Months | 12.65% | - | -
95 | Selude | Nandini Construction | 1,00,72,122 | 16-09-2022 | 18 Months | 12.15% | - | -

## Slide 11: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
96 | Jainpur Khothara | Nandini Construction | 34,24,172 | 28-11-2022 | 18 Months | 12.12% | - | -
97 | Pimpalgaon Barao | Nandini Construction | 54,54,128 | 16-09-2022 | 18 Months | 7.25% | 13.40% | 7.31
98 | Nimbola | Nandini Construction | 57,82,535 | 16-09-2022 | 18 Months | 5.94% | - | -
99 | Kedarkheda Bamkheda | Nandni Construction | 1,93,12,487 | 26-08-2022 | 18 Months | 5.86% | - | -
100 | Garkheda | Nandini Construction | 68,09,518 | 05-12-2022 | 15 Months | 4.78% | - | -
101 | Tadegaon | Nandani Construction | 1,52,03,944 | 26-08-2022 | 18 Months | 4.23% | - | -
102 | Dawargaon Walsa | Sarvdharm Sambhav Mss | 23,17,497 | 11-08-2022 | 12 Months | 4.01% | - | -
103 | Kalyani | Nandini Construction | 1,29,97,470 | 21-09-2022 | 18 Months | 4.01% | - | -
104 | Dhondkheda | S.R.L Construction Ltd | 72,77,775 | 10-10-2022 | 18 Months | 4.01% | - | -
105 | Takali Bajad | Nandini Construction | 36,80,042 | 28-11-2022 | 18 Months | 3.67% | - | -
106 | Kodoli | Nandani Construction | 85,35,370 | 05-09-2022 | 18 Months | 3.66% | - | -
107 | Takli Bhokardan | Nandani Construction | 79,86,548 | 26-08-2022 | 18 Months | 3.07% | - | -
108 | Itta Ramnagar | Nandini Construction | 1,00,33,415 | 21-09-2022 | 18 Months | 3.06% | - | -
109 | Pimpalgaon Sermulki | Nandini Construction | 99,31,013 | 28-11-2022 | 18 Months | 2.05% | - | -

## Slide 12: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
110 | Jawkheda Thombari | Nandini Construction | 1,03,58,471 | 23-12-2022 | 15 Months | 1.63% | - | -
111 | Tadkalas | Mangesh Shalikram Kolhe | 39,01,031 | 17-10-2022 | 18 Months | 1.27% | - | -
112 | Sirasgaon Mandap | Nandini Construction | 74,45,190 | 28-11-2022 | 18 Months | 1.21% | - | -
113 | Merkheda | Nandini Construction | 39,56,694 | 23-12-2022 | 15 Months | 1.05% | - | -
114 | Kotara Jainpur | Nandini Construction | 41,53,862 | 28-11-2022 | 18 Months | 0.91% | - | -
115 | Jawkheda Kh | Nandini Construction | 85,05,177 | 28-11-2022 | 18 Months | 0.77% | - | -
116 | Soygaondevi | Nandini Construction | 4,55,32,546 | 06-01-2023 | 15 Months | 0.68% | - | -
117 | Talni | Nandini Construction | 57,78,889 | 21-09-2022 | 18 Months | 0.63% | - | -
118 | Sipora Bazar | Nandini Construction | 1,96,29,917 | 28-11-2022 | 18 Months | 0.62% | - | -
119 | Bhyadi | Nandini Construction | 90,25,194 | 21-09-2022 | 18 Months | 0.36% | - | -
120 | Warud Bk | Nandini Construction | 1,79,52,123 | 21-09-2022 | 18 Months | 0.32% | - | -
121 | Alapur | Sanjay Raghunath Bhandare | 49,54,336 | 05-12-2022 | 18 Months | 0.20% | - | -
Ghanswangi Taluka | Ghanswangi Taluka |  |  |  |  |  |  | 
122 | Chitravadgaon | Krushna Kuntimal | 44,04,964 | 22-08-2022 | 18 Months | 86.30% | 58.27% | 25.67

## Slide 13: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
123 | Hatadi | C. Yamuna | 23,04,303 | 25-08-2022 | 18 Months | 59.78% | 58.88% | 13.57
124 | Shevgal | Mayur Construction | 97,93,483 | 12-09-2022 | 18 Months | 53.16% | - | -
125 | Belwadi | Pawan Surang | 32,98,998 | 25-08-2022 | 12 Months | 43.02% | 30.20% | 9.96
126 | Talegaon | Mayur Construction | 61,01,387 | 25-08-2022 | 18 Months | 21.82% | - | -
127 | Ukkadgaon | Bappa Udhan | 9,33,023 | 27-06-2022 | 12 Months | 21.75% | 21.46% | 2.00
128 | Devli Hadgaon |  | 13,20,000 | 15-03-2022 |  | 19.60% | - | -
129 | Viregavhan | Shital Rustom Rathod | 35,75,811 | 28-10-2022 | 18 Months | 13.61% | - | -
130 | Argadegavhan | B.N Udhan | 67,16,219 | 16-09-2022 | 18 Months | 13.33% | - | -
131 | Nipani Pimpalgaon | Mayur Construction | 88,85,927 | 12-09-2022 | 18 Months | 9.84% | - | -
132 | Nageshnagar | Amrut Pandurang Pawar | 58,18,758 | 24-09-2022 | 18 Months | 9.01% | - | -
133 | Bor Rajani | Ramdhan Bahusing Chavhan | 51,80,502 | 07-12-2022 | 15 Months | 8.35% | - | -
134 | Khapardev Hiwra | Sambhaji Sirsath | 53,51,606 | 05-12-2022 | 18 Months | 8.28% | - | -
135 | Guna Naik | Ajinkya Ramrao Rathod | 69,58,322 | 17-11-2022 | 18 Months | 7.09% | - | -
136 | Sakalgaon | Amrut Pandurang Pawar | 81,43,522 | 05-09-2022 | 18 Months | 6.70% | - | -

## Slide 14: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
137 | Krishnapurwadi | Mayur Construction | 1,04,45,226 | 21-09-2022 | 18 Months | 6.46% | - | -
138 | Mandala | Mrunal Bhagwanrao Dhave | 30,87,931 | 10-11-2022 | 18 Months | 3.87% | - | -
139 | Ghonsi Bk | Ramdhan Bhausing Chavhan | 77,94,393 | 05-09-2022 | 18 Months | 3.29% | - | -
140 | Antarwala Bk | Gyaneshwar R. Jarhad | 59,51,626 | 17-11-2022 | 18 Months | 2.53% | - | -
141 | Rajniwadi | Ajinkya Ratod | 14,26,225 | 01-02-2022 | 6 Months | 2.31% | - | -
142 | Shindewadgaon | P.S Katkar | 69,03,765 | 13-09-2022 | 18 Months | 2.28% | - | -
143 | Kardgaon | Rajkumar Borade | 40,71,241 | 23-09-2022 | 18 Months | 1.29% | - | -
144 | Shripath Dhamangaon | Sambhaji Sirsath | 52,43,570 | 17-11-2022 | 18 Months | 1.14% | - | -
145 | Jiradgaon | Kailash Patil Ubale | 80,08,132 | 22-08-2022 | 18 Months | 0.95% | - | -
146 | Shivangan | Pawan Surang | 31,40,744 | 25-08-2022 | 18 Months | 0.86% | - | -
147 | Guru Pimpri | Mayur Construction | 1,31,96,990 | 05-01-2023 | 15 Months | 0.80% | - | -
148 | Khadka | Sameer Construction | 61,14,389 | 22-08-2022 | 18 Months | 0.74% | - | -
149 | Limboni | Kailash Ubale | 74,17,275 | 23-11-2022 | 18 Months | 0.45% | - | -
150 | Borgaon Kh. | Padyanath Developers | 1,78,45,403 | 15-12-2022 | 15 Months | 0.41% | - | -

## Slide 15: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
151 | Awalgaon(Bk,Kh) | Sameer Construction | 1,79,96,880 | 27-12-2022 | 15 Months | 0.38% | - | -
152 | Wadiramasgaon | Kailash Ubale | 66,04,210 | 13-09-2022 | 18 Months | 0.34% | - | -
153 | Bhadregaon | Chairman Jabuwant Mss | 28,52,856 | 28-09-2022 | 12 Months | 0.33% | - | -
154 | Soundalgaon | Sambhaji Sirsath | 60,50,669 | 17-11-2022 | 18 Months | 0.33% | - | -
155 | Bhyegvhan | Amrut Pandurang Pawar | 81,12,649 | 27-09-2022 | 18 Months | 0.31% | - | -
156 | Mudregaon | Padmakar Suryakant Katkar | 65,85,523 | 22-08-2022 | 18 Months | 0.28% | - | -
157 | Ramgavhan Kh | Kailsh Ubale | 57,60,811 | 13-09-2022 | 18 Months | 0.26% | - | -
158 | Daithana Bk | Prashant Sampantrao Salve | 43,40,056 | 23-09-2022 | 18 Months | 0.24% | - | -
159 | Sindkhed | B.N Udhan | 95,43,248 | 23-12-2022 | 15 Months | 0.22% | - | -
160 | Devhiwra Ekrukha | Kailash Laxman Ubale | 1,02,16,438 | 02-12-2022 | 18 Months | 0.20% | - | -
161 | Murma | Shreekant Bhanudas Ghule | 1,17,69,942 | 15-09-2022 | 18 Months | 0.14% | - | -
162 | Kandhari Partur | Padyanath Developers | 1,41,34,672 | 05-12-2022 | 18 Months | 0.13% | - | -
163 | Masegaon | Gyaneshwar R. Jarhad | 1,90,82,615 | 17-11-2022 | 18 Months | 0.10% | - | -

## Slide 16: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
Jafrabad Taluka | Jafrabad Taluka |  |  |  |  |  |  | 
164 | Khasgaon | Prashant Salve | 23,56,037 | 10-03-2022 | 12 Months | 92.50% | 4.77% | 1.12
165 | Kumbharzari | Ajinkya Rathod | 23,74,906 | 11-05-2022 | 12 Months | 74.39% | - | -
166 | Sipora Ambhora | Nandini Construction | 1,02,24,695 | 14-09-2022 | 18 Months | 22.35% | - | -
167 | Wankheda Jaf | Shital Rustom Rathod | 13,04,318 | 20-10-2022 | 12 Months | 22.21% | - | -
168 | Borkhedi Chinch | Vishal Sarjrao Shinde | 37,68,997 | 05-12-2022 | 15 Months | 13.86% | - | -
169 | Pokhari | S.R.L Construction Ltd | 90,14,742 | 14-09-2022 | 18 Months | 10.50% | - | -
170 | Hiwrabali | S.R.L Construction | 84,07,720 | 23-11-2022 | 18 Months | 6.68% | - | -
171 | Sindi | S.R.L Construction | 1,20,13,355 | 14-09-2022 | 18 Months | 3.31% | - | -
172 | Kinhi | Sudhir Shankarrao Mapari | 17,19,948 | 08-11-2022 | 12 Months | 2.59% | - | -
173 | Deulgaon Ugle | Sudhir S.Mapari | 52,70,423 | 02-12-2022 | 18 Months | 1.33% | - | -
174 | Asai | S.R.L Construction | 73,98,099 | 16-09-2022 | 18 Months | 1.30% | - | -
175 | Nalvihira | S.R.L Construction Ltd | 66,95,150 | 09-05-2022 | 18 Months | 1.25% | - | -
176 | Sawargaon Mhaske | Sudhir S. Mapari | 79,74,126 | 05-01-2023 | 15 Months | 1.18% | - | -
177 | Warud Kd | S.R.L Ltd Khasgaon | 83,24,543 | 14-09-2022 | 18 Months | 0.96% | - | -

## Slide 17: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
178 | Sonkheda | S.R.L Construction | 52,11,295 | 23-11-2022 | 18 Months | 0.84% | - | -
179 | Harpala | S.R.L Construction | 70,53,100 | 23-11-2022 | 18 Months | 0.82% | - | -
180 | Pimpalgaon Kad | Kailash Ubale | 86,72,520 | 09-05-2022 | 18 Months | 0.77% | - | -
181 | Sawasni | S.R.L Ltd Khasgaon | 95,94,099 | 14-09-2022 | 18 Months | 0.72% | - | -
182 | Khanapur | Sudhir S. Mapari | 78,02,122 | 28-11-2022 | 18 Months | 0.62% | - | -
183 | Dongaon Jaf | S.R.L Construction | 1,80,53,579 | 26-12-2022 | 15 Months | 0.52% | - | -
184 | Bharadkheda | Sudhir S. Mapari | 90,89,894 | 05-12-2022 | 18 Months | 0.49% | - | -
185 | Nimkheda Kh | Chairmen Sangmeshwar Majur Sahkari Sanstha Maryadit | 22,26,582 | 24-12-2022 | 15 Months | 0.47% | - | -
186 | Garkheda | S.R.L Construction | 53,16,270 | 23-09-2022 | 18 Months | 0.45% | - | -
187 | Virkheda Bhakli | Swabhiman | 23,67,610 | 29-04-2022 | 12 Months | 0.39% | - | -
188 | Shirala | S.R.L Construction Ltd | 76,28,874 | 16-09-2022 | 18 Months | 0.33% | - | -
189 | Butkheda | Sudhir Shankarrao Mapari | 76,34,566 | 09-12-2022 | 18 Months | 0.30% | - | -
190 | Akola Dev | Kailash Laxman Ubale | 1,90,46,546 | 28-11-2022 | 18 Months | 0.17% | - | -
191 | Warkheda Viro | S.R.L. Construction Ltd | 55,06,278 | 14-10-2022 | 18 Months | 0.14% | - | -

## Slide 18: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
192 | Wadhona | Shivanand Narayan Mudhe | 50,28,463 | 05-01-2023 | 15 Months | 0.11% | - | -
193 | Rastal | S.R.L Construction | 86,74,099 | 23-11-2022 | 18 Months | 0.05% | - | -
Jalna Taluka | Jalna Taluka |  |  |  |  |  |  | 
194 | Antarwala Sindkhed | Shital Rustom Rathod | 20,93,337 | 17-11-2022 | 18 Months | 64.79% | - | -
195 | Mamdabad | Ajinkya Rathod | 23,23,393 | 04-05-2022 | 12 Months | 46.20% | - | -
196 | Malegaon Kh | S.B Sirsath | 55,14,864 | 05-01-2023 | 15 Months | 40.50% | - | -
197 | Dahifal And Tanda | Ajinkya Rathod | 23,76,397 | 10-03-2022 | 12 Months | 37.78% | 7.38% | 1.75
198 | Wadiwadi | Ramdhan Bhausing Chavhan | 42,19,026 | 24-09-2022 | 18 Months | 35.51% | - | -
199 | Ahankar Deulgaon | Ramkisan Nathadarade | 48,73,807 | 21-09-2022 | 18 Months | 31.34% | - | -
200 | Nasagaon Vasti | Shital Rustom Rathod | 9,50,897 | 24-02-2022 | 6 Months | 29.58% | - | -
201 | Kumbhephal | Sambhaji Sirsath | 32,97,904 | 27-12-2022 | 15 Months | 24.42% | - | -
202 | Kumbephal Sindkhed | Sandipan Ghare | 70,63,307 | 22-09-2022 | 18 Months | 20.20% | - | -
203 | Kolwadi Daregaon | Matsyodari Mss | 22,54,173 | 30-03-2022 | 12 Months | 19.75% | - | -
204 | Islamwadi | D.R Jarhad | 70,64,998 | 21-09-2022 | 18 Months | 18.53% | - | -

## Slide 19: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
205 | Manegaon Jahangir | Shivanand Narayan Mundhe | 1,10,44,957 | 05-12-2022 | 18 Months | 17.14% | - | -
206 | Gokul Nagar | Aadhar Mss Dhoksal | 24,56,850 | 05-12-2022 | 15 Months | 14.95% | - | -
207 | Nipani Pokhri | Sudhakar Mohanrao Nikalje | 48,12,017 | 28-11-2022 | 18 Months | 11.20% | - | -
208 | Punegaon | Gyaneshwar R. Jarhad | 51,02,119 | 17-11-2022 | 18 Months | 11.11% | - | -
209 | Warud Jalna | Ramdhan Bhavsing Chavhan | 44,14,507 | 02-12-2022 | 18 Months | 9.46% | - | -
210 | Malshendra | Mangesh Enterprises | 14,99,800 | 07-12-2022 | 6 Months | 9.14% | - | -
211 | Ghanewadi | S.M Nikalje | 56,77,559 | 04-01-2023 | 15 Months | 8.32% | - | -
212 | Paregaon | Ajinkya Ramrao Rathod | 90,16,197 | 17-11-2022 | 18 Months | 6.85% | - | -
213 | Nidhona | Pooja Mss | 26,97,346 | 09-12-2022 | 12 Months | 6.67% | - | -
214 | Daregaon | Sudhakar Mohanrao Nikalje | 65,81,987 | 28-11-2022 | 18 Months | 6.09% | - | -
215 | Dambari | Padmakumar Suryakant Katkar | 66,32,481 | 22-08-2022 | 18 Months | 4.80% | - | -
216 | Pirpimpalgaon | Sudhakar Mohanrao Nikalje | 1,09,40,234 | 02-12-2022 | 18 Months | 2.94% | - | -
217 | Shrikrushnanagar | S.B Sirsath | 75,34,702 | 05-01-2023 | 15 Months | 2.02% | - | -
218 | Ghetuli | Atul Bhagwan Yadav | 42,58,636 | 21-09-2022 | 18 Months | 1.72% | - | -

## Slide 20: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
219 | Wanjar Umrad | S.M. Nikalje | 1,68,18,637 | 09-12-2022 | 18 Months | 1.71% | - | -
220 | Pimpalwadi | Padyanath Developers | 89,61,604 | 19-12-2022 | 15 Months | 1.20% | - | -
221 | Nirkheda | D.R Jarhad | 1,22,94,581 | 10-10-2022 | 18 Months | 1.13% | - | -
222 | Bramhankheda | Mahesh Digambarrao Gogde | 21,96,433 | 05-12-2022 | 15 Months | 1.13% | - | -
223 | Bathan Bk | Sahdev Rajesh Raut | 14,98,000 | 11-01-2023 | 6 Months | 0.70% | - | -
224 | Utwad | Sandipan Ghare | 79,95,553 | 24-12-2022 | 15 Months | 0.66% | - | -
225 | Wazar Sarate | Gyaneshwar R. Jarhad | 95,19,408 | 17-11-2022 | 18 Months | 0.65% | - | -
226 | Palaskheda (Kailashnagar) | Rajkumar Janardhan Borade | 14,29,293 | 17-08-2022 | 6 Months | 0.59% | - | -
227 | Panshendra | O.B Sanap | 1,43,19,282 | 19-10-2022 | 18 Months | 0.26% | - | -
228 | Warkheda Sindkhed | S.B Sirsath | 41,54,362 | 05-01-2023 | 15 Months | 0.15% | - | -
229 | Kadwanchi | D.R Jarhad | 1,13,87,164 | 05-01-2023 | 15 Months | 0.15% | - | -
230 | Kawatha | Padyanath Developers | 59,87,318 | 05-12-2022 | 18 Months | 0.15% | - | -
231 | Mali Pimpalgaon | Mrunal Dhabe | 39,34,089 | 29-09-2022 | 18 Months | 0.02% | - | -
226 | Panshendra | O.B Sanap | 1,43,19,282 | 19-10-2022 | 18 Months | 0.26% | - | -

## Slide 21: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
227 | Dambari | Padmakumar Suryakant Katkar | 66,32,481 | 22-08-2022 | 18 Months | 0.22% | - | -
228 | Warkheda Sindkhed | S.B Sirsath | 41,54,362 | 05-01-2023 | 15 Months | 0.15% | - | -
229 | Kadwanchi | D.R Jarhad | 1,13,87,164 | 05-01-2023 | 15 Months | 0.15% | - | -
230 | Kawatha | Padyanath Developers | 59,87,318 | 05-12-2022 | 18 Months | 0.15% | - | -
231 | Mali Pimpalgaon | Mrunal Dhabe | 39,34,089 | 29-09-2022 | 18 Months | 0.02% | - | -

## Slide 22: Abstract of Schemes – Work in Progress Category – “New”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
Ambad Taluka | Ambad Taluka |  |  |  |  |  |  | 
1 | Kingaon | Krushna Kruntimal | 19,23,264 | 30-03-2022 | 12 Months | 98.13% | 75.26% | 14.47
2 | Deshgavhan | P.S Katkar | 52,40,141 | 20-04-2022 | 18 Months | 49.91% | - | -
3 | Katkheda | D.R.G.Haad | 92,27,077 | 22-08-2022 | 18 Months | 31.95% | 10.21% | 9.42
4 | Renapuri | Krushnaraj Shivaji Shinde | 21,01,567 | 16-06-2022 | 12 Months | 30.69% | - | -
5 | Patharwala Bk | B.N. Udhan | 23,55,380 | 10-03-2022 | 12 Months | 28.08% | - | -
6 | Gori Gandhari | B.N Udhan | 86,86,733 | 10-03-2022 | 18 Months | 15.46% | - | -
7 | Soundalgaon Kh | Rajkumar Borade | 31,17,387 | 09-01-2023 | 15 Months | 13.09% | - | -
8 | Bakshachiwadi | S.B Sirsath | 78,43,783 | 17-11-2022 | 18 Months | 12.44% | - | -
9 | Shahgad | Shrikant Bhanudas Ghule | 1,68,09,339 | 15-09-2022 | 18 Months | 6.47% | - | -
10 | Bhasunaik Tanda | Sambhaji Sirsath | 41,05,601 | 02-01-2023 | 15 Months | 6.27% | - | -
11 | Sasht Pimpalgaon Ambad | Kailash Ubale | 1,92,24,290 | 22-08-2022 | 18 Months | 3.35% | - | -
12 | Dodadgaon Tanda | Kailash Mss | 13,60,974 | 07-01-2023 | 15 Months | 2.64% | - | -
13 | Gondi | Sambhaji Sirsath | 1,99,99,146 | 17-11-2022 | 18 Months | 2.56% | - | -

## Slide 23: Abstract of Schemes – Work in Progress Category – “New”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
14 | Soniya Nagar | Kailash Mss | 16,30,296 | 17-01-2023 | 15 Months | 2.14% | - | -
15 | Parner Tanda | Mrunal Dhabe | 20,19,208 | 05-01-2023 | 15 Months | 1.99% | - | -
16 | Rui | Shrikant Bhanudas Ghule | 1,06,84,065 | 15-09-2022 | 18 Months | 1.59% | - | -
17 | Antarwali Sarthi | Kailash Laxmanrao Ubale | 74,00,050 | 16-09-2022 | 18 Months | 1.08% | - | -
18 | Sonak Pimpalgaon | Sambhaji Sirsath | 1,13,07,729 | 17-11-2022 | 18 Months | 0.50% | - | -
19 | Wadikalya | Shaker Khan Shafiq Khan Pathan | 23,31,253 | 10-03-2022 | 12 Months | 0.44% | - | -
20 | Kailashnagar | Ajinkya Ramrao Rathod | 55,48,150 | 16-09-2022 | 18 Months | 0.44% | - | -
21 | Math Jalgaon Tanda 1 & 2 | Mrunal Dhabe | 17,60,777 | 05-01-2023 | 15 Months | 0.18% | - | -
Badnapur Taluka | Badnapur Taluka |  |  |  |  |  |  | 
22 | Kinhola | Dudhna Mss | 17,64,988 | 10-03-2022 | 12 Months | 96.94% | - | -
23 | Laxmannagar | Shital Rustom Rahod | 14,28,134 | 20-02-2022 | 6 Months | 81.99% | - | -
24 | Georai Bazar | Gyaneshwar R. Jarhad | 87,06,584 | 02-01-2023 | 15 Months | 70.44% | - | -
25 | Deo Pimpalgaon | N.N Nannaware | 1,16,02,296 | 20-04-2022 | 18 Months | 24.47% | - | -
26 | Asola | N.N Nannaware | 53,07,573 | 11-08-2022 | 18 Months | 23.84% | 24.27% | 12.88

## Slide 24: Abstract of Schemes – Work in Progress Category – “New”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
27 | Ujjainpuri | Tirupati Construction Badrinarayan Upare | 22,75,372 | 28-03-2022 | 12 Months | 10.90% | - | -
28 | Ramkheda | Ajinkya Ramrao Rathod | 49,49,910 | 27-12-2022 | 15 Months | 1.56% | - | -
29 | Laxman Tanda | R.B Chavhan | 20,23,435 | 03-01-2023 | 15 Months | 0.45% | - | -
30 | Kadegaon | Sudhakar Maohanrao Nikalje | 94,29,734 | 28-11-2022 | 18 Months | 0.21% | - | -
31 | Mandevalgaon & Dagadwadi | Shreekant Bhanudas Ghule | 1,99,71,523 | 05-01-2023 | 15 Months | 0.06% | - | -
Bhokardan Taluka | Bhokardan Taluka |  |  |  |  |  |  | 
32 | Kosgaon | Nandini Construction | 1,92,29,322 | 23-09-2022 | 18 Months | 30.40% | - | -
33 | Kshrisagar | Sanjay Raghunath Bhandhare | 43,95,032 | 20-10-2022 | 18 Months | 29.83% | - | -
34 | Koparda | Nandini Construction | 1,33,61,470 | 28-11-2022 | 18 Months | 27.51% | - | -
35 | Muthad | Nandini Construction | 62,85,897 | 28-11-2022 | 18 Months | 26.59% | - | -
36 | Chandai Ekko | Nandini Construction | 84,19,305 | 16-09-2022 | 18 Months | 20.04% | - | -
37 | Walsa Khalsa | Nandini Construction | 59,17,013 | 21-09-2022 | 18 Months | 16.36% | - | -
38 | Pimpalgaon Kolte | Nandini Construction | 47,53,154 | 30-12-2022 | 15 Months | 14.35% | - | -
39 | Wadi Kh | Nandini Construction | 71,89,457 | 21-09-2022 | 18 Months | 10.58% | 9.04% | 6.50

## Slide 25: Abstract of Schemes – Work in Progress Category – “New”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
40 | Pimpalgaon Thote | Nandini Construction | 67,20,665 | 16-09-2022 | 18 Months | 9.99% | - | -
41 | Thigalkheda | Nandini Construction | 1,18,96,698 | 23-09-2022 | 18 Months | 7.08% | - | -
42 | Jawkheda Bk | Tushar Vishnu Kharat | 26,93,566 | 24-12-2022 | 15 Months | 6.38% | - | -
43 | Paradh Kh | Nandini Construction | 72,51,167 | 30-12-2022 | 15 Months | 6.19% | - | -
44 | Deulgaon Tad | Nandini Construction | 1,32,16,732 | 16-09-2022 | 18 Months | 5.73% | - | -
45 | Danapur | Nandini Construction | 77,25,445 | 23-09-2022 | 18 Months | 5.09% | - | -
46 | Wadi Bk. | Nandini Construction | 40,45,820 | 30-12-2022 | 15 Months | 4.91% | - | -
47 | Hasnabad | Nandini Construction | 1,99,66,183 | 30-12-2022 | 15 Months | 3.79% | - | -
48 | Walsawangi Sunderwadi | Nandini Construction | 3,67,32,657 | 06-01-2023 | 15 Months | 3.33% | - | -
49 | Avhana | Nandini Construction | 79,82,888 | 16-09-2022 | 18 Months | 2.87% | - | -
50 | Chandai Tepli | Nandini Construction | 27,10,708 | 28-10-2022 | 16 Months | 2.42% | - | -
51 | Adgaon Wadi | Nandini Construction | 49,71,601 | 30-12-2022 | 15 Months | 1.84% | - | -
52 | Umarkheda | Nandini Construction | 99,53,000 | 16-09-2022 | 18 Months | 0.86% | - | -
53 | Wadod Tangda | Nandini Construction | 1,26,07,032 | 28-11-2022 | 18 Months | 0.68% | - | -

## Slide 26: Abstract of Schemes – Work in Progress Category – “New”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
54 | Palaskheda Pimple | Nandini Construction | 1,92,30,252 | 14-10-2022 | 18 Months | 0.62% | - | -
55 | Chetak Nagar , M Pratap Nagar (Tadegaon) | Nandini Construction | 37,59,907 | 28-12-2022 | 15 Months | 0.56% | - | -
56 | Pokhari | Arjun Ganesh Dhale | 39,70,523 | 09-01-2023 | 15 Months | 0.45% | - | -
57 | Dahigaon Bhok | Nandini Construction | 1,24,27,531 | 28-11-2022 | 18 Months | 0.41% | 32.49% | 40.38
58 | Baranjale Sable | Nandini Construction | 33,08,423 | 30-12-2022 | 15 Months | 0.39% | - | -
59 | Bhorkheda | S.Rl. Construction | 62,66,876 | 23-11-2022 | 18 Months | 0.38% | - | -
60 | Ahilya Nagar (Jalgaon Sapkal) | Shiveshwar Mss Maryadit | 10,96,700 | 18-02-2023 | 6 Months | 0.37% | - | -
61 | Kukdi Wakdi | Nandini Construction | 82,65,200 | 30-12-2022 | 15 Months | 0.35% | - | -
62 | Hisoda Kh | Nandini Construction | 56,30,491 | 16-09-2022 | 18 Months | 0.25% | - | -
63 | Adgaon | Nandini Construction | 1,90,91,333 | 23-09-2022 | 18 Months | 0.24% | - | -
64 | Anwa | Nandini Construction | 4,54,84,350 | 06-01-2023 | 15 Months | 0.22% | - | -
65 | Anwa Pada | Nandini Construction | 3,31,30,851 | 06-01-2023 | 15 Months | 0.19% | - | -
66 | Hisoda Bk | Nandini Construction | 1,48,62,563 | 23-09-2022 | 18 Months | 0.17% | - | -

## Slide 27: Abstract of Schemes – Work in Progress Category – “New”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
Ghanswangi Taluka | Ghanswangi Taluka |  |  |  |  |  |  | 
67 | Mohpuri | Pooja Mss | 23,70,493 | 14-03-2022 | 12 Months | 82.09% | - | -
68 | Rajegaon | B.N Udhan | 1,73,21,792 | 15-08-2022 | 18 Months | 50.69% | 40.96% | 70.95
69 | Manepuri | Mayur Construction | 86,52,918 | 12-09-2022 | 18 Months | 44.52% | 23.84% | 20.63
70 | Krishna Nagar | Kailash Ubale | 1,24,41,932 | 20-08-2022 | 18 Months | 32.13% | - | -
71 | Yawala | Ajinkya Ramrao Rathod | 31,46,200 | 17-11-2022 | 18 Months | 30.97% | - | -
72 | Kothi | Sachin Enterprises | 14,23,216 | 12-02-2022 | 6 Months | 18.55% | - | -
73 | Rawana | Shrikant Bhanudas Ghule | 1,57,84,878 | 23-11-2022 | 18 Months | 18.41% | 12.88% | 20.33
74 | Pudali Kd | B. N Udhan | 47,95,140 | 06-04-2022 | 18 Months | 18.16% | - | -
75 | Pimparkheda Bk | B.N Udhan | 1,48,42,565 | 17-08-2022 | 18 Months | 15.81% | - | -
76 | Raniuchegaon Ghan | Kailash Ubale | 1,03,02,825 | 13-09-2022 | 18 Months | 7.31% | - | -
77 | Ghonsi Tanda.No:- 2 | Sameer Construction | 89,13,688 | 29-09-2022 | 18 Months | 6.60% | - | -
78 | Ramasgaon | Bappasaheb Narhari Uddhan | 58,25,395 | 21-09-2022 | 18 Months | 5.30% | - | -
79 | Ghanegaon | Ravi Manojkumar Bhakkad | 43,44,332 | 11-08-2022 | 18 Months | 4.50% | - | -
80 | Dahalegaon | Mayur Construction | 85,96,963 | 05-12-2022 | 18 Months | 2.23% | - | -

## Slide 28: Abstract of Schemes – Work in Progress Category – “New”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
81 | Bodkha Bk | Pawan Shivaji Surang | 45,34,510 | 20-10-2022 | 18 Months | 2.15% | - | -
82 | Paradgaon | B.N Udhan | 1,86,88,267 | 23-11-2022 | 18 Months | 1.56% | - | -
83 | Bhogaon | Bappasaheb Narhari Udhan | 81,44,609 | 21-09-2022 | 18 Months | 1.35% | - | -
84 | Rahera | B.N Udhan | 84,85,941 | 09-12-2022 | 18 Months | 1.24% | - | -
85 | Maherjawala (Lamhanwdi) | Sachin Enterprises | 1,01,24,489 | 05-01-2023 | 15 Months | 1.08% | - | -
86 | Jamb Samarth | Sambhaji Sirsath | 1,36,75,649 | 02-01-2023 | 15 Months | 0.85% | - | -
87 | Bhadali Khu. | Mayur Construction | 1,00,04,341 | 16-09-2022 | 18 Months | 0.69% | - | -
88 | Antarwali Tembhi | Mayur Construction | 1,28,44,950 | 22-08-2022 | 18 Months | 0.36% | - | -
89 | Raja Takli | Sameer Construction | 1,28,94,582 | 12-12-2022 | 15 Months | 0.31% | - | -
90 | Rajurkar Kotha | Sameer Construction | 42,21,664 | 29-09-2022 | 18 Months | 0.26% | - | -
91 | Ranjani | Shrikant Bhanudas Ghule | 1,66,03,625 | 23-11-2022 | 18 Months | 0.21% | - | -
92 | Kothala Tanda | Mrunal Dhabe | 17,55,378 | 05-01-2023 | 15 Months | 0.19% | - | -
93 | Kumbhar Pimpalgaon Tanda | Shreekant Bhanudas Ghule | 1,95,64,211 | 03-01-2023 | 15 Months | 0.18% | - | -
94 | Machindranath Chincholi | Kailash Ubale | 1,82,46,398 | 02-12-2022 | 18 Months | 0.14% | - | -

## Slide 29: Abstract of Schemes – Work in Progress Category – “New”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
95 | Mangrul | Kailash Laxman Ubale | 1,81,72,232 | 23-11-2022 | 18 Months | 0.14% | - | -
Jafrabad Taluka | Jafrabad Taluka |  |  |  |  |  |  | 
96 | Konad Bk(Ahilyabai Holkar Wasthi) | Sarpanch/ Gramsevak | 2,56,282 | 27-12-2022 | 3 Months | 77.58% | - | -
97 | Devulzari | Srl Ltd | 89,98,721 | 23-03-2022 | 18 Months | 44.96% | - | -
98 | Bharaj Kh | S.R.L Construction | 71,37,953 | 16-09-2022 | 18 Months | 28.15% | - | -
99 | Merkheda | S.R.L Construction | 80,58,337 | 23-11-2022 | 18 Months | 23.25% | - | -
100 | Ambegaon | S.R.L Construction Ltd | 73,41,572 | 05-01-2023 | 15 Months | 7.75% | - | -
101 | Borgaon Math | Vishal Shinde | 29,36,859 | 25-08-2022 | 12 Months | 2.80% | - | -
102 | Gondhankheda | S.R.L. Construction Ltd | 79,67,674 | 23-09-2022 | 18 Months | 2.45% | - | -
103 | Janefal Pandit | S. R. L Construction Ltd | 1,05,88,260 | 05-01-2023 | 15 Months | 1.97% | - | -
104 | Yeota | S.R.L Construction | 1,05,58,736 | 23-09-2022 | 18 Months | 1.71% | - | -
105 | Borkhedi Gaiki | S.R.L Construction | 42,14,448 | 23-12-2022 | 15 Months | 1.23% | - | -
106 | Tapovan Gondhan | Sudhir Shankarrao Mapari | 87,77,373 | 08-11-2022 | 18 Months | 1.08% | - | -
107 | Gokulwadi Aradkheda.1 | Sandipan Ghare | 94,69,150 | 31-05-2022 | 18 Months | 1.01% | - | -

## Slide 30: Abstract of Schemes – Work in Progress Category – “New”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
108 | Nimkheda Bk | S.R.L Construction Ltd | 77,31,485 | 16-09-2022 | 18 Months | 0.77% | - | -
109 | Wadala | Chairmen Yamuna Majur Sahkari Sanstha Maryadit | 23,07,761 | 28-09-2022 | 12 Months | 0.63% | - | -
110 | Sawarkheda | Vishal Sarjrao Shinde | 30,51,019 | 23-12-2022 | 15 Months | 0.49% | - | -
111 | Mhasrul | S.R.L Ltd Khasgaon | 1,15,22,563 | 09-05-2022 | 18 Months | 0.34% | - | -
112 | Ambegaon (Dhakewadi) | S.R.L Ltd Khasgaon | 87,23,073 | 09-05-2022 | 18 Months | 0.29% | - | -
113 | Bharaj Bk | S.R.L Construction Ltd | 2,23,49,430 | 09-01-2023 | 15 Months | 0.17% | - | -
Jalna Taluka | Jalna Taluka |  |  |  |  |  |  | 
114 | Loundhiyachiwadi | Chairmen Sarvdharm Sambhav Mss | 21,67,116 | 09-05-2022 | 12 Months | 46.83% | - | -
115 | Samangaon | Ajinkya Ramrav Rathod | 1,15,23,858 | 17-11-2022 | 18 Months | 34.52% | - | -
116 | Rohanwadi | Sameer Construction | 69,27,468 | 09-12-2022 | 18 Months | 21.57% | - | -
117 | Tandulwadi Kh | Sameer Construction | 58,55,809 | 09-12-2022 | 18 Months | 15.73% | - | -
118 | Gawali Pokhari | Ajinkya Ramrao Rathod | 95,85,264 | 28-11-2022 | 18 Months | 14.12% | - | -
119 | Ambedkar Nagar | Pooja Mss | 25,83,061 | 09-12-2022 | 12 Months | 8.55% | - | -
120 | Tandulwadi Bk | Gyaneshwar R. Jarhad | 75,57,211 | 17-11-2022 | 18 Months | 7.32% | - | -

## Slide 31: Abstract of Schemes – Work in Progress Category – “New”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
121 | Revgaon | D.R. Jarhad | 1,64,07,524 | 14-10-2022 | 18 Months | 7.24% | - | -
122 | Wanadgaon | Pawan Surang | 34,45,539 | 25-08-2022 | 12 Months | 3.27% | - | -
123 | Golawadi | Mayur Construction | 60,20,522 | 22-08-2022 | 18 Months | 2.93% | - | -
124 | Bapkal | D.R Jarad | 77,04,487 | 25-08-2022 | 18 Months | 1.80% | - | -
125 | Gondegaon | Gyaneshwar R. Jarhad | 1,18,19,843 | 17-11-2022 | 18 Months | 1.74% | - | -
126 | Jamwadi | Sambhaji Sirsath | 1,80,60,000 | 27-12-2022 | 15 Months | 1.51% | - | -
127 | Pirkalyan | Sameer Construction | 66,49,583 | 21-10-2022 | 18 Months | 1.11% | - | -
128 | Dhavedi Thar | Sameer Construction | 1,08,08,604 | 10-08-2022 | 18 Months | 0.77% | - | -
129 | Solgavhan | Mayur Construction | 69,98,833 | 12-01-2023 | 15 Months | 0.11% | - | -

## Slide 32: Abstract of Schemes – Work Completed Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
Ambad Taluka | Ambad Taluka |  |  |  |  |  |  | 
1 | Dhakalgaon | Sameer Construction | 23,77,151 | 26-04-2022 | 12 Months |  |  | 
2 | Dungaon | Sameer Construction | 10,18,171 | 20-01-2022 | 6 Months |  |  | 
3 | Ganga Chincholi | Gauri Construction | 7,31,790 | 14-10-2021 | 6 Months |  |  | 
4 | Kaudgaon |  | 14,99,000 | 03-03-2022 | 12 Months |  |  | 
5 | Pagirwadi |  | 14,98,000 | 27-12-2021 | 6 Months |  |  | 
6 | Badapur | Sarpanch/ Gramsevak | 4,27,223 | 14-03-2022 | 3 Months |  |  | 
Badnapur Taluka | Badnapur Taluka |  |  |  |  |  |  | 
7 | Dhamangaon | Nayan Nanasaheb Nannware | 23,07,095 | 10-05-2022 | 12 Months |  |  | 
Ghanswangi Taluka | Ghanswangi Taluka |  |  |  |  |  |  | 
8 | Mangu Jalgaon | Pooja Mss | 23,90,086 | 14-03-2022 | 12 Months |  |  | 
Jafrabad Taluka | Jafrabad Taluka |  |  |  |  |  |  | 
9 | Bramhapuri | Sameer Construction | 10,61,596 | 18-04-2022 | 6 Months |  |  | 

## Slide 33: Abstract of Schemes – Work Completed Category – “New”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
Ghanswangi Taluka | Ghanswangi Taluka |  |  |  |  |  |  | 
1 | Yawalpimpri Tanda |  | 14,28,000 | 14-10-2021 |  |  |  | 

## Slide 34
Dashboard

## Slide 35
Dashboard
Work Status

## Slide 36
Dashboard
Progress Milestone

## Slide 37
Dashboard
Work Status – “New” Schemes
Work Status – “Retro” Schemes

## Slide 38
MS Project
Work in Progress Schemes

## Slide 39
Sample Site Visit Photos

## Slide 40
Taluka

## Slide 41
Thank You!