## Data
Category | Scheme Type | Taluka | Village Name | Net Cost (excl GST) | W.O. Amount (excl GST) | W.O. Date | Construction Period | Trial & Run | Physical Progress | Financial Progress | Cost Over-run (Sanctioned) | Cost Over-run (Not Sanctioned) | Name Of Agency
Retro | PMC | Aurangabad | Girnar Tanda | 12,79,706 | 12,79,706 | 2022-05-15 | 3 Months | 3 | 83.89% | 69.91% | 8.95 |  | Nilesh Chavan
Retro | PMC | Aurangabad | Karodi | 16,64,705 | 16,06,431 | 28-07-2022 | 3 Months | 3 | 67.22% | 6-.21% | - |  | Shree Satynarayan Sandulal Jajure
Retro | PMC | Aurangabad | Gangapur Nehari | 29,71,866 | 29,15,304 | 23-01-2023 | 3 Months | 3 | 39.3% | - | - | 0% | Shree Mahesh Babanrao Pere
Retro | PMC | Aurangabad | Bhindon | 25,09,567 | 22,83,695 | 2022-07-06 | 3 Months | 3 | 35.25% | 35.-8% | - |  | Shree Satyanarayan Sandulal Jajure
Retro | PMC | Aurangabad | Shindon | 34,61,244 | 31,49,725 | 2022-07-06 | 3 Months | 3 | 30.09% | 29.12% | 9.17 |  | Shree Sataynarayan Sandulal Jajure
Retro | PMC | Aurangabad | Jatwada | 35,68,053 | 33,86,082 | 23-01-2023 | 5 Months | 3 | 18.26% | - | - |  | Shree Ashok Nanaji Randhe
Retro | PMC | Aurangabad | Pardari & Pardari Tanda | 47,12,043 | 47,43,303 | 2023-02-01 | 6 Months | 3 | 12.83% | 11.47% | 5.44 | 0% | Nilesh Construction
Retro | PMC | Aurangabad | Kachhighati | 10,11,937 | 10,11,937 | 31-03-2022 | 3 Months | 3 | 0.92% | - | - | 0% | Sarpanch , Grampanchayat - Sultanpur
Retro | PMC | Aurangabad | Georai Kuber | 11,82,267 | 11,82,267 | 2022-06-23 | 3 Months | 3 | 0.51% | - | - | 0% | Sarpanch, Grampanchayat - Georai Kuber
Retro | PMC | Aurangabad | Shendraban & Gangapur | 16,63,908 | 15,63,077 | 2022-12-30 | 6 Months | 3 | 0.44% | - | - | 0% | Shree Yogesh Uttamrao Rathod
Retro | PMC | Aurangabad | Kankora | 4,35,699 | 4,35,699 | 23-06-2022 | 3 Months | 3 | 0.39% | - | - | 0% | Sarpanch Grampanchayat - Sarola
Retro | PMC | Aurangabad | Satana | 14,94,188 | 15,80,255 | 2022-09-12 | 3 Months | 3 | 0.25% | - | - | 0% | Shree Sudarshan Dilip Bhatane
Retro | PMC | Aurangabad | Pirwadi | 7,49,071 | 7,49,071 | 23-06-2022 | 3 Months | 3 | 0.23% | - | - | 0% | Sarpanch , Grampanchayat - Pirwadi
Retro | PMC | Aurangabad | Dudhad | 26,53,525 | 26,53,501 | 2023-01-30 | 6 Months | 3 | 0.22% | - | - | 0% | Amogh Dadarao Dakore
Retro | PMC | Aurangabad | Garkheda | 24,29,293 | 24,05,153 | 30-01-2023 | 6 Months | 3 | 0.17% | - | - | 0% | Shrimati Punam Tushar Ghodake
Retro | PMC | Aurangabad | Karmad | 62,15,118 | 60,56,627 | 31-01-2023 | 9 Months | 3 | 0.17% | - | - | 0% | M/S Khushi Construction
Retro | PMC | Aurangabad | Takli Shimpi&Takli Vaidya | 10,88,941 | 10,88,941 | 28-07-2022 | 3 Months | 3 | 0.17% | - | - | 0% | Sarpanch, Grampanchayat - Nipani
Retro | PMC | Aurangabad | Ghardon | 53,44,126 | 50,94,479 | 17-11-2022 | 6 Months | 3 | 0.15% | - | - | 0% | Shree Uttamrao Rathod
Retro | PMC | Aurangabad | Daigavhan | 37,46,624 | 35,96,639 | 22-11-2022 | 3 Months | 3 | 0.14% | - | - | 0% | M/S Ghuge Construction
Retro | PMC | Aurangabad | Pimpalkhuta & Kanchanpur | 1,24,44,173 | 1,20,43,429 | 2022-12-27 | 18 Months | 3 | 0.14% | - | - | 0% | M/S S P Construction
Retro | PMC | Aurangabad | Bagtalab | 17,77,339 | 17,77,320 | 23-01-2023 | 3 Months | 3 | 0.14% | - | - | 0% | Amogh Dadarao Dakore
Retro | PMC | Aurangabad | Patoda | 35,04,408 | 34,73,852 | 20-02-2023 | 3 Months | 3 | 0.14% | - | - | 0% | Shree Mahesh Babanrao Pere
Retro | PMC | Aurangabad | Murumkheda | 62,76,082 | 62,14,497 | 23-01-2023 | 9 Months | 3 | 0.13% | - | - | 0% | Shree Atul Laxman Jadhao
Retro | PMC | Aurangabad | Donwada | 25,12,476 | 25,12,467 | 2022-12-30 | 6 Months | 3 | 0.11% | - | - | 0% | M/S Sparsha Infra
Retro | PMC | Aurangabad | Laygaon | 20,68,339 | 26,72,566 | 23-01-2023 | 5 Months | 3 | 0.1% | - | - | 0% | Shree Asaram Govindrao Pawar
Retro | PMC | Aurangabad | Wadkha | 96,50,865 | 1,10,98,524 | 30-06-2022 | 18 Months | 3 | 0.1% | - | - | 0% | Shree Pramod Kakasaheb Kawade
Retro | PMC | Aurangabad | Borwadi Tanda | 52,96,349 | 48,19,118 | 20-02-2023 | 6 Months | 3 | 0.1% | - | - | 0% | Shree Mangesh Shrichand Rothod
Retro | PMC | Aurangabad | Hirapur | 24,31,248 | 23,88,691 | 23-01-2023 | 3 Months | 3 | 0.1% | - | - | 0% | Shree Sachin Raghunath Rithe
Retro | PMC | Aurangabad | Kadrabad & Ibrahimpur. | 92,10,230 | 90,54,740 | 30-01-2023 | 18 Months | 3 | 0.09% | - | - | 0% | M/S Ghuge Construction
Retro | PMC | Aurangabad | Malkapur | 25,44,046 | 24,85,842 | 23-01-2023 | 6 Months | 3 | 0.09% | - | - | 0% | Sandip Niwrutti Aawhad
Retro | PMC | Aurangabad | Sanjkheda | 23,15,511 | 26,40,913 | 30-01-2023 | 6 Months | 3 | 0.08% | - | - | 0% | Mahesh Babanrao Pere
Retro | PMC | Aurangabad | Tongaon | 74,70,432 | 70,13,971 | 2022-12-14 | 6 Months | 3 | 0.07% | - | - | 0% | Nilesh Uttamrao Rathod
Retro | PMC | Aurangabad | Golatgaon | 1,17,89,045 | 1,13,00,010 | 23-01-2023 | 18 Months | 3 | 0.06% | - | - | 0% | Shivsai Construction Pvt Ltd
Retro | PMC | Aurangabad | Bebalyachiwadi | 29,69,623 | 29,40,150 | 2023-01-31 | 6 Months | 3 | 0.05% | - | - | 0% | Shree Shyamsingh Suresh Shihire
Retro | PMC | Aurangabad | Chitegaon | 1,08,36,893 | 99,80,601 | 30-01-2023 | 18 Months | 3 | 0.04% | - | - | 0% | Shrimati Punam Tushar Ghodake
Retro | PMC | Aurangabad | Daregaon& Konewadi | 1,23,47,884 | 1,23,02,793 | 20-02-2023 | 9 Months | 3 | 0.04% | - | - | 0% | M/S Mayur Construction
Retro | PMC | Aurangabad | Darakwadi | 73,29,309 | 69,25,452 | 30-01-2023 | 9 Months | 3 | 0.03% | - | - | 0% | Sandip Niwrutti Aawhad
Retro | PMC | Aurangabad | Mahmadpur & Eklahara | 56,69,281 | 53,64,349 | 30-01-2023 | 9 Months | 3 | 0.03% | - | - | 0% | Sandip Niwrutti Aawhad
Retro | PMC | Aurangabad | Hatmali | 87,30,718 | 94,28,296 | 13-02-2023 | 9 Months | 3 | 0.02% | - | - | 0% | M/S Ruchita Construction
Retro | PMC | Gangapur | Malunja Bk | 17,58,555 | 17,70,669 | 18-07-2022 | 4 Months | 3 | 100% | - | - |  | Shree Deepak Manikraw Ambalike
Retro | PMC | Gangapur | Ekburji | 6,62,339 | 6,62,339 | 2022-03-31 | 3 Months | 3 | 100% | 46.16% | 3.06 |  | Sarpanch, Gram Panchayat (Wasusaigaon)Ekbhurji Waghalgaon & Shahanawajpur
Retro | PMC | Gangapur | Fultabad & Sidhi Sirajgaon | 10,28,132 | 10,28,132 | 23-06-2022 | 3 Months | 3 | 100% | 71.83% | 7.39 |  | Sarpanch, Grampanchayat-Fatulabad
Retro | PMC | Gangapur | Sultanpur | 4,81,811 | 4,81,811 | 31-03-2022 | 3 Months | 3 | 100% | 7-.99% | - |  | Sarpanch,Gram Panchayat, Sultanpur (Guru Dhanora)
Retro | PMC | Gangapur | Pandharohal | 12,52,137 | 12,52,137 | 2022-04-03 | 3 Months | 3 | 100% | 75.5% | 9.45 |  | Sarpanch,Gram, Panchayat, Pandharohal
Retro | PMC | Gangapur | Sultanbad | 13,01,063 | 13,66,063 | 2022-11-01 | 3 Months | 3 | 100% | 76.37% | 10.43 | 0% | Sarpanch Grampanchayat - Sultanbad
Retro | PMC | Gangapur | Apegaon & Govindpur | 11,65,712 | 11,65,712 | 23-02-2022 | 3 Months | 3 | 100% | 56.8% | 6.62 |  | Sarpanch, Gram Panchayat - Ranjangaon Pol
Retro | PMC | Gangapur | Shirodi | 18,63,893 | 18,46,167 | 19-10-2022 | 6 Months | 3 | 100% | - | - | 0% | Shree Shrikesh Prabhakar Sonwane
Retro | PMC | Gangapur | Tembhapuri, Chandikpur, Antapur | 18,48,072 | 18,32,188 | 2022-09-12 | 6 Months | 3 | 100% | - | - | 0% | Shree Swastik Jagannath Fulare
Retro | PMC | Gangapur | Jamgaon | 62,79,419 | 59,41,826 | 24-11-2022 | 6 Months | 3 | 100% | - | - | 0% | M/S Sancheti Associates
Retro | PMC | Gangapur | Mudhesh Wadgaon | 32,11,772 | 30,79,777 | 19-10-2022 | 3 Months | 3 | 100% | 87% | 26.79 | 0% | Sancheti Associates - Kirtikumar Chandanmal Sancheti
Retro | PMC | Gangapur | Murshidabad | 8,94,131 | 8,94,130 | 31-03-2022 | 3 Months | 3 | 100% | - | - | 0% | Sarpanch Grampanchayat- Murshidabad (Guru Dhanora)
Retro | PMC | Gangapur | Palasgaon | 10,30,988 | 10,30,988 | 2022-03-31 | 3 Months | 3 | 100% | 66.44% | 6.85 | 0% | Sarpanch Grampanchayat - Palasgaon (Shahapur)
Retro | PMC | Gangapur | Rahimpur | 11,18,074 | 11,18,074 | 31-03-2022 | 3 Months | 3 | 100% | 59.43% | 6.64 | 0% | Sarpanch Grampanchayat - Rahimpur (Limbe Jalgaon)
Retro | PMC | Gangapur | Dhoregaon | 14,34,921 | 14,20,550 | 24-08-2022 | 3 Months | 3 | 100% | - | - | 0% | Shree Alim Gafur Sheikh
Retro | PMC | Gangapur | Borgaon | 13,89,071 | 13,82,912 | 31-10-2022 | 3 Months | 3 | 100% | 78.45% | 10.85 | 0% | Shree Sachin Dadasaheb Shelake
Retro | PMC | Gangapur | Gavali Shivra | 11,17,857 | 11,17,857 | 2022-06-23 | 3 Months | 3 | 100% | - | -
Retro | PMC | Gangapur | Deokarwadi | 8,01,168 | 8,01,168 | 2022-03-31 | 3 Months | 3 | 100% | - | - | 0% | Sarpanch - Gram Panchayat, Manegaon.
Retro | PMC | Gangapur | Bolegaon | 11,04,475 | 10,04,477 | 28-07-2022 | 3 Months | 3 | 100% | - | - | 0% | Grampanchayat Sarpanch
Retro | PMC | Gangapur | Padampur | 4,92,251 | 4,92,260 | 31-03-2022 | 3 Months | 3 | 100% | - | - | 0% | Gram Panchayat
Retro | PMC | Gangapur | Shivpur | 9,83,672 | 9,89,679 | 23-06-2022 | 3 Months | 3 | 100% | - | - | 0% | Gram Panchayat
Retro | PMC | Gangapur | Domegaon | 50,53,167 | 47,98,471 | 2023-01-16 | 6 Months | 3 | 96.5% | - | - | 0% | Shree Parwej Bhikan Patel
Retro | PMC | Gangapur | Sawkheda | 26,51,284 | 27,55,631 | 2022-10-21 | 3 Months | 3 | 96.41% | - | - | 0% | Shree Rahul Balasaheb Udage
Retro | PMC | Gangapur | Rampuri | 11,74,605 | 11,74,568 | 2022-07-09 | 3 Months | 3 | 96.06% | - | - | 0% | Gram Panchayat
Retro | PMC | Gangapur | Kaigaon | 18,69,691 | 17,71,413 | 22-12-2022 | 3 Months | 3 | 95.59% | - | - | 0% | Shree Rahul Balasaheb Udage
Retro | PMC | Gangapur | Yesgaon | 31,17,254 | 29,90,103 | 2022-10-31 | 6 Months | 3 | 94.85% | - | - | 0% | Shree Shrikesh Prabhakar Sonawane
Retro | PMC | Gangapur | Mendhi | 11,19,674 | 11,19,675 | 28-07-2022 | 3 Months | 3 | 92.59% | - | - | 0% | Gram Panchayat
Retro | PMC | Gangapur | Tandulwadi | 7,97,576 | 7,97,576 | 31-03-2022 | 3 Months | 3 | 88.37% | 68.29% | 5.45 | 0% | Sarpanch Grampanchayat - Tandulwadi
Retro | PMC | Gangapur | Wasusaigaon | 13,69,936 | 13,69,936 | 2022-11-04 | 3 Months | 3 | 88.15% | - | - | 0% | Shree Swastik Jagannath Fulare
Retro | PMC | Gangapur | Pachpirwadi | 17,68,050 | 17,28,131 | 24-08-2022 | 4 Months | 3 | 87.67% | 55.63% | 9.61 | 0% | Mujib Sheikh Badshaha Patel
Retro | PMC | Gangapur | Diwashi | 15,57,285 | 15,41,718 | 2023-01-23 | 6 Months | 3 | 84.48% | - | - | 0% | Shree Swastik Jagganath Fulare
Retro | PMC | Gangapur | Mandwa | 13,19,869 | 13,19,867 | 2022-11-24 | 3 Months | 3 | 83.73% | - | - | 0% | Shree Rahul Balasaheb Udage
Retro | PMC | Gangapur | Puri | 5,27,346 | 5,27,346 | 2022-04-03 | 3 Months | 3 | 78.9% | 56.74% | 2.99 |  | Sarpanch, Gram Panchayat, Puri
Retro | PMC | Gangapur | Siddhanth Wadgaon | 22,92,523 | 24,00,475 | 28-07-2022 | 3 Months | 3 | 77.93% | - | - | 0% | Shree Pramod Kakasaheb Kawade
Retro | PMC | Gangapur | Nawabpur | 17,40,887 | 17,01,242 | 15-11-2022 | 3 Months | 3 | 77.07% | - | - | 0% | Shree Sandeep Namdeo Borde
Retro | PMC | Gangapur | Pendapur | 5,33,811 | 5,33,811 | 2022-03-31 | 3 Months | 3 | 73.57% | 55.-2% | - | 0% | Sarpanch Grampanchayat - Pendapur
Retro | PMC | Gangapur | Bhagathan | 11,65,304 | 11,65,304 | 2022-04-03 | 3 Months | 3 | 72.67% | - | - |  | Sarpanch, Grampanchayat-Bhagathan
Retro | TSP | Gangapur | Nevargaon | 1,12,73,766 | 1,10,07,804 | 19-10-2022 | 18 Months | 3 | 62.37% | - | - | 0% | Shree Akshay Dileep Manjare
Retro | PMC | Gangapur | Kasoda | 31,45,667 | 31,07,745 | 2022-11-17 | 3 Months | 3 | 55.51% | - | - | 0% | Shree Mayur Ramakant Banasod
Retro | PMC | Gangapur | Guru Dhanora | 14,82,182 | 14,00,743 | 2022-09-12 | 6 Months | 3 | 48.18% | - | - | 0% | Shree Swastik Jagannath Fulare
Retro | PMC | Gangapur | Asegaon + Talesaman | 21,62,249 | 19,83,378 | 2022-09-12 | 6 Months | 3 | 39.78% | - | - | 0% | Shree Swastik Jagannath Fulare
Retro | PMC | Gangapur | Shahapur Banjar | 6,11,257 | 6,11,257 | 31-03-2022 | 3 Months | 3 | 37.7% | - | - |  | Sarpanch, Grampanchayat-Shahapur Banjar
Retro | PMC | Gangapur | Toki, Bargipur | 17,48,195 | 17,28,336 | 2022-09-12 | 6 Months | 3 | 35.93% | - | - | 0% | Shree Mayur Ramakant Banasod
Retro | PMC | Gangapur | Bhendala | 24,75,464 | 23,88,926 | 30-01-2023 | 3 Months | 3 | 31.78% | - | - | 0% | Rahul B Udage
Retro | PMC | Gangapur | Vairagad | 22,36,622 | 21,86,082 | 2022-09-12 | 3 Months | 3 | 28.14% | - | - | 0% | Shree Sachin Dadasaheb Shelake
Retro | PMC | Gangapur | Mahalaxmi Kheda | 12,07,135 | 12,07,135 | 28-07-2022 | 3 Months | 3 | 26.22% | - | - | 0% | Sarpanch - Grampanchayat Mangegaon
Retro | PMC | Gangapur | Khadak Narla | 18,89,204 | 18,50,362 | 17-11-2022 | 3 Months | 3 | 25.32% | - | - | 0% | Shree Mayur Ramakant Banasod
Retro | PMC | Gangapur | Butte Wadgaon | 22,29,293 | 21,81,876 | 26-09-2022 | 3 Months | 3 | 24.24% | - | - | 0% | Shree Vinayak Popatrao More -Aurangabad
Retro | PMC | Gangapur | Kolghar | 13,84,702 | 14,76,597 | 2022-10-10 | 3 Months | 3 | 20.81% | - | - | 0% | Shree Dipak Manikrao Ambalike
Retro | PMC | Gangapur | Warzadi | 12,79,316 | 12,79,318 | 2022-07-09 | 3 Months | 3 | 18% | - | - | 0% | Gram Panchayat
Retro | PMC | Gangapur | Potul | 17,39,654 | 17,39,641 | 16-09-2022 | 3 Months | 3 | 16.38% | - | - | 0% | Mujib Sheikh Badshaha Patel
Retro | PMC | Gangapur | Warkhed | 20,68,906 | 20,49,043 | 18-07-2022 | 4 Months | 3 | 0.1% | - | - |  | Shree Deepak Manikrao Ambalike
Retro | PMC | Gangapur | Agar Kanadgaon- Gangapur | 5,10,866 | 5,10,866 | 2022-04-03 | 3 Months | 3 | 0.08% | - | - | 0% | Sarpanch Grampanchayat - Agar Kanadgaon
Retro | PMC | Gangapur | Murmi | 3,58,605 | 3,58,604 | 2022-03-31 | 3 Months | 3 | 0.05% | - | - | 0% | Gram Panchayat
Retro | PMC | Gangapur | Rotasthal | 3,38,108 | 3,38,107 | 31-03-2022 | 3 Months | 3 | 0.05% | - | - | 0% | Gram Panchayat
Retro | PMC | Gangapur | Surewadi | 3,64,004 | 3,63,969 | 31-03-2022 | 3 Months | 3 | 0.05% | - | - | 0% | Gram Panchayat
Retro | PMC | Gangapur | Nagapur | 3,60,593 | 3,60,595 | 31-03-2022 | 3 Months | 3 | 0.05% | - | - | 0% | Gram Panchayat
Retro | PMC | Gangapur | Wadali | 14,64,425 | 16,64,200 | 2022-03-04 | 3 Months | 3 | 0.04% | - | - | 0% | Sarpanch, Grampanchayat - Wadali
Retro | PMC | Gangapur | Lanzi | 13,44,358 | 13,31,167 | 2022-11-11 | 3 Months | 3 | 0.04% | - | - | 0% | Shree Laveshkumar Uttamrao Pawar
Retro | PMC | Gangapur | Harsul | 27,62,049 | 26,87,373 | 2022-12-09 | 6 Months | 3 | 0.04% | - | - | 0% | Shree Sachin Dadasaheb Shelake
Retro | PMC | Gangapur | Kodapur | 19,50,777 | 19,99,084 | 2022-06-10 | 3 Months | 3 | 0.03% | - | - | 0% | Shree Ajinkya Ramrao Rathod
Retro | PMC | Gangapur | Aurangpur & Harsuli | 16,49,827 | 16,08,684 | 23-01-2023 | 3 Months | 3 | 0.03% | - | - | 0% | Shree Vikas Tarachand Tejinkar
Retro | PMC | Gangapur | Bargipur | 15,73,761 | 17,28,336 | 2022-09-12 | 3 Months | 3 | 0.03% | - | - | 0% | Mr. Mayur Ramakant Bansod
Retro | PMC | Gangapur | Mahmadpur(Devali) | 4,26,589 | 11,53,681 | 2022-09-07 | 3 Months | 3 | 0.03% | - | - | 0% | Gram Panchayat
Retro | PMC | Gangapur | Maujudabad | 5,41,897 | 5,41,860 | 23-06-2022 | 3 Months | 3 | 0.03% | - | - | 0% | Gram Panchayat
Retro | PMC | Gangapur | Mendhipur | 6,25,611 | 6,25,616 | 31-03-2022 | 3 Months | 3 | 0.03% | - | - | 0% | Gram Panchayat
Retro | PMC | Gangapur | Bhoigaon | 20,83,682 | 19,05,976 | 2022-06-10 | 3 Months | 3 | 0.02% | - | - | 0% | Shree Ajinkya Ramrao Rathod
Retro | PMC | Gangapur | Pakhora | 16,20,156 | 15,76,184 | 23-09-2022 | 3 Months | 3 | 0.02% | - | - | 0% | Mujib Sheikh Badshaha Patel
Retro | PMC | Gangapur | Shekta | 14,96,152 | 14,54,005 | 24-11-2022 | 3 Months | 3 | 0.02% | - | - | 0% | Shree Sandeep Namadeo Borde
Retro | PMC | Gangapur | Siresaigaon | 14,58,460 | 14,21,827 | 2022-11-17 | 3 Months | 3 | 0.02% | - | - | 0% | Shree Sandeep Namadeo Borde
Retro | PMC | Gangapur | Maliwadgaon | 25,30,567 | 24,53,447 | 31-01-2023 | 3 Months | 3 | 0.02% | - | - | 0% | Mr Aditya Umesh Limbhare
Retro | PMC | Gangapur | Malunja Kh | 17,45,741 | 17,70,669 | 2022-07-18 | 4 Months | 3 | 0.02% | - | - | 0% | Shree Dipak Manikrao Ambalike
Retro | PMC | Gangapur | Shahapur | 16,31,226 | 16,14,844 | 24-01-2023 | 6 Months | 3 | 0.02% | - | - | 0% | Shree Swastik Jagganath Fulare
Retro | PMC | Gangapur | Shahapur Kadim | 17,07,242 | 16,90,165 | 23-01-2023 | 6 Months | 3 | 0.02% | - | - | 0% | Shree Swastik Jagganath Fulare
Retro | PMC | Gangapur | Bhivdhanora | 13,76,223 | 13,61,124 | 21-10-2022 | 3 Months | 3 | 0.02% | - | - | 0% | Sheikh Afatab Ajij
Retro | PMC | Gangapur | Sawangi, Anantpur & Lasur | 1,69,48,461 | 1,62,64,717 | 21-12-2022 | 12 Months | 3 | 0.02% | - | - | 0% | M/S S P Construction
Retro | PMC | Gangapur | Dongaon | 9,22,244 | 9,22,244 | 31-03-2022 | 3 Months | 3 | 0.02% | - | - | 0% | Sarpanch Grampanchayat - Dongaon
Retro | PMC | Gangapur | Borodi | 7,99,704 | 7,99,704 | 2022-03-31 | 3 Months | 3 | 0.02% | - | - | 0% | Sarpanch -Grampanchayat, Pandharol
Retro | PMC | Gangapur | Derda | 8,95,261 | 8,95,275 | 2022-03-31 | 3 Months | 3 | 0.02% | - | - | 0% | Gram Panchayat
Retro | PMC | Gangapur | Gokulwadi | 6,94,035 | 6,93,997 | 2022-07-09 | 3 Months | 3 | 0.02% | - | - | 0% | Gram Panchayat
Retro | PMC | Gangapur | Gopalwadi | 9,10,304 | 9,10,303 | 2022-03-31 | 3 Months | 3 | 0.02% | - | - | 0% | Gram Panchayat
Retro | PMC | Gangapur | Hirapur | 7,86,736 | 7,86,766 | 2022-06-23 | 3 Months | 3 | 0.02% | - | - | 0% | Gram Panchayat
Retro | PMC | Gangapur | Kinhal | 9,98,025 | 9,97,991 | 2022-03-31 | 3 Months | 3 | 0.02% | - | - | 0% | Gram Panchayat
Retro | PMC | Gangapur | Nagapur & Narsapur | 6,57,677 | 6,57,644 | 2022-06-23 | 3 Months | 3 | 0.02% | - | - | 0% | Gram Panchayat
Retro | PMC | Gangapur | Narayanpur Kh | 8,37,255 | 8,37,262 | 2022-07-09 | 3 Months | 3 | 0.02% | - | - | 0% | Gram Panchayat
Retro | PMC | Gangapur | Siddhapur | 7,67,743 | 7,67,716 | 23-06-2022 | 3 Months | 3 | 0.02% | - | - | 0% | Gram Panchayat
Retro | PMC | Gangapur | Shankarpuri | 5,74,533 | 5,74,533 | 23-06-2022 | 3 Months | 3 | 0.01% | - | - |  | Sarpanch, Graam Panchayat, Shankarpur
Retro | PMC | Gangapur | Sanav | 9,29,038 | 9,29,038 | 31-03-2022 | 3 Months | 3 | 0.01% | - | - |  | Sarpanch, Grampanchayat-Sanav
Retro | PMC | Gangapur | Padsala | 3,09,705 | 3,09,705 | 2022-03-31 | 3 Months | 3 | 0.01% | - | - |  | Sarpanch, Grampanchayat-Padalsa
Retro | PMC | Gangapur | Manjarpuri | 3,75,116 | 3,75,116 | 2022-03-04 | 3 Months | 3 | 0.01% | - | - |  | Sarpancha, Grampanchayat-Manjarpuri
Retro | PMC | Gangapur | Dhamori | 9,09,799 | 9,09,799 | 2022-06-23 | 3 Months | 3 | 0.01% | - | - |  | Sarpanch, Grampanchayt- Dhamori Kh.
Retro | PMC | Gangapur | Derhal | 7,73,435 | 7,73,435 | 31-03-2022 | 3 Months | 3 | 0.01% | - | - |  | Sarpanch, Grampanchayat-Derhal
Retro | PMC | Gangapur | Talpimpri | 5,74,396 | 5,74,396 | 2022-04-03 | 3 Months | 3 | 0.01% | - | - |  | Sarpanch, Gram Panchayat, Talpimpri
Retro | PMC | Gangapur | Malkapur | 4,08,214 | 4,08,214 | 2022-04-03 | 3 Months | 3 | 0.01% | - | - |  | Sarpanch, Gram Panchayat, Malkapur
Retro | PMC | Gangapur | Ambe & Mustafabad | 13,22,800 | 13,22,800 | 31-03-2022 | 3 Months | 3 | 0.01% | - | - |  | Sarpanch Gram Panchayat- Ambegaon
Retro | PMC | Gangapur | Dahegaon | 8,74,923 | 8,74,923 | 31-03-2022 | 3 Months | 3 | 0.01% | - | - |  | Sarpanch, Gram Panchayat-Dahegaon
Retro | PMC | Gangapur | Golegaon | 10,77,289 | 10,77,289 | 31-03-2022 | 3 Months | 3 | 0.01% | - | - |  | Sarpanch Gram Panchayat - Shahapur
Retro | PMC | Gangapur | Jambhala | 12,97,235 | 12,97,235 | 31-03-2022 | 3 Months | 3 | 0.01% | - | - |  | Sarpanch Gram Panchayat- Jambhala
Retro | PMC | Gangapur | Agathan | 13,49,953 | 13,91,034 | 23-01-2023 | 3 Months | 3 | 0.01% | - | - | 0% | Shree Vikas Tarachand Tejankar
Retro | PMC | Gangapur | Devali | 25,33,505 | 26,09,511 | 2022-12-12 | 3 Months | 3 | 0.01% | - | - | 0% | Shree Krushnaraj Shivaji Shinde
Retro | PMC | Gangapur | Gajgaon & Khadgaon | 38,02,411 | 36,08,115 | 2022-12-08 | 3 Months | 3 | 0.01% | - | - | 0% | Shre Mujib Sheikh Badshaha Patel
Retro | PMC | Gangapur | Kankori | 20,87,734 | 20,39,802 | 24-11-2022 | 3 Months | 3 | 0.01% | - | - | 0% | Shree Sandip Namadeo Borde
Retro | PMC | Gangapur | Mirzapur+Jikthan+Sultanpur | 22,92,800 | 20,61,006 | 2023-02-24 | 3 Months | 3 | 0.01% | - | - | 0% | Shree Abhishek Pradipkumar Patani
Retro | PMC | Gangapur | Nandrabad | 16,01,960 | 15,60,720 | 2022-10-11 | 6 Months | 3 | 0.01% | - | - | 0% | Shree Kalyan Bhausaheb Barahatte - Gangapur
Retro | PMC | Gangapur | Ranjangaon Pol & Umarpur. | 36,01,459 | 34,12,662 | 29-12-2022 | 6 Months | 3 | 0.01% | - | - | 0% | Shree Mujib Sheikh Badashaha Patel
Retro | PMC | Gangapur | Sillegaon | 28,59,602 | 27,64,603 | 2022-08-12 | 6 Months | 3 | 0.01% | - | - | 0% | Shree Sheikh Aftab Ajij
Retro | PMC | Gangapur | Turkabad Kharadi | 61,88,197 | 59,40,399 | 20-02-2023 | 3 Months | 3 | 0.01% | - | - | 0% | Mr Swastik Jagannath Phulare
Retro | PMC | Gangapur | Wadgaon1 | 21,71,173 | 21,15,791 | 24-01-2023 | 6 Months | 3 | 0.01% | - | - | 0% | Vithumauli Construction
Retro | PMC | Gangapur | Agarwardgaon | 26,84,068 | 26,54,251 | 19-10-2022 | 3 Months | 3 | 0.01% | - | - | 0% | Sheikh Aftab Ajij
Retro | PMC | Gangapur | Daigaon | 22,30,793 | 21,48,246 | 2022-10-11 | 3 Months | 3 | 0.01% | - | - | 0% | Shree Nilesh Uttamrao Rathod
Retro | PMC | Gangapur | Galnimb | 15,91,682 | 15,75,717 | 16-01-2023 | 3 Months | 3 | 0.01% | - | - | 0% | Shree Sheikh Aftab Ajij
Retro | PMC | Gangapur | Shendurwada | 22,24,284 | 21,99,740 | 29-12-2022 | 3 Months | 3 | 0.01% | - | - | 0% | Shree Shrikesh Prabhakar Sonwane
Retro | PMC | Gangapur | Takli | 19,46,555 | 18,49,227 | 30-01-2023 | 3 Months | 3 | 0.01% | - | - | 0% | M/S Sparsh Infra
Retro | PMC | Gangapur | Wazar | 25,49,233 | 24,21,762 | 2022-11-01 | 3 Months | 3 | 0.01% | - | - | 0% | Mr Sparsh Infra
Retro | PMC | Gangapur | Dhamori Bk | 14,28,255 | 13,56,809 | 23-01-2023 | 3 Months | 3 | 0.01% | - | - | 0% | M/S Ashwamedh Supplyers And Construction
Retro | PMC | Gangapur | Naigaon | 37,78,676 | 35,28,284 | 2022-09-12 | 3 Months | 3 | 0.01% | - | - | 0% | M/S Noor Construction
Retro | PMC | Gangapur | Raipur | 15,23,225 | 14,60,989 | 2023-01-30 | 3 Months | 3 | 0.01% | - | - | 0% | Mr Mayur Balasaheb Kundle
Retro | PMC | Gangapur | Amalner | 16,68,799 | 15,57,041 | 2023-01-23 | 3 Months | 3 | 0.01% | - | - | 0% | M/S Ashwamedh Suppliers And Construction
Retro | PMC | Gangapur | Babhulgaon | 15,40,560 | 14,62,882 | 28-12-2022 | 3 Months | 3 | 0.01% | - | - | 0% | Shree Parwej Bhikan Patel
Retro | PMC | Gangapur | Gavli Dhanora | 19,50,971 | 18,51,251 | 28-12-2022 | 3 Months | 3 | 0.01% | - | - | 0% | Shree Mayur Balasaheb Kudale
Retro | PMC | Gangapur | Ghanegaon | 34,67,589 | 33,24,993 | 31-01-2023 | 3 Months | 3 | 0.01% | - | - | 0% | M/S Noor Construction
Retro | PMC | Gangapur | Mangegaon | 23,71,249 | 22,46,731 | 31-01-2023 | 3 Months | 3 | 0.01% | - | - | 0% | Mr Mangal Singhramesh Chavan
Retro | PMC | Gangapur | Manjari | 38,98,124 | 37,46,148 | 31-01-2023 | 3 Months | 3 | 0.01% | - | - | 0% | Noor Construction
Retro | PMC | Gangapur | Narayanpur Bk | 17,85,597 | 16,94,332 | 16-01-2023 | 3 Months | 3 | 0.01% | - | - | 0% | Shree Sheikh Aaftab Ajij
Retro | PMC | Gangapur | Ranjangaon Narhari | 15,53,177 | 15,30,180 | 23-01-2023 | 3 Months | 3 | 0.01% | - | - | 0% | Shree Shyamsingh Suresh Shihire
Retro | PMC | Gangapur | Shivrai | 22,21,840 | 21,16,159 | 16-01-2023 | 3 Months | 3 | 0.01% | - | - | 0% | Shree Shrikesh Sonawane
Retro | PMC | Gangapur | Siregaon | 39,57,111 | 36,94,473 | 24-02-2023 | 3 Months | 3 | 0.01% | - | - | 0% | M/S Shivana Construction
Retro | PMC | Gangapur | Waluj Bk & Kh. | 1,75,63,310 | 1,66,35,827 | 22-12-2022 | 12 Months | 3 | 0.01% | - | - | 0% | M/S S P Construction
Retro | PMC | Gangapur | Khojewadi | 10,33,251 | 10,33,251 | 2022-03-31 | 3 Months | 3 | 0.01% | - | - | 0% | Sarpanch Grampanchayat- Khojewadi (Ambegaon)
Retro | PMC | Gangapur | Tandulwadi(Mandwa) | 13,29,546 | 13,29,546 | 28-07-2022 | 3 Months | 3 | 0.01% | - | - | 0% | Sarpanch Grampanchayat - Tandulwadi(Mandwa)
Retro | PMC | Gangapur | Chinchkheda | 21,95,527 | 21,68,018 | 31-01-2023 | 3 Months | 3 | 0.01% | - | - | 0% | Aditya Umesh Nlimbhare
Retro | PMC | Gangapur | Eklahera-Ganagapur | 10,43,862 | 10,43,862 | 2022-03-31 | 3 Months | 3 | 0.01% | - | - | 0% | Sarpanch Grampanchayat- Eklahera
Retro | PMC | Gangapur | Ganeshwadi | 11,29,957 | 11,29,921 | 2022-09-07 | 3 Months | 3 | 0.01% | - | - | 0% | Gram Panchayat
Retro | PMC | Gangapur | Kalegaon & Dighi | 11,09,919 | 11,09,920 | 31-03-2022 | 3 Months | 3 | 0.01% | - | - | 0% | Gram Panchayat
Retro | PMC | Gangapur | Kobapur | 12,50,388 | 12,50,389 | 2022-07-28 | 3 Months | 3 | 0.01% | - | - | 0% | Gram Panchayat
Retro | PMC | Gangapur | Maholi | 11,65,520 | 11,64,795 | 28-07-2022 | 3 Months | 3 | 0.01% | - | - | 0% | Gram Panchayat
Retro | PMC | Gangapur | Pimpalgaon | 13,05,411 | 13,05,409 | 2022-03-31 | 3 Months | 3 | 0.01% | - | - | 0% | Gram Panchayat
Retro | PMC | Gangapur | Itava | 13,08,081 | 1,30,883 | 2022-07-09 | 3 Months | 3 | 0.01% | - | - | 0% | Gram Panchayat
Retro | PMC | Gangapur | Lakhmapur | 10,57,820 | 10,57,820 | 2022-10-10 | 3 Months | 3 | 0.01% | - | - | 0% | Gram Panchayat
Retro | PMC | Gangapur | Mamdapur | 11,53,680 | 11,53,681 | 2022-07-09 | 3 Months | 3 | 0.01% | - | - | 0% | Gram Panchayat
Retro | PMC | Gangapur | Pimpri | 13,22,598 | 13,22,597 | 2022-07-09 | 3 Months | 3 | 0.01% | - | - | 0% | Gram Panchayat
Retro | PMC | Gangapur | Rajura | 11,48,168 | 11,48,150 | 31-03-2022 | 3 Months | 3 | 0.01% | - | - | 0% | Gram Panchayat
Retro | PMC | Gangapur | Ranjangaon | 1,78,24,384 | 1,78,24,432 | 2023-01-03 | 3 Months | 3 | 0.01% | - | - | 0% | Noor Construction
Retro | PMC | Gangapur | Sanjarpur | 13,15,453 | 13,15,426 | 23-06-2022 | 3 Months | 3 | 0.01% | - | - | 0% | Gram Panchayat
Retro | PMC | Gangapur | Wajnapur | 11,11,608 | 11,11,609 | 31-03-2022 | 3 Months | 3 | 0.01% | - | - | 0% | Gram Panchayat
Retro | PMC | Kannad | Gaur Pimpri - Kannad | 13,10,021 | 13,10,021 | 31-03-2022 | 3 Months | 3 | 77% | - | - | 0% | Sarpanch Grampanchayat - Gaurpimpri
Retro | PMC | Kannad | Wadali | 25,09,128 | 24,07,785 | 14-11-2022 | 4 Months | 3 | 67.67% | 64.77% | 15.6 | 0% | Shree Pramod Kawade
Retro | PMC | Kannad | Bharmba Tanda | 5,69,721 | 5,69,721 | 23-06-2022 | 3 Months | 3 | 51.27% | - | - | 0% | Sarpanch Grampanchayat - Bharmba Tanda
Retro | PMC | Kannad | Hasanabad | 12,47,941 | 12,47,941 | 2022-09-07 | 3 Months | 3 | 49.76% | - | - | 0% | Sarpanch - Gram Panchayat Saigavhan
Retro | PMC | Kannad | Rithi | 61,85,125 | 59,42,129 | 27-09-2022 | 3 Months | 3 | 49.75% | 48.88% | 29.05 | 0% | Shree Ankush Subhash Bawiskar
Retro | PMC | Kannad | Dhangarwadi | 3,66,196 | 4,24,800 | 23-02-2022 | 3 Months | 3 | 49.54% | 31.53% | 1.34 |  | Sarpanch,Gram Panchayat- Dhangarwadi
Retro | PMC | Kannad | Padakwadi | 10,09,411 | 10,09,411 | 31-03-2022 | 3 Months | 3 | 49.54% | 39.68% | 4.01 |  | Sarpanch,Graam Panchayat,Padakwadi
Retro | PMC | Kannad | Sasegaon | 20,29,117 | 21,94,215 | 18-12-2022 | 9 Months | 3 | 22.31% | - | - | 0% | Shree Akshay Ghuge
Retro | PMC | Kannad | Haraswadi | 6,97,143 | 6,97,143 | 31-03-2022 | 3 Months | 3 | 16.65% | - | - |  | Sarpanch,Graam Panchayat, Haraswadi
Retro | PMC | Kannad | Umberkheda Tanda | 9,28,856 | 9,28,856 | 28-07-2022 | 3 Months | 3 | 9.52% | - | - | 0% | Sarpanch , Grampanchayat - Umarkheda Tanda
Retro | PMC | Kannad | Athegaon | 11,35,315 | 11,35,315 | 31-03-2022 | 3 Months | 3 | 9.49% | - | - | 0% | Sarpanch, Grampanchayat - Athegaon
Retro | PMC | Kannad | Umbarkheda | 1,00,73,739 | 97,65,462 | 30-01-2023 | 18 Months | 3 | 3.61% | 2.9% | 2.83 | 0% | Shree Chandrakant Vishnu Manakape
Retro | PMC | Kannad | Khamgaon | 9,09,341 | 9,09,341 | 2022-03-04 | 3 Months | 3 | 0.91% | - | - |  | Sarpanch,Graam Panchayat,Khamgaon
Retro | PMC | Kannad | Alapur | 10,60,672 | 10,60,672 | 31-03-2022 | 3 Months | 3 | 0.88% | - | - |  | Sarpanch, Graam Panchayat, Alapur
Retro | PMC | Kannad | Raigaon | 5,89,751 | 5,89,751 | 23-06-2022 | 3 Months | 3 | 0.84% | - | - | 0% | Sarpanch, Grampanchayat - Barkatpur
Retro | PMC | Kannad | Sahangaon | 14,94,893 | 14,79,995 | 2022-12-09 | 3 Months | 3 | 0.75% | - | - | 0% | Shree Asaram Govindarao Pawar
Retro | PMC | Kannad | Chimnapur | 11,34,639 | 4,54,626 | 2022-04-03 | 3 Months | 3 | 0.66% | - | - |  | Sarpanch, Graam Panchayat, Chimnapur
Retro | PMC | Kannad | Jamdi(Ghat) | 6,92,098 | 6,92,099 | 2022-07-09 | 3 Months | 3 | 0.66% | - | - | 0% | Sarpanch, Grampanchayat - Jamdi ( Ghat )
Retro | PMC | Kannad | Hasankheda | 16,09,214 | 15,57,738 | 23-01-2023 | 6 Months | 3 | 0.65% | - | - | 0% | Shree V G Fulare
Retro | PMC | Kannad | Dongargaon | 12,27,803 | 11,80,000 | 31-03-2022 | 3 Months | 3 | 0.61% | - | - |  | Sarpanch, Graam Panchayat, Dongargaon
Retro | PMC | Kannad | Adgaon(Pishor) | 17,20,180 | 17,20,150 | 23-01-2023 | 3 Months | 3 | 0.57% | - | - | 0% | Shree Vishal Ramadas Nikam
Retro | PMC | Kannad | Vaispur | 4,79,649 | 4,79,649 | 28-07-2022 | 3 Months | 3 | 0.55% | - | - | 0% | Sarpanch , Grampanchayat - Takli ( Lavali)
Retro | PMC | Kannad | Wadgaon | 16,32,827 | 15,50,284 | 17-11-2022 | 3 Months | 3 | 0.54% | - | - | 0% | Shree Aasaram Govindrao Pawar
Retro | PMC | Kannad | Sakharwel | 8,21,824 | 8,21,824 | 28-07-2022 | 3 Months | 3 | 0.51% | - | - | 0% | Sarpanch , Grampanchayat - Katkheda
Retro | PMC | Kannad | Bormali Tanda | 16,12,079 | 15,45,171 | 31-01-2023 | 6 Months | 3 | 0.49% | - | - | 0% | Shree Ankush Bawiskar
Retro | PMC | Kannad | Tapowan | 59,48,326 | 57,49,038 | 20-02-2023 | 9 Months | 3 | 0.46% | - | - | 0% | Shrimati Priyanka Rohit Nawandar
Retro | PMC | Kannad | Borsar Kh | 11,11,570 | 11,11,570 | 31-03-2022 | 3 Months | 3 | 0.43% | - | - | 0% | Sarpanch, Grampanchayat - Borsar Kh
Retro | PMC | Kannad | Palaskheda | 10,53,555 | 10,53,555 | 23-06-2022 | 3 Months | 3 | 0.42% | - | - | 0% | Sarpanch, Grampanchayat - Palaskheda
Retro | PMC | Kannad | Mundwadi Tanda | 30,24,222 | 30,09,144 | 24-11-2022 | 9 Months | 3 | 0.41% | - | - | 0% | Shree Nanasaheb Kacharu Kalange
Retro | PMC | Kannad | Antapur | 16,46,444 | 17,39,006 | 27-09-2022 | 3 Months | 3 | 0.4% | - | - | 0% | Shree Sangharsh Raveev Boldhane
Retro | PMC | Kannad | Nagad | 59,98,762 | 57,39,278 | 31-01-2023 | 6 Months | 3 | 0.37% | - | - | 0% | M/S Saibhumi Construction
Retro | PMC | Kannad | Hiwarkheda | 42,44,002 | 40,62,023 | 31-01-2023 | 6 Months | 3 | 0.37% | - | - | 0% | M/S Saibhumi Construction
Retro | PMC | Kannad | Sonwadi | 7,15,861 | 7,15,861 | 31-03-2022 | 3 Months | 3 | 0.36% | - | - |  | Sarpanch,Gram Panchayat, Sonwadi
Retro | PMC | Kannad | Makrunpur | 24,30,648 | 23,05,663 | 14-12-2022 | 3 Months | 3 | 0.34% | - | - | 0% | Shree Pramod Kawade
Retro | PMC | Kannad | Shirodi | 59,20,892 | 56,81,027 | 2022-12-09 | 9 Months | 3 | 0.33% | - | - | 0% | Shree Sangharsh Rajeev Boladhane
Retro | PMC | Kannad | Dabhadi | 40,25,795 | 38,74,103 | 23-01-2023 | 6 Months | 3 | 0.33% | - | - | 0% | Shree Shyamsingh Shihire
Retro | PMC | Kannad | Ganeshpur | 51,22,128 | 48,65,536 | 14-11-2022 | 9 Months | 3 | 0.3% | - | - | 0% | Shreemati Punam Tushar Ghodake
Retro | PMC | Kannad | Bhopewadi | 27,89,800 | 27,55,208 | 23-01-2023 | 6 Months | 3 | 0.27% | - | - | 0% | Shree Asaram Govindrao Pawar
Retro | PMC | Kannad | Borsar Bk 1 | 31,14,015 | 31,05,360 | 31-01-2023 | 9 Months | 3 | 0.26% | - | - | 0% | Shree Sangharsh Rajeev Boladhane
Retro | PMC | Kannad | Jawali Kh | 19,54,441 | 19,54,413 | 2022-09-12 | 6 Months | 3 | 0.24% | - | - | 0% | Shree Sangharsh Rajeev Boladhane
Retro | PMC | Kannad | Moharda | 33,65,240 | 30,40,827 | 22-11-2022 | 9 Months | 3 | 0.2% | - | - | 0% | Shree Aasaram Govindrao Pawar
Retro | PMC | Kannad | Navadi | 77,45,303 | 72,48,977 | 2023-02-08 | 18 Months | 3 | 0.19% | - | - | 0% | Shree Sangharsh Rajeev Boladhane
Retro | PMC | Kannad | Chincholi Limbachi | 71,58,924 | 65,23,799 | 23-01-2023 | 6 Months | 3 | 0.18% | - | - | 0% | Anjali Construction
Retro | PMC | Kannad | Malegaon(Lokhandi) | 62,88,785 | 61,17,113 | 31-01-2023 | 9 Months | 3 | 0.18% | - | - | 0% | Shree Akshay Ghuge
Retro | PMC | Kannad | Shivrai | 1,65,57,393 | 1,52,82,492 | 2023-08-02 | 18 Months | 3 | 0.17% | - | - | 0% | S P Construction
Retro | PMC | Kannad | Nachanwel | 1,08,57,306 | 1,07,02,599 | 18-11-2022 | 12 Months | 3 | 0.16% | - | - | 0% | Shree Nilesh Uttamrao Rathod
Retro | PMC | Kannad | Sarola | 29,31,475 | 28,68,813 | 30-01-2023 | 4 Months | 3 | 0.13% | - | - | 0% | Real Constro Project Pvt Ltd
Retro | PMC | Kannad | Chambharwadi | 92,37,279 | 88,67,198 | 24-01-2023 | 18 Months | 3 | 0.13% | - | - | 0% | Shree Nanasaheb Kacharu Kalange
Retro | PMC | Kannad | Shafiyabad | 21,78,464 | 21,78,487 | 30-01-2023 | 9 Months | 3 | 0.11% | - | - | 0% | Shree Vishal Ramdas Nikam
Retro | PMC | Kannad | Karanjkheda Jahagir | 1,62,67,645 | 1,61,06,386 | 31-01-2023 | 18 Months | 3 | 0.11% | - | - | 0% | Pardesi & Sons
Retro | PMC | Kannad | Khedi | 1,76,90,226 | 1,11,15,816 | 23-01-2023 | 18 Months | 3 | 0.11% | - | - | 0% | Shree Arun Ganpat Edhate
Retro | PMC | Kannad | Nandgirwadi | 92,05,886 | 97,19,972 | 23-01-2023 | 18 Months | 3 | 0.11% | - | - | 0% | Shree Piyush Kantilal Salawe
Retro | PMC | Kannad | Bharamba | 53,70,910 | 51,77,008 | 30-01-2023 | 9 Months | 3 | 0.1% | - | - | 0% | Shree Vishal Ramadas Nikam
Retro | PMC | Kannad | Upla | 42,99,607 | 41,70,630 | 31-01-2023 | 6 Months | 3 | 0.1% | - | - | 0% | Shree Ankush Subhash Bawiskar
Retro | PMC | Kannad | Kheda | 15,49,409 | 14,20,807 | 24-01-2023 | 6 Months | 3 | 0.1% | - | - | 0% | Shree Ankush Bawiskar
Retro | PMC | Kannad | Garada | 67,73,096 | 66,08,039 | 20-02-2023 | 9 Months | 3 | 0.09% | - | - | 0% | Shree Ankush Bawiskar
Retro | PMC | Kannad | Khaparkheda | 81,80,938 | 81,14,074 | 31-01-2023 | 18 Months | 3 | 0.09% | - | - | 0% | Shree Pramod Kakasaheb Kawade
Retro | PMC | Kannad | Mehun Purnawadi | 77,39,380 | 75,99,979 | 24-01-2023 | 18 Months | 3 | 0.09% | - | - | 0% | Shree Arun Ganapat Edhate
Retro | PMC | Kannad | Newpur(Khalsa Jahngir) | 1,00,29,086 | 99,29,797 | 23-01-2023 | 18 Months | 3 | 0.09% | - | - | 0% | Shree Anil Kandalkar
Retro | PMC | Kannad | Karanjkheda Khalsa | 1,64,20,451 | 1,62,57,796 | 2023-08-02 | 18 Months | 3 | 0.08% | - | - | 0% | Pardesi & Sons
Retro | PMC | Kannad | Satkund | 66,35,517 | 64,39,180 | 20-02-2023 | 9 Months | 3 | 0.07% | - | - | #DIV/0! | Shree Shashikant Khade
Retro | PMC | Kannad | Hasta | 85,67,303 | 83,43,699 | 30-01-2023 | 9 Months | 3 | 0.06% | - | - | 0% | Shree Vishal Ramdas Nikam
Retro | PMC | Kannad | Boltek | 88,43,904 | 80,92,679 | 2023-02-09 | 9 Months | 3 | 0.06% | - | - | 0% | Shree Sangharsh Rajeev Boladhane
Retro | PMC | Kannad | Tandulwadi | 37,07,570 | 36,70,354 | 20-02-2023 | 9 Months | 3 | 0.05% | - | - | 0% | M/S Rockline Construction
Retro | PMC | Kannad | Hiwarkhed& Gautala | 87,14,655 | 86,27,530 | 20-02-2023 | 9 Months | 3 | 0.05% | - | - | 0% | M/S Rockline Construction
Retro | PMC | Kannad | Koparwel | 34,10,331 | 35,80,850 | 20-02-2023 | 6 Months | 3 | 0.05% | - | - | 0% | Shree Vishal Ramadas Nikam
Retro | PMC | Kannad | Rewoolgaon | 94,25,346 | 93,31,107 | 20-02-2023 | 18 Months | 3 | 0.05% | - | - | 0% | Rockline Construction
Retro | PMC | Kannad | Khedi - Kannad | 1,12,41,494 | 1,11,15,816 | 23-01-2023 | 18 Months | 3 | 0.05% | - | - | 0% | Shree Arun Ganpat Edhate
Retro | PMC | Kannad | Digaon 1 | 1,30,12,835 | 1,26,79,177 | 30-01-2023 | 18 Months | 3 | 0.04% | - | - | 0% | Shree Arun Edhate
Retro | PMC | Kannad | Deolana | 1,54,42,446 | 1,51,32,196 | 31-01-2023 | 18 Months | 3 | 0.03% | - | - | 0% | Mayur Construction
Retro | PMC | Kannad | Jalgaon Ghat & Palasgaon | 1,13,67,333 | 1,05,36,856 | 20-02-2023 | 18 Months | 3 | 0.03% | - | - | 0% | Shree Sangharsh Rajeev Boladhane
Retro | PMC | Kannad | Mohara Makta | 1,01,14,938 | 99,12,577 | 2023-09-02 | 18 Months | 3 | 0.03% | - | - | 0% | Shree Nanasaheb Kalange
Retro | PMC | Kannad | Takli(Lavali) | 55,98,600 | 52,39,663 | 31-01-2023 | 6 Months | 3 | 0.03% | - | - | 0% | Nills Construction
Retro | PMC | Kannad | Bramhani | 81,85,892 | 77,71,503 | 30-01-2023 | 9 Months | 3 | 0.02% | - | - | 0% | Shree Piyush Kantilal Salawe
Retro | PMC | Kannad | Ghat Shendra | 2,17,35,474 | 1,63,21,376 | 20-02-2023 | 18 Months | 3 | 0.02% | - | - | 0% | M/S Rockline Construction
Retro | PMC | Kannad | Barkatpur 1 | 1,57,06,184 | 1,57,21,313 | 30-01-2023 | 18 Months | 3 | 0.02% | - | - | 0% | Shri Atul Sambhaji Nikam
Retro | PMC | Kannad | Jaitkheda& Jaitkheda Tanda | 1,25,98,234 | 1,21,32,128 | 2023-09-02 | 6 Months | 3 | 0.01% | - | - | 0% | Shree Sangharsh Rajeev Boladhane
Retro | PMC | Khulatabad | Nandrabad | 16,11,102 | 15,16,532 | 30-01-2023 | 6 Months | 3 | 0.43% | - | - | 0% | Shree Sheikh Wasim Sharikh
Retro | PMC | Khulatabad | Sobalgaon | 20,15,315 | 20,13,199 | 22-12-2022 | 4 Months | 3 | 0.35% | - | - | 0% | Shree Saurabh Machhindra Kurhade
Retro | PMC | Khulatabad | Kagjipura | 32,12,809 | 31,52,328 | 2022-09-12 | 3 Months | 3 | 0.31% | - | - | 0% | Shree Amey Arun Pawar
Retro | PMC | Khulatabad | Khirdi | 40,33,760 | 38,61,559 | 23-01-2023 | 5 Months | 3 | 0.24% | - | - | 0% | Shree Omkar Bhausaheb Tandale
Retro | PMC | Khulatabad | Tisgaon Tanda | 49,65,019 | 47,23,848 | 14-12-2023 | 6 Months | 3 | 0.2% | - | - | 0% | Shree Sanjay Raghunath Bhandare
Retro | PMC | Khulatabad | Jafarwadi | 30,64,580 | 29,04,246 | 16-01-2023 | 6 Months | 3 | 0.2% | - | - | 0% | Noor Construction
Retro | PMC | Khulatabad | Bhndegaon | 25,04,990 | 23,49,211 | 18-11-2022 | 3 Months | 3 | 0.18% | - | - | 0% | Shree Alim Gafur Sheikh
Retro | PMC | Khulatabad | Gadana | 1,09,85,508 | 1,05,78,461 | 23-01-2023 | 6 Months | 3 | 0.15% | - | - | 0% | Shree Piyush Kantilal Salwe
Retro | PMC | Khulatabad | Takli Rr | 1,11,92,721 | 1,03,57,221 | 22-12-2022 | 6 Months | 3 | 0.13% | - | - | 0% | S P Construction
Retro | PMC | Khulatabad | Kasabkheda | 53,97,876 | 53,39,722 | 31-01-2023 | 6 Months | 3 | 0.13% | - | - | 0% | Shree Sheikh Salim Gulamoedidan
Retro | PMC | Khulatabad | Sultanpur | 1,23,55,295 | 1,16,10,322 | 31-01-2023 | 9 Months | 3 | 0.13% | - | - | 0% | Shree Saurabh Machhindra Kurhade
Retro | PMC | Khulatabad | Verul | 98,84,543 | 1,02,79,926 | 24-01-2023 | 9 Months | 3 | 0.12% | - | - | 0% | Shubhangi Construction
Retro | PMC | Khulatabad | Khandi Pimapalgaon | 1,13,86,259 | 1,09,64,833 | 30-01-2023 | 18 Months | 3 | 0.11% | - | - | 0% | Shree Viraj Awotade
Retro | PMC | Khulatabad | Dhamangaon | 79,95,325 | 79,45,351 | 23-01-2023 | 6 Months | 3 | 0.09% | - | - | 0% | M/S Rockline Construction
Retro | PMC | Khulatabad | Nirgudi Kh | 26,31,241 | 26,31,211 | 20-02-2023 | 6 Months | 3 | 0.07% | - | - | 0% | M/S Jadhao Construction
Retro | PMC | Khulatabad | Sulibhanhajan | 93,75,033 | 92,72,225 | 20-02-2023 | 6 Months | 3 | 0.06% | - | - | 0% | Noor Construction
Retro | PMC | Paithan | Talewadi | 39,39,340 | 38,39,645 | 27-12-2022 | 3 Months | 3 | 85.87% | 82.-9% | - | 0% | Khushi Construction
Retro | TSP | Paithan | Krishnapur | 17,15,335 | 15,43,973 | 2022-08-03 | 3 Months | 3 | 84.02% | 83.13% | 12.84 |  | M/S Hari Om Construction
Retro | PMC | Paithan | Solnapur | 14,48,047 | 14,33,566 | 25-08-2022 | 3 Months | 3 | 81.76% | 8-.74% | - |  | Shree Rishikesh Kale
Retro | TSP | Paithan | Agarnandar | 43,85,840 | 41,34,531 | 14-09-2022 | 3 Months | 3 | 75.73% | 72.51% | 29.98 |  | Shree Nilesh Utamraw Rathod
Retro | PMC | Paithan | Pachalgaon | 11,47,547 | 11,47,547 | 2022-09-03 | 1 Months | 3 | 71.45% | 62.36% | 7.16 |  | Sarpanch, Gram Panchayat Panchalgaon
Retro | PMC | Paithan | Murma | 16,07,476 | 15,99,987 | 2022-05-09 | 3 Months | 3 | 65.75% | 65.64% | 10.5 | 0% | Shree Anna Bhagwan Mote
Retro | PMC | Paithan | Parundi Tanda | 19,16,033 | 18,48,779 | 25-08-2022 | 3 Months | 3 | 65.72% | 62.4% | 11.54 |  | Mr. Nilesh Uttam Rao Rathod
Retro | PMC | Paithan | Parundi | 35,35,748 | 34,11,606 | 27-09-2022 | 3 Months | 3 | 59.08% | - | - | 0% | Shree Nilesh Uttamrao Rathod
Retro | PMC | Paithan | Harshi Bk | 19,93,224 | 18,22,625 | 29-07-2022 | 3 Months | 3 | 56.25% | 44.-1% | - | 0% | Shree Ajinkya Ramrao Rathod
Retro | PMC | Paithan | Farola | 5,33,635 | 5,33,635 | 2022-07-28 | 3 Months | 3 | 55.18% | - | - | 0% | Sarpanch , Grampanchayat - Farola
Retro | PMC | Paithan | Katpur | 28,77,240 | 30,95,321 | 23-09-2022 | 3 Months | 3 | 54.78% | - | - | 0% | M/S Rockline Construction, Town Center A'Bad
Retro | TSP | Paithan | Adgaon | 9,66,060 | 9,66,060 | 23-02-2022 | 3 Months | 3 | 53.55% | 52% | 5.02 |  | Sarpanch ,Gram Panchayat Adgaon Jawale
Retro | PMC | Paithan | Limbgaon | 21,16,241 | 20,98,237 | 16-09-2022 | 3 Months | 3 | 53.19% | - | - | 0% | Shree Anna Bhagwan Mote
Retro | PMC | Paithan | Dongaon | 23,07,295 | 21,84,954 | 22-08-2022 | 3 Months | 3 | 51.74% | - | - | 0% | Shree Alim Gafur Sheikh
Retro | PMC | Paithan | Wadgavhan | 10,44,693 | 10,44,693 | 23-02-2022 | 3 Months | 3 | 45.98% | 45.5% | 4.75 | 0% | Sarpanch Grampanchayat - Wadgavhan(Nilajgaon)
Retro | PMC | Paithan | Gharegaon | 9,39,806 | 9,39,806 | 23-06-2022 | 3 Months | 3 | 44.72% | 39.-1% | - |  | Sarpanch, Gram Panchayat, Gharegaon
Retro | PMC | Paithan | Padli & Gazipur | 31,57,217 | 31,57,225 | 24-11-2022 | 3 Months | 3 | 41.08% | - | - | 0% | Shree Ameya Arun Pawar
Retro | PMC | Paithan | Shekta | 18,81,630 | 18,07,733 | 23-12-2022 | 3 Months | 3 | 40.17% | - | - | 0% | Shree Mangalsingh Ramesh Chavhan
Retro | PMC | Paithan | Jainpur | 10,15,383 | 10,15,383 | 2022-07-28 | 3 Months | 3 | 36.44% | - | - | 0% | Sarpanch, Grampanchayat - Dhupkheda
Retro | PMC | Paithan | Harshi | 15,61,332 | 14,27,682 | 2022-08-03 | 3 Months | 3 | 34.81% | 34.58% | 4.94 |  | Shree Ajinkya Ramraw Rathod
Retro | PMC | Paithan | Mahmadpur | 9,70,197 | 9,70,197 | 2022-11-01 | 3 Months | 3 | 31.34% | 3-.62% | - | 0% | Sarpanch Grampanchayat - Mahmadpur(Changatpuri)
Retro | TSP | Paithan | Pachod | 18,64,326 | 16,96,723 | 2022-03-27 | 3 Months | 3 | 31.01% | - | - |  | Shree B.B. Lahamge
Retro | PMC | Paithan | Hingani | 14,92,237 | 14,92,237 | 2022-06-17 | 3 Months | 3 | 30% | - | - |  | Shree Omkar Bhausaheb Tandale
Retro | PMC | Paithan | Mudhalwadi | 77,27,544 | 72,82,354 | 2022-12-21 | 3 Months | 3 | 29.52% | - | - | 0% | Khushi Construction
Retro | PMC | Paithan | Akhatwada | 21,14,171 | 19,51,379 | 2022-08-12 | 3 Months | 3 | 28.35% | - | - |  | Shree Ajinke Ramraw Rathor
Retro | PMC | Paithan | Pusegaon | 10,46,977 | 10,51,800 | 2022-10-01 | 3 Months | 3 | 28.34% | 27.6% | 2.9 |  | Sarpanch, Gram Panchayat Pusegaon
Retro | PMC | Paithan | Khandala | 9,89,588 | 9,89,588 | 2023-01-16 | 3 Months | 3 | 28.19% | - | - | 0% | Sarpanch , Grampanchayat - Salwadgaon
Retro | PMC | Paithan | Pimpalwadi | 54,49,751 | 53,63,749 | 13-10-2022 | 3 Months | 3 | 27.84% | - | - | 0% | S P Construction
Retro | PMC | Paithan | Dhupkheda | 16,17,010 | 15,40,880 | 21-12-2022 | 3 Months | 3 | 26.61% | - | - | 0% | Shree Bhushan Tambe
Retro | PMC | Paithan | Chincholi | 8,43,657 | 8,43,657 | 31-03-2022 | 3 Months | 3 | 25.59% | 22.24% | 1.88 |  | Sarpanch, Gram Panchayat - Chincholi
Retro | PMC | Paithan | Mharola | 5,36,373 | 5,36,372 | 2022-04-03 | 3 Months | 3 | 25.31% | - | - | 0% | Sarpanch, Grampanchayat - Mharola
Retro | PMC | Paithan | Karkin | 39,54,508 | 37,64,895 | 23-01-2023 | 3 Months | 3 | 25.23% | - | - | 0% | Khushi Construction
Retro | PMC | Paithan | Ranjangaon Khuri | 35,42,299 | 33,73,338 | 23-12-2022 | 3 Months | 3 | 25.13% | - | - | 0% | Khushi Construction
Retro | PMC | Paithan | Ektuni | 27,18,403 | 26,62,075 | 2022-07-11 | 3 Months | 3 | 24.89% | - | - | 0% | Nandini Construction
Retro | PMC | Paithan | Kherda | 13,08,347 | 13,08,347 | 23-06-2022 | 3 Months | 3 | 24.31% | - | - | 0% | Sarpanch , Grampanchayat - Kherda
Retro | PMC | Paithan | Kaundar | 12,03,643 | 12,03,643 | 2022-10-01 | 3 Months | 3 | 23.37% | 23.34% | 2.81 |  | Sarpanch, Gram Panchayat Kaundar
Retro | PMC | Paithan | Kekat Jalgaon | 21,21,972 | 20,49,702 | 2022-12-23 | 3 Months | 3 | 23.32% | - | - | 0% | Shree Alok Gorade
Retro | PMC | Paithan | Kapuswadi | 16,66,603 | 16,33,768 | 2022-12-09 | 3 Months | 3 | 21.25% | - | - | 0% | Shree Amol Anna Bhopale
Retro | TSP | Paithan | Mavasgavhan | 12,75,302 | 12,75,302 | 23-02-2022 | 3 Months | 3 | 20.01% | - | - |  | Sarpanch, Gram Panchayat, Mavasgavhan
Retro | PMC | Paithan | Bramhagaon | 4,72,664 | 4,72,664 | 2022-04-03 | 3 Months | 3 | 19.96% | - | - | 0% | Sarpanch, Grampanchayat - Bramhagaon
Retro | PMC | Paithan | Sonwadi | 21,67,412 | 20,92,847 | 23-12-2022 | 3 Months | 3 | 19.1% | - | - | 0% | Khushi Construction
Retro | PMC | Paithan | Bramhangaon | 10,91,501 | 10,91,501 | 28-07-2022 | 3 Months | 3 | 18.59% | - | - | 0% | Sarpanch, Grampanchayat - Bramhangaon
Retro | PMC | Paithan | Sonwadi Bk & Kh | 12,25,675 | 12,25,675 | 31-03-2022 | 3 Months | 3 | 18.37% | - | - | 0% | Sarpanch , Grampanchayat - Sonwadi (Bk)
Retro | PMC | Paithan | Saigaon | 12,24,145 | 12,24,145 | 31-03-2022 | 3 Months | 3 | 16.88% | - | - | 0% | Sarpanch , Grampanchayat - Dadegaon Jahagir
Retro | PMC | Paithan | Honobachiwadi | 11,96,010 | 11,96,010 | 31-03-2022 | 3 Months | 3 | 15.91% | - | - |  | Sarpanch, Gram Panchayat, Georai Bk
Retro | PMC | Paithan | Babulgaon | 28,82,146 | 28,80,661 | 2022-09-12 | 3 Months | 3 | 15.83% | - | - | 0% | Shree Amol Anna Bhopale
Retro | PMC | Paithan | Indegaon | 11,83,299 | 11,83,299 | 2022-04-03 | 3 Months | 3 | 15.65% | - | - | 0% | Sarpanch , Grampanchayat - Indegaon
Retro | PMC | Paithan | Wadji | 22,95,953 | 22,73,330 | 24-11-2022 | 3 Months | 3 | 15.45% | - | - | 0% | Shree Sachin Dhondoba Bansod
Retro | PMC | Paithan | Tekdi Tanda | 15,99,161 | 15,83,025 | 2022-02-09 | 3 Months | 3 | 15.27% | - | - | 0% | Shree Annabhagwan Mote
Retro | TSP | Paithan | Takli Paithan | 4,27,590 | 4,27,590 | 23-02-2022 | 3 Months | 3 | 14.66% | - | - |  | Sarpanch, Gram Panchayat, Takli Paithan
Retro | PMC | Paithan | Tanda | 27,09,280 | 24,65,174 | 15-11-2022 | 3 Months | 3 | 14.4% | - | - | 0% | Shree Asaram Govindarao Pawar
Retro | PMC | Paithan | Pangra | 9,44,110 | 9,44,110 | 28-07-2022 | 3 Months | 3 | 14.39% | - | - | 0% | Sarpanch , Grampanchayat - Pangra
Retro | TSP | Paithan | Anandpur | 7,69,320 | 7,69,320 | 23-02-2022 | 3 Months | 3 | 14.08% | - | - |  | Sarpanch, Gram Panchayat, Anandpur
Retro | PMC | Paithan | Tupewadi | 11,14,203 | 11,14,203 | 2022-04-03 | 3 Months | 3 | 12.03% | - | - | 0% | Sarpanch , Grampanchayat - Daregaon
Retro | PMC | Paithan | Hingni | 15,84,486 | 14,92,237 | 17-06-2022 | 3 Months | 3 | 11.69% | - | - | 0% | Shree Omkar Bhausaheb Tandale
Retro | PMC | Paithan | Daregaon | 32,67,639 | 31,52,924 | 2022-09-12 | 3 Months | 3 | 11.47% | - | - | 0% | Shree Trushikesh Kale
Retro | PMC | Paithan | Narayangaon | 19,38,528 | 18,41,379 | 14-10-2022 | 3 Months | 3 | 10.6% | - | - | 0% | Shree Asaram Govindrao Pawar
Retro | PMC | Paithan | Borgaon | 4,61,599 | 4,61,599 | 2022-07-28 | 3 Months | 3 | 0.16% | - | - | 0% | Sarpanch, Grampanchayat - Isarwadi
Retro | PMC | Paithan | Wahegaon | 23,01,454 | 22,78,683 | 23-01-2023 | 3 Months | 3 | 0.14% | - | - | 0% | Shree Rohit Ramesh Jadhav
Retro | PMC | Paithan | Shivani | 5,47,970 | 5,47,970 | 31-03-2022 | 3 Months | 3 | 0.13% | - | - | 0% | Sarpanch , Grampanchayat - Pangra
Retro | PMC | Paithan | Dadegaon | 5,41,499 | 5,41,499 | 2022-02-23 | 3 Months | 3 | 0.12% | - | - |  | Sarpanch, Gram Panchayat, Dadegaon Jahangir
Retro | PMC | Paithan | Dawarwadi | 40,77,992 | 38,64,301 | 23-01-2023 | 3 Months | 3 | 0.11% | - | - | 0% | Shree Yogesh Rathod
Retro | PMC | Paithan | Abdulapur | 20,20,011 | 18,98,794 | 2023-01-23 | 3 Months | 3 | 0.11% | - | - | 0% | Shrimati Priyanka Rohit Nawandar
Retro | PMC | Paithan | Waghadi | 10,23,517 | 10,23,517 | 2022-03-31 | 3 Months | 3 | 0.11% | - | - | 0% | Sarpanch , Grampanchayat - Waghadi
Retro | PMC | Paithan | Sompuri | 14,07,066 |  |  | Months |  | 0.08% | - | - | 0%
Retro | PMC | Paithan | Nandalgaon | 8,14,667 | 8,14,667 | 2022-03-04 | 3 Months | 3 | 0.06% | - | - |  | Sarpanch, Gram Panchayat, Nandalgaon
Retro | PMC | Paithan | Dinnapur | 7,77,488 | 7,77,488 | 2022-04-03 | 3 Months | 3 | 0.06% | - | - | 0% | Sarpanch, Grampanchayat - Dinnapur
Retro | PMC | Paithan | Gadhegaon | 11,12,924 | 11,12,924 | 2022-07-28 | 3 Months | 3 | 0.06% | - | - | 0% | Sarpanch, Grampanchayat - Gadhegaon Paithan
Retro | PMC | Paithan | Lakhegaon | 4,87,430 | 4,87,430 | 2022-04-03 | 3 Months | 3 | 0.06% | - | - | 0% | Sarpanch, Grampanchayat - Lakhegaon
Retro | PMC | Paithan | Thapti Tanda | 10,64,846 | 10,64,846 | 31-03-2022 | 3 Months | 3 | 0.06% | - | - | 0% | Sarpanch , Grampanchayat - Hirapur
Retro | PMC | Paithan | Apegaon | 18,71,692 | 17,83,694 | 23-12-2022 | 3 Months | 3 | 0.05% | - | - | 0% | Shree Nanasaheb Kacharu Kalange
Retro | PMC | Paithan | Amrapur Waghundi | 10,12,018 | 10,12,018 | 2022-04-03 | 3 Months | 3 | 0.05% | - | - | 0% | Sarpanch, Grampanchayat - Pimpalwadi ( Pirachi )
Retro | PMC | Paithan | Jogeshwari | 9,64,333 | 9,64,333 | 2022-06-23 | 3 Months | 3 | 0.05% | - | - | 0% | Sarpanch, Grampanchayat - Mulani Wadgaon
Retro | PMC | Paithan | Rajapur | 9,00,618 | 9,00,618 | 28-07-2022 | 3 Months | 3 | 0.05% | - | - | 0% | Sarpanch, Grampanchayat - Rajapur
Retro | PMC | Paithan | Maigaon | 17,76,194 | 16,69,596 | 24-01-2023 | 3 Months | 3 | 0.04% | - | - | 0% | Shree Sandip Jadhav
Retro | PMC | Paithan | Dadegaon1 | 14,44,320 | 14,17,111 | 15-12-2022 | 3 Months | 3 | 0.04% | - | - | 0% | Shree Rohit Raju Papal
Retro | PMC | Paithan | Awade Unchegaon | 24,44,570 | 24,14,011 | 23-01-2023 | 3 Months | 3 | 0.04% | - | - | 0% | Shree Ajinkyarao Bhumare
Retro | PMC | Paithan | Shevta | 10,44,867 | 10,44,867 | 23-06-2022 | 3 Months | 3 | 0.04% | - | - | 0% | Sarpanch , Grampanchayat - Shevata
Retro | PMC | Paithan | Lohagaon | 48,89,158 |  |  | Months |  | 0.03% | - | - | 0%
Retro | PMC | Paithan | Kutub Kheda | 21,80,349 | 21,64,653 | 2022-02-09 | 3 Months | 3 | 0.03% | - | - | 0% | Shree Anna Bhagwan Mote
Retro | PMC | Paithan | Chinchala | 14,47,148 | 14,11,581 | 26-12-2022 | 3 Months | 3 | 0.03% | - | - | 0% | Shree Mahesh Gorakhanath Kale
Retro | PMC | Paithan | Pachod Bk | 45,50,122 | 43,86,312 | 16-01-2023 | 3 Months | 3 | 0.03% | - | - | 0% | Shree Alim Gafur Sheikh
Retro | PMC | Paithan | Adool Kh | 10,56,314 | 10,56,314 | 2022-07-09 | 3 Months | 3 | 0.03% | - | - | 0% | Sarpanch , Grampanchayat - Adool (Kh)
Retro | PMC | Paithan | Lamgavhan - Mulaniwadgaon | 34,91,561 | 33,86,791 | 2023-01-23 | 6 Months | 3 | 0.03% | - | - | 0% | Shree Sanjay Raghunath Bhandare
Retro | TSP | Paithan | Georai Kh | 10,11,378 | 10,11,378 | 23-02-2022 | 3 Months | 3 | 0.02% | - | - |  | Sarpanch, Gram Panchayat, Georai Kh
Retro | PMC | Paithan | Antarwadi | 6,65,977 | 6,65,977 | 28-07-2022 | 3 Months | 3 | 0.02% | - | - |  | Sarpanch, Grampanchayat - Antarwadi Khandi
Retro | PMC | Paithan | Hiradpuri | 55,31,729 | 54,70,239 | 16-01-2023 | 3 Months | 3 | 0.02% | - | - | 0% | S P Construction
Retro | PMC | Paithan | Paithan Kheda | 27,49,862 | 27,00,111 | 23-01-2023 | 3 Months | 3 | 0.02% | - | - | 0% | Shree Arun Wasankar
Retro | PMC | Paithan | Balanagar | 39,68,001 | 37,41,807 | 2023-02-20 | 3 Months | 3 | 0.02% | - | - | 0% | Shree Alok Gorde
Retro | PMC | Paithan | Devgaon & Devgaon Tanda | 21,71,374 | 21,11,824 | 24-01-2023 | 6 Months | 3 | 0.02% | - | - | 0% | Shree Yogesh Rathod
Retro | PMC | Paithan | Gidhada | 31,47,916 | 33,14,349 | 2022-03-10 | 3 Months | 3 | 0.01% | - | - | 0% | M/S V R Mahajan
Retro | PMC | Paithan | Changatpuri | 31,02,014 | 31,02,014 | 23-12-2022 | 3 Months |  | 0.01% | - | - | 0% | Shree Santosh Shivaji Batule
Retro | PMC | Paithan | Dongri Naik Tanda | 25,66,531 | 24,38,221 | 2023-01-30 | 6 Months | 3 | 0.01% | - | - | 0% | Shree Sandip Jadhav
Retro | PMC | Phulambari | Wakod | 33,11,152 | 32,24,730 | 25-07-2022 | 3 Months | 3 | 53.32% | 44.27% | 14.28 |  | Shree Sudarshan Dilip Bhatane
Retro | PMC | Phulambari | Ridhora | 43,74,450 | 49,18,641 | 27-06-2022 | 6 Months | 3 | 29.89% | - | - | 0% | M/S. D R More
Retro | TSP | Phulambari | Gevrai Gungi | 95,10,599 | 1,07,04,092 | 18-11-2022 | 6 Months | 3 | 17.68% | 15.26% | 16.33 | 0% | Shree Swaraj Jagadish Darakh
Retro | PMC | Phulambari | Jatwa | 34,62,252 | 34,41,481 | 25-01-2023 | 6 Months | 3 | 9.08% | - | - | 0% | Shree Satyanarayan Sandulal Jajure
Retro | TSP | Phulambari | Takli-Kolte | 33,17,743 | 38,11,329 | 18-11-2022 | 6 Months | 3 | 3.01% | 2.17% | 0.83 | 0% | Shree S. R. Jaiswal
Retro | TSP | Phulambari | Shelgaon | 39,28,757 | 43,65,634 | 23-01-2023 | 6 Months | 3 | 1.23% | - | - | 0% | Shree Manik Infra Projects
Retro | PMC | Phulambari | Bilda | 36,43,463 | 35,25,049 | 2022-07-06 | 3 Months | 3 | 1.12% | - | - |  | Prmod Kamasaheb Kwde
Retro | TSP | Phulambari | Liha | 21,22,926 | 20,95,182 | 28-06-2022 | 3 Months | 3 | 1.09% | - | - |  | M/S Hari Om Construction
Retro | TSP | Phulambari | Shirudi Kh | 5,61,858 | 5,61,858 | 23-02-2022 | 3 Months | 3 | 0.32% | - | - | 0% | Sarpanch, Grampanchayat - Shirodi Kh
Retro | TSP | Phulambari | Dhanora | 40,80,955 | 46,66,190 | 30-01-2023 | 5 Months | 3 | 0.26% | - | - | 0% | Manik Infra Projects
Retro | PMC | Phulambari | Lalwan | 9,12,848 | 9,12,848 | 23-02-2022 | 3 Months | 3 | 0.23% | - | - | 0% | Sarpanch, Grampanchayat - Lalwan
Retro | PMC | Phulambari | Narala | 26,31,216 | 25,62,728 | 2023-01-25 | 6 Months | 3 | 0.21% | - | - | 0% | Shree Sudarshan Dilip Bhatane
Retro | TSP | Phulambari | Ganori | 99,19,090 | 93,44,703 | 23-01-2023 | 18 Months | 3 | 0.16% | - | - | 0% | Shree Omkar Bhaosaheb Tandale
Retro | PMC | Phulambari | Umrawati | 1,06,30,388 | 99,18,158 | 30-01-2023 | 9 Months | 3 | 0.12% | - | - | 0% | M/S D R More
Retro | PMC | Phulambari | Pimpalgaon Gangdeo | 61,96,951 | 58,56,155 | 20-02-2023 | 9 Months | 3 | 0.08% | - | - | 0% | M/S Patel Construction
Retro | PMC | Phulambari | Wanegaon Kh & Bk | 89,38,007 | 98,43,654 | 2022-08-12 | 18 Months | 3 | 0.07% | - | - | 0% | M/S Nandini Construction
Retro | PMC | Phulambari | Lahanyachiwadi | 65,42,972 | 63,50,168 | 2022-12-30 | 12 Months | 3 | 0.06% | - | - | 0% | Sheekar Nagnath Kasture
Retro | PMC | Phulambari | Waregaon | 1,09,81,581 | 1,02,95,288 | 2023-01-20 | 9 Months | 3 | 0.02% | - | - | 0% | Shree Vishwajit Rupsingh Jadhao
Retro | PMC | Phulambari | Wadod Bazar& Wadod Kh | 4,13,96,774 | 3,82,00,275 | 2023-02-20 | 12 Months | 3 | 0.01% | - | - | 0% | M/S S. P. Construction
Retro | PMC | Sillod | Shindephal | 41,26,423 | 44,39,205 | 30-06-2022 | 4 Months | 3 | 100% | 91.-7% | - |  | Shree Rishikesh Anil Kale
Retro | PMC | Sillod | Khupta | 51,37,765 | 58,12,977 | 30-06-2022 | 6 Months | 3 | 100% | 54.53% | 31.7 |  | Shree Pramod Kakasaheb Kwde
Retro | PMC | Sillod | Takli Kh | 10,42,495 | 10,06,350 | 2022-10-12 | 3 Months | 3 | 100% | 91.69% | 9.23 | 0% | Shree Shubham Nanasaheb Janjal
Retro | PMC | Sillod | Sarola | 45,17,712 | 43,70,340 | 21-12-2022 | 3 Months | 3 | 95.49% | 94.96% | 41.5 | 0% | M/S Khushi Construction
Retro | PMC | Sillod | Talni | 48,70,157 | 48,05,413 | 28-12-2022 | 6 Months | 3 | 74.11% | - | - | 0% | Shree Suresh Ratanlal Jaiswal
Retro | PMC | Sillod | Gavahali | 41,75,003 | 39,62,123 | 23-01-2023 | 6 Months | 3 | 68.96% | - | - | 0% | Piyush Kantilal Salve
Retro | PMC | Sillod | Takli Jiwrag | 33,94,094 | 32,57,170 | 21-12-2022 | 3 Months | 3 | 51.15% | - | - | 0% | Shree Trushikesh Anil Kale
Retro | TSP | Sillod | Borgaon Kasari | 61,45,217 | 70,37,977 | 30-06-2022 | 6 Months | 3 | 46.31% | 46.1% | 32.45 |  | M/S Nandini Construction
Retro | PMC | Sillod | Mangrul | 32,10,342 | 29,85,475 | 23-01-2023 | 3 Months | 3 | 41.29% | - | - | 0% | Shree Suresh Ratanlal Jaiswal
Retro | PMC | Sillod | Anad | 13,82,553 | 13,56,278 | 28-12-2022 | 3 Months | 3 | 38.98% | - | - | 0% | Suresh Ratanlal Jaisawal
Retro | PMC | Sillod | Kaigaon | 55,60,446 | 55,04,804 | 15-12-2022 | 6 Months | 3 | 27.8% | - | - | 0% | Shree Ashok Janardhan Tayade
Retro | TSP | Sillod | Undangaon | 1,78,51,806 | 1,72,45,496 | 15-11-2022 | 12 Months | 3 | 26.73% | - | - | 0% | M/S Samir Construction
Retro | PMC | Sillod | Nillod | 48,75,392 | 47,68,148 | 28-12-2022 | 6 Months | 3 | 25.25% | - | - | 0% | Dinesh Laxman Aher
Retro | PMC | Sillod | Pimpalghat | 18,10,055 | 17,91,954 | 23-01-2023 | 3 Months | 3 | 0.48% | - | - | 0% | Shree Mahadeo Tukaram Fad
Retro | PMC | Sillod | Mandgaon | 22,73,178 | 22,27,691 | 23-01-2023 | 3 Months | 3 | 0.44% | - | - | 0% | Ganraj Construction
Retro | PMC | Sillod | Pimpalgaon Peth | 50,46,293 | 49,96,329 | 23-01-2023 | 6 Months | 3 | 0.38% | - | - | 0% | Nandini Construction
Retro | PMC | Sillod | Georai Shemi | 46,05,551 | 45,19,132 | 13-01-2023 | 3 Months | 3 | 0.34% | - | - | 0% | M/S Nandini Construction
Retro | PMC | Sillod | Andhari | 1,29,74,827 | 1,28,45,073 | 28-12-2022 | 3 Months | 3 | 0.34% | - | - | 0% | Shivshahi Construction
Retro | PMC | Sillod | Chinchkheda | 33,63,092 | 33,31,201 | 23-01-2023 | 6 Months | 3 | 0.32% | - | - | 0% | M/S Nandini Construction
Retro | PMC | Sillod | Bhawan | 56,05,412 | 55,49,920 | 23-01-2023 | 6 Months | 3 | 0.3% | - | - | 0% | M/S Nandini Construction
Retro | PMC | Sillod | Khedi | 49,14,442 | 47,89,921 | 16-01-2023 | 3 Months | 3 | 0.14% | - | - | 0% | Shree Suresh Ratanalal Jaiswal
Retro | PMC | Sillod | Modha Bk | 1,76,86,729 | 1,59,03,761 | 23-01-2023 | 18 Months | 3 | 0.12% | - | - | 0% | Shree Arun Ganpat Edhate
Retro | PMC | Sillod | Babhulgaon Bk | 11,91,411 | 11,91,411 | 31-03-2022 | 3 Months | 3 | 0.02% | - | - | 0% | Gram Panchayat Babhulgaon Bk
Retro | PMC | Sillod | Bodwad & Sarati | 16,07,785 | 15,59,386 | 30-01-2023 | 3 Months | 3 | 0.01% | - | - | 0% | Rahul Vishwnath Aage
Retro | TSP | Soegaon | Jangla Tanda | 30,29,873 | 31,79,549 | 30-06-2022 | 3 Months | 3 | 96.55% | 95.-8% | - |  | Shree Dilip Ramraw More
Retro | PMC | Soegaon | Umarvihiri | 16,17,523 | 16,17,523 | 31-03-2022 | 3 Months | 3 | 88.7% | 84.-8% | - |  | M/S D.R. More
Retro | TSP | Soegaon | Devhari | 29,96,749 | 29,67,081 | 2022-03-08 | 4 Months | 3 | 79.18% | 78.68% | 23.34 | 0% | Shree Anna Bhagwan Mote
Retro | PMC | Soegaon | Sawarkheda | 41,40,608 | 41,03,476 | 24-11-2022 | 12 Months | 3 | 53.29% | 51.24% | 21.03 | 0% | Shree Shubham Nanasaheb Janjal
Retro | PMC | Soegaon | Molkheda | 72,58,265 | 70,21,796 | 21-10-2022 | 12 Months | 3 | 50.59% | 48.81% | 34.27 | 0% | Shree Shubham Nanasaheb Janjal
Retro | PMC | Soegaon | Sawaldbara | 65,00,806 | 63,38,302 | 30-01-2023 | 9 Months | 3 | 41.71% | 33.66% | 21.33 | 0% | M/S Khushi Construction
Retro | PMC | Soegaon | Tikhi | 19,50,793 | 18,42,489 | 15-02-2023 | 3 Months | 3 | 2.15% | - | - | 0% | M/S Sambhaji Bhausaheb Shirasath
Retro | PMC | Soegaon | Bahulkheda | 76,87,415 | 72,60,641 | 15-02-2023 | 6 Months | 3 | 1% | - | - | 0% | M/S Sambhaji Bhausaheb Shirasath
Retro | PMC | Soegaon | Banoti | 54,60,999 | 52,34,642 | 23-01-2023 | 6 Months | 3 | 0.35% | - | - | 0% | Shree Kalpesh Shantilal Nainav - Ushakal Construction
Retro | PMC | Soegaon | Nimkhedi | 13,36,276 | 13,36,276 | 2022-07-09 | 3 Months | 3 | 0.31% | - | - | 0% | Sarpanch , Grampanchayat - Nimkhedi
Retro | PMC | Soegaon | Kaldari | 19,15,037 | 18,08,716 | 30-01-2023 | 3 Months | 3 | 0.25% | - | - | 0% | M/S Sambhaji Bhaosaheb Shirsath
Retro | PMC | Soegaon | Pimpala | 86,22,804 | 78,89,029 | 31-01-2023 | 12 Months | 3 | 0.18% | - | - | 0% | Shree Virendrasingh Vijaysingh Chavhan
Retro | PMC | Soegaon | Mahalbda & Pimpalwadi | 67,75,766 | 60,97,529 | 16-01-2023 | 6 Months | 3 | 0.17% | - | - | 0% | Shree Mangalsingh Ramesh Chavhan
Retro | PMC | Soegaon | Wangaon | 97,42,271 | 92,01,937 | 30-01-2023 | 9 Months | 3 | 0.14% | - | - | 0% | M/S Sambhaji Bhaosaheb Shirasath
Retro | PMC | Soegaon | Murti | 65,88,383 | 63,89,224 | 23-01-2023 | 6 Months | 3 | 0.12% | - | - | 0% | Shree Ramesh Panditrao Pawar
Retro | PMC | Soegaon | Nimbayati | 1,17,46,176 | 1,06,71,394 | 23-01-2023 | 12 Months | 3 | 0.12% | - | - | 0% | Shree Chandrakant Vishnu Mankape
Retro | PMC | Soegaon | Hanumantkheda | 47,07,433 | 47,07,368 | 31-01-2023 | 9 Months | 3 | 0.11% | - | - | 0% | Shree Yogesh Shyamarao Patil
Retro | PMC | Soegaon | Rampura | 97,87,067 | 96,90,218 | 23-01-2023 | 9 Months | 3 | 0.11% | - | - | 0% | Shree Sunil M Patil
Retro | PMC | Soegaon | Malegaon | 67,14,546 | 66,48,013 | 23-01-2023 | 6 Months | 3 | 0.08% | - | - | 0% | Shree Sunil M Patil
Retro | PMC | Soegaon | Nimbhora & Galwada | 95,20,573 | 94,26,276 | 31-01-2023 | 12 Months | 3 | 0.04% | - | - | 0% | Shree Yogesh Shyamrao Patil
Retro | PMC | Soegaon | Uppalkheda Sutonda | 1,19,98,971 | 1,11,32,327 | 20-02-2023 | 12 Months | 3 | 0.02% | - | - | 0% | M/S V R Mahajan
Retro | PMC | Vaijapur | Agar Saigaon | 8,18,239 | 8,18,239 | 2022-04-03 | 3 Months | 3 | 100% | - | - |  | Sarpanch, Graam Panchayat,Agar Saigaon
Retro | PMC | Vaijapur | Nadi | 9,36,607 | 9,36,607 | 23-02-2022 | 3 Months | 3 | 90% | - | - |  | Sarpanch , Grampanch - Nadi
Retro | PMC | Vaijapur | Satana | 12,67,857 | 12,67,857 | 31-03-2022 | 3 Months | 3 | 90% | - | - |  | Sarpanch , Grampanchayat - Satana
Retro | PMC | Vaijapur | Bhadali | 29,29,460 | 29,29,474 | 22-07-2022 | 3 Months | 3 | 85.29% | 78.72% | 23.06 |  | Shree Nanasaheb Kalange
Retro | PMC | Vaijapur | Kharaj | 22,09,837 | 21,48,793 | 2022-10-11 | 3 Months | 3 | 81.09% | 8-.89% | - | 0% | Swastik Jagannath Fulare - Aurangabad
Retro | PMC | Vaijapur | Kavitkheda | 10,12,728 | 11,81,000 | 23-02-2022 | 3 Months | 3 | 74.89% | 74.79% | 8.83 |  | Sarpanch. Gram Panchayat , Kavitheda
Retro | PMC | Vaijapur | Birola | 11,85,479 | 11,85,479 | 2022-04-03 | 3 Months | 3 | 70.21% | 58.16% | 6.89 |  | Sarpanch, Gram Panchayat, Birola
Retro | PMC | Vaijapur | Kapus Wadgaon |  |  |  | Months |  | 70% | - | -
Retro | PMC | Vaijapur | Panvi Khandala | 12,23,449 | 12,23,449 | 2022-04-03 | 3 Months | 3 | 69.2% | - | - |  | Sarpanch,Gram Panchayat, Panvi Khandala
Retro | PMC | Vaijapur | Hadas Pimpalgaon | 23,92,291 | 23,68,208 | 2022-11-10 | 3 Months | 3 | 65.82% | - | - | 0% | Shree Swastik Jagannath Fulare - Aurangabad
Retro | PMC | Vaijapur | Panvi Khurd | 9,43,254 | 9,43,254 | 31-03-2022 | 3 Months | 3 | 64.73% | 56.4% | 5.32 |  | Sarpanch, Gram Panchayat, Panvi Khurd
Retro | PMC | Vaijapur | Tunki | 8,96,161 | 8,96,161 | 2022-03-04 | 3 Months | 3 | 63.73% | 53.33% | 4.78 |  | Sarpanch, Gram Panchayat, Tunki
Retro | PMC | Vaijapur | Jategaon | 24,89,049 | 23,87,557 | 29-09-2022 | 3 Months | 3 | 61.48% | - | - | 0% | Shree S N Borde
Retro | PMC | Vaijapur | Lakhganaga | 23,44,456 | 23,24,436 | 14-11-2022 | 3 Months | 3 | 60.89% | - | - | 0% | Shree Vaibhav Pralhad Somvanshi
Retro | PMC | Vaijapur | Kapuswadgaon | 6,83,850 | 6,83,850 | 23-06-2022 | 3 Months | 3 | 60.87% | - | - | 0% | Sarpanch , Grampanchayat - Kapus Wadgaon
Retro | PMC | Vaijapur | Loni Kh | 13,38,496 | 13,38,496 | 24-02-2022 | 3 Months | 3 | 56.86% | 43.25% | 5.79 |  | Sarpancvh, Grampanchayat - Loni Kh
Retro | PMC | Vaijapur | Khambala | 8,26,276 | 8,26,276 | 31-03-2022 | 3 Months | 3 | 56.39% | 46.-5% | - |  | Sarpanch,Gram Panchayat, Khambala
Retro | PMC | Vaijapur | Nimgaon | 17,46,079 | 17,27,161 | 14-11-2022 | 3 Months | 3 | 55.87% | - | - | 0% | Nawanath Construction - Dhulegaon
Retro | PMC | Vaijapur | Takli Sagaj | 12,60,246 | 12,60,246 | 2022-03-04 | 3 Months | 3 | 55.8% | 43.66% | 5.5 |  | Sarpanch, Gram Panchayat, Takli Sagaj
Retro | PMC | Vaijapur | Sidhapurwadi | 19,22,420 | 16,99,419 | 28-07-2022 | 4 Months | 3 | 55.24% | - | - |  | Shree Sandeep Namdev Borde
Retro | PMC | Vaijapur | Fakirabadwadi | 13,25,005 | 13,25,005 | 2022-04-03 | 3 Months | 3 | 54.49% | 38.4% | 5.09 |  | Sarpanch Grampanchayat - Fakirabadwadi
Retro | PMC | Vaijapur | Shivrai | 19,68,072 | 19,50,297 | 25-10-2022 | 3 Months | 3 | 53.6% | - | - | 0% | Real Constro Projects Pvt Ltd - Aurangabad
Retro | PMC | Vaijapur | Bhokargaon | 19,68,627 | 17,31,407 | 2022-08-03 | 3 Months | 3 | 52.7% | - | - |  | M/S Hari Om Construction
Retro | PMC | Vaijapur | Goyagaon | 9,32,857 | 9,32,857 | 2022-04-03 | 3 Months | 3 | 51.31% | 39.95% | 3.73 |  | Sarpanch, Gram Panchayat - Goyagaon
Retro | PMC | Vaijapur | Pathri | 11,49,384 | 13,39,000 | 23-02-2022 | 3 Months | 3 | 41.53% | 4-.65% | - |  | Sarpanch, Gram Panchayat , Pathri
Retro | PMC | Vaijapur | Nagina Pimpalgaon | 9,28,261 | 9,28,261 | 23-02-2022 | 3 Months | 3 | 41.44% | 33.46% | 3.11 |  | Sarpanch,Gram Panchayat, Nagina Pimpalgaon
Retro | PMC | Vaijapur | Ladgaon | 15,88,035 | 15,14,949 | 2022-12-12 | 3 Months | 3 | 41.14% | - | - | 0% | Nills Construction
Retro | PMC | Vaijapur | Nandgaon | 6,13,393 | 6,13,393 | 31-03-2022 | 3 Months | 3 | 40% | - | - |  | Sarpanch , Grampanhayat - Nandagaon
Retro | PMC | Vaijapur | Pimpalgaon Khandala | 8,50,893 | 8,50,893 | 2022-03-04 | 3 Months | 3 | 40% | - | - |  | Sarpanch , Grampanchayat - Pimpalgaon Khandala
Retro | PMC | Vaijapur | Tartyachi Wadi | 3,42,857 | 3,42,857 | 31-03-2022 | 3 Months | 3 | 40% | - | - |  | Sarpanch , Grampanchayat - Hajipurwadi
Retro | PMC | Vaijapur | Zholegaon | 19,46,066 | 17,31,026 | 2022-08-03 | 3 Months | 3 | 35.09% | - | - |  | M/R Hari Om Construction
Retro | PMC | Vaijapur | Lasurgaon | 39,40,455 | 38,68,124 | 2022-07-10 | 3 Months | 3 | 34.49% | - | - | 0% | Shree V G Fulare
Retro | PMC | Vaijapur | Hamrapur | 19,37,659 | 20,13,589 | 23-01-2023 | 3 Months | 3 | 32.11% | - | - | 0% | Shree Atul Nikam
Retro | PMC | Vaijapur | Dahegaon | 9,01,593 | 9,01,593 | 2022-04-03 | 3 Months | 3 | 26.29% | - | - | 0% | Sarpanch , Grampanchayat - Dahegaon
Retro | PMC | Vaijapur | Garaj | 20,10,128 | 18,90,115 | 2022-08-03 | 3 Months | 3 | 24.28% | 23.3% | 4.4 |  | R.B.Udhage
Retro | PMC | Vaijapur | Babhulgaon Ganga | 6,25,680 | 6,25,680 | 2022-03-31 | 3 Months | 3 | 21.59% | - | - | 0% | Sarpanch Grampanchayat - Nandurdhok
Retro | PMC | Vaijapur | Mahalgaon | 77,22,549 | 77,14,907 | 24-11-2022 | 9 Months | 3 | 20.95% | - | - | 0% | Shree Yashawant Kandalkar
Retro | PMC | Vaijapur | Aghur | 39,25,672 | 40,70,541 | 31-10-2022 | 3 Months | 3 | 20.92% | - | - | 0% | M/S V R Mahajan
Retro | PMC | Vaijapur | Sanjarpurwadi | 16,05,546 | 15,88,687 | 31-01-2023 | 3 Months | 3 | 13.18% | - | - | 0% | Shree Sagar Sunil Shinde
Retro | PMC | Vaijapur | Raghunathpurwadi | 9,39,888 | 9,39,888 | 2022-04-03 | 3 Months | 3 | 10.99% | - | - |  | Sarpanch, Gram Panchayat, Raghunathpurwadi
Retro | PMC | Vaijapur | Dawala | 12,95,715 | 11,64,070 | 28-07-2022 | 3 Months | 3 | 6.35% | - | - |  | Shree S.N.Borde
Retro | PMC | Vaijapur | Hajipurwadi | 8,94,506 | 8,94,506 | 2022-11-01 | 3 Months | 3 | 5.99% | - | - |  | Sarpanch , Gramsevak- Hajipurwadi
Retro | PMC | Vaijapur | Manoor | 46,40,290 | 46,17,585 | 17-11-2022 | 6 Months | 3 | 0.79% | - | - | 0% | Shree Kamasaheb Kawade
Retro | PMC | Vaijapur | Deogaon Shani | 9,17,583 | 9,17,583 | 23-02-2022 | 3 Months | 3 | 0.35% | - | - |  | Sarpanch/ Gram Panchayat, Deogaon Shani
Retro | PMC | Vaijapur | Babhulgaon | 36,13,921 | 25,75,844 | 2022-02-08 | 3 Months | 3 | 0.32% | - | - |  | Shree Nanasaheb Kalnge
Retro | PMC | Vaijapur | Manoli | 12,63,909 | 12,63,909 | 24-02-2022 | 3 Months | 3 | 0.32% | - | - |  | Sarpanch , Grampanchayat - Manoli
Retro | PMC | Vaijapur | Golwadi | 19,83,414 | 20,25,262 | 31-10-2022 | 3 Months | 3 | 0.23% | - | - | 0% | M/S V R Mahajan
Retro | PMC | Vaijapur | Karanjgaon | 14,86,204 | 14,10,999 | 27-12-2022 | 3 Months | 3 | 0.23% | - | - | 0% | M/S Khairnar And Company
Retro | PMC | Vaijapur | Jiri | 10,76,480 | 10,76,480 | 2022-04-03 | 3 Months | 3 | 0.22% | - | - |  | Sarpanch,Gram Panchayat, Jiri
Retro | PMC | Vaijapur | Bhivgaon | 30,87,831 | 29,17,705 | 2022-09-12 | 3 Months | 3 | 0.22% | - | - | 0% | Shree Aditya Umesh Limbhare
Retro | PMC | Vaijapur | Tembhi | 17,64,476 | 21,48,793 | 2022-11-10 | 3 Months | 3 | 0.21% | - | - | 0% | Satwik Jaggannath Fulare
Retro | PMC | Vaijapur | Amanatpurwadi | 7,07,569 | 7,07,569 | 24-02-2022 | 3 Months | 3 | 0.2% | - | - |  | Sarpanch, Grampanchayat - Amanatpurwadi
Retro | TSP | Vaijapur | Surala | 52,10,886 | 51,51,511 | 23-01-2023 | 6 Months | 3 | 0.17% | - | - | 0% | Shree Manoj Vinod Patel
Retro | PMC | Vaijapur | Hanmantgaon | 11,21,261 | 11,21,261 | 31-03-2022 | 3 Months | 3 | 0.15% | - | - |  | Sarpanch,Graam Panchayat,Hanmantgaon
Retro | PMC | Vaijapur | Belgaon | 27,40,542 | 26,57,822 | 23-01-2023 | 3 Months | 3 | 0.15% | - | - | 0% | Akash Bajirao Tathe
Retro | PMC | Vaijapur | Chikatgaon | 26,52,641 | 27,47,840 | 2022-06-10 | 3 Months | 3 | 0.14% | - | - | 0% | Shree D U Joshi
Retro | PMC | Vaijapur | Tidi | 15,02,905 | 14,93,130 | 23-01-2023 | 3 Months | 3 | 0.14% | - | - | 0% | Shree Sachin Ankush Kale - 9850501244
Retro | PMC | Vaijapur | Biloli | 49,12,927 | 45,99,850 | 23-01-2023 | 6 Months | 3 | 0.12% | - | - | 0% | Anjali Ashok Gayakwad
Retro | PMC | Vaijapur | Alapurwadi | 11,58,628 | 11,58,628 | 24-02-2022 | 3 Months | 3 | 0.11% | - | - |  | Sarpanch, Grampanchayat- Alapurwadi
Retro | PMC | Vaijapur | Dhondalgaon | 40,92,833 | 39,41,393 | 15-12-2022 | 3 Months | 3 | 0.1% | - | - | 0% | Neels Construction
Retro | PMC | Vaijapur | Shioor | 1,72,83,130 | 1,55,15,080 | 29-12-2022 | 9 Months | 3 | 0.07% | - | - | 0% | M/S Khushi Construction
Retro | PMC | Vaijapur | Khandala | 1,13,12,357 | 1,06,34,918 | 25-01-2023 | 6 Months | 3 | 0.04% | - | - | 0% | Shree Sangharsh Rajeev Boladhane
New | TSP | Aurangabad | Shivgad Tanda | 69,04,060 | 76,01,133 | 30-08-2022 | 18 Months | 3 | 11.77% | - | - | 0% | Shree Suryabhan Sakharam Rathod
New | PMC | Aurangabad | Nagonachiwadi | 80,64,402 | 79,71,660 | 2023-08-02 | 6 Months | 3 | 0.1% | - | - | 0% | M/S Ruchita Construction
New | PMC | Aurangabad | Girnera | 58,87,353 | 58,72,484 | 30-01-2023 | 9 Months | 3 | 0.08% | - | - | 0% | Shree Viraj Pradip Awotade
New | PMC | Aurangabad | Jogwada | 88,81,494 | 88,02,539 | 30-01-2023 | 9 Months | 3 | 0.06% | - | - | 0% | Namadeo Muralidhar Ghodake
New | PMC | Aurangabad | Aurangapur | 1,06,47,481 | 1,00,56,626 | 2023-01-30 | 9 Months | 3 | 0.03% | - | - | 0% | Shree Saurabh Shantaram Kurhade
New | PMC | Aurangabad | Hivra | 69,83,385 | 63,56,636 | 23-01-2023 | 9 Months | 3 | 0.01% | - | - | 0% | Shree Saurabh Kurhade
New | PMC | Gangapur | Fatiyabad | 9,99,573 | 9,99,573 | 29-07-2022 | 3 Months | 3 | 100% | 76.31% | 7.63 |  | Mr Aditya Dev
New | PMC | Gangapur | Takliwadi | 15,76,557 | 16,33,251 | 2022-09-05 | 3 Months | 3 | 100% | 79.1% | 12.92 | 0% | Shree Rahul Balasaheb Udage
New | PMC | Gangapur | Bhalgaon | 31,72,549 | 30,42,094 | 2022-09-21 | 3 Months | 3 | 100% | 86.32% | 26.26 | 0% | Sancheti Associates- Kirtikumar Chandanmal Sancheti
New | PMC | Gangapur | Sarangpur | 12,55,984 | 12,55,984 | 2022-07-09 | 3 Months | 3 | 100% | 71.57% | 8.99 | 0% | Sarpanch Grampanchayat - Sarangpur (Dahegaon)
New | PMC | Gangapur | Uttarwadi | 4,97,269 | 4,97,269 | 2022-03-04 | 3 Months | 3 | 100% | 61.42% | 3.05 | 0% | Sarpanch Grampanchayat- Uttarwadi (Tandulwadi)
New | PMC | Gangapur | Mehbubkheda | 12,35,633 | 12,35,633 | 31-03-2022 | 3 Months | 3 | 100% | 68.34% | 8.44 | 0% | Sarpanch - Gram Panchayat, Mahebubkheda
New | PMC | Gangapur | Jogeswari & Kamlapur | 1,23,74,820 | 1,21,23,606 | 2022-09-12 | 12 Months | 3 | 99.39% | - | - | 0% | M/S Nasis Infrastructure
New | PMC | Gangapur | Ramrai | 29,39,567 | 28,95,159 | 2022-09-06 | 3 Months | 3 | 98.65% | 84.36% | 24.42 | 0% | Shree Trushikesh Anil Kambale
New | PMC | Gangapur | Khopeshwar | 10,96,578 | 10,96,578 | 2022-03-31 | 3 Months | 3 | 92.81% | - | - | 0% | Sarpanch Grampanchayat - Kopeshwar(Wadali)
New | PMC | Gangapur | Haibatpur | 13,08,363 | 13,08,363 | 28-07-2022 | 3 Months | 3 | 92.35% | 66.86% | 8.75 | 0% | Sarpanch - Gram Panchayat, Haibatpur
New | PMC | Gangapur | Sirasgaon | 27,35,542 | 26,46,599 | 2023-01-16 | 3 Months | 3 | 71.32% | - | - | 0% | Shree Shrikesh Prabhakar Sonawane
New | PMC | Gangapur | Limbe Jalgaon | 45,37,098 | 44,91,483 | 16-09-2022 | 3 Months | 3 | 40.89% | - | - | 0% | Alum Gafur Sheikh
New | PMC | Gangapur | Shingi | 25,88,676 | 25,02,072 | 23-01-2023 | 3 Months | 3 | 31.78% | - | - | 0% | Shree Sheikh Aftab Ajij
New | PMC | Gangapur | Balapur | 8,68,620 | 9,01,191 | 2022-07-09 | 3 Months | 3 | 28.03% | - | - | 0% | Balapur Gram Panchayat (Sarpanch )
New | PMC | Gangapur | Pratappur Wadi | 21,30,824 | 21,06,317 | 2022-11-11 | 3 Months | 3 | 25.83% | - | - | 0% | Sheikh Afatab Ajij
New | PMC | Gangapur | Ambelohal | 36,91,499 | 35,71,374 | 2022-09-12 | 6 Months | 3 | 25.2% | - | - | 0% | Shree Swastik Jagannath Fulare
New | PMC | Gangapur | Pimpalwadi | 8,23,482 | 8,23,458 | 23-06-2022 | 3 Months | 3 | 24.06% | - | - | 0% | Gram Panchayat
New | PMC | Gangapur | Alamgirpur | 4,83,923 | 4,83,923 | 2022-03-31 | 3 Months | 3 | 0.04% | - | - | 0% | Sarpanch - Grampanchayat Muddhesh Wadgaon
New | PMC | Gangapur | Pimparkheda | 4,24,866 | 6,37,685 | 31-03-2022 | 3 Months | 3 | 0.04% | - | - | 0% | Gram Panchayat
New | PMC | Gangapur | Nandeda | 14,18,799 | 14,02,316 | 2022-12-09 | 3 Months | 3 | 0.02% | - | - | 0% | Shree Sachin Dadasaheb Shelake
New | PMC | Gangapur | Akoli Wadgaon & Aminabad | 23,52,985 | 23,04,167 | 24-02-2023 | 3 Months | 3 | 0.02% | - | - | 0% | M/S Real Constro Projects Pvt Ltd
New | PMC | Gangapur | Hadiyabad | 9,82,744 | 9,82,762 | 2022-03-31 | 3 Months | 3 | 0.02% | - | - | 0% | Gram Panchayat
New | PMC | Gangapur | Hanumantgaon | 7,61,203 | 7,61,201 | 31-03-2022 | 3 Months | 3 | 0.02% | - | - | 0% | Gram Panchayat
New | PMC | Gangapur | Bagadi | 23,12,073 | 22,88,944 | 2022-10-21 | 3 Months | 3 | 0.01% | - | - | 0% | Shree Dipak Manikrao Ambilke
New | PMC | Gangapur | Pekalwadi | 16,35,374 | 14,99,605 | 2023-01-30 | 3 Months | 3 | 0.01% | - | - | 0% | Mr Alim Gufur Saikh
New | PMC | Gangapur | Dinwada | 16,13,202 | 15,32,540 | 2023-01-24 | 3 Months | 3 | 0.01% | - | - | 0% | M/S Ashwamedh Suppliers And Construction
New | PMC | Gangapur | Solegaon | 14,97,261 | 14,22,416 | 31-01-2023 | 3 Months | 3 | 0.01% | - | - | 0% | Shrikesh Prabhakar Sonwane
New | PMC | Gangapur | Khadak Waghalgaon | 13,24,543 | 13,24,544 | 2022-03-31 | 3 Months | 3 | 0.01% | - | - | 0% | Gram Panchayat
New | PMC | Gangapur | Bolthan | 11,21,206 | 10,42,474 | 31-03-2022 | 3 Months | 3 | 0.01% | - | - | 0% | Gram Panchayat
New | PMC | Gangapur | Fulshivara | 12,94,123 | 12,94,121 | 2022-09-07 | 3 Months | 3 | 0.01% | - | - | 0% | Gram Panchayat
New | PMC | Gangapur | Hakikatpur | 3,55,979 | 3,55,981 | 2022-03-31 | 3 Months | 3 | 0.01% | - | - | 0% | Gram Panchayat
New | PMC | Gangapur | Sarifpur | 11,17,790 | 11,17,793 | 23-06-2022 | 3 Months | 3 | 0.01% | - | - | 0% | Gram Panchayat
New | PMC | Kannad | Sawargaon | 1,23,58,195 | 1,20,44,102 | 2023-02-01 | 18 Months | 3 | 5.85% | 4.73% | 5.7 | 0% | Shree Saurabh Manchhindra Kurhade
New | PMC | Kannad | Gondegaon | 11,12,286 | 11,12,286 | 31-03-2022 | 3 Months | 3 | 0.69% | - | - |  | Sarpanch,Graam Panchayat,Gondegaon
New | PMC | Kannad | Jamdi | 12,37,539 | 12,37,539 | 31-03-2022 | 3 Months | 3 | 0.55% | - | - |  | Sarpanch,Graam Panchayat,Jamdi (F)
New | PMC | Kannad | Bhildari(Nagad) | 40,24,803 | 38,97,747 | 31-01-2023 | 9 Months | 3 | 0.3% | - | - | 0% | M/S Saibhumi Construction
New | PMC | Kannad | Khatkheda | 76,15,538 | 75,31,749 | 24-01-2023 | 18 Months | 3 | 0.21% | - | - | 0% | Shree L. P. Ghuge
New | PMC | Kannad | Bhildari Pishor | 1,65,84,798 | 1,60,85,611 | 31-01-2023 | 18 Months | 3 | 0.21% | - | - | 0% | Rockline Construction
New | PMC | Kannad | Telwadi | 79,44,752 | 78,65,240 | 23-01-2023 | 18 Months | 3 | 0.15% | - | - | 0% | Mayur Construction
New | PMC | Kannad | Tadpimpalgaon | 1,68,17,336 | 1,56,77,805 | 2023-08-02 | 18 Months | 3 | 0.14% | - | - | 0% | S P Construction
New | TSP | Kannad | Kolambi Makta | 82,27,366 | 80,62,091 | 24-01-2023 | 18 Months | 3 | 0.13% | - | - | 0% | Mayur Construction
New | PMC | Kannad | Amba | 1,10,85,108 | 1,10,85,133 | 23-01-2023 | 18 Months | 3 | 0.11% | - | - | 0% | Shree Pramod Kakasaheb Kawade
New | TSP | Kannad | Debhegaon | 1,07,08,600 | 1,03,88,287 | 30-01-2023 | 18 Months | 3 | 0.11% | - | - | 0% | Shree Ghanshyam Pawar
New | PMC | Kannad | Nimdongri | 39,32,339 | 41,42,423 | 23-01-2023 | 6 Months |  | 0.11% | - | - | 0% | M/S Rockline Construction
New | PMC | Kannad | Chikhalthana | 1,67,85,745 | 1,59,29,274 | 31-01-2023 | 18 Months | 3 | 0.09% | - | - | 0% | Shree Sangharsh Rajeev Boladhane
New | PMC | Kannad | Ghusur | 1,68,19,680 | 1,66,52,523 | 31-01-2023 | 18 Months | 3 | 0.09% | - | - | 0% | Shree Anil Kandalkar
New | PMC | Kannad | Shelgaon Khalsa & Jahagir | 2,39,80,036 | 2,26,12,982 | 2023-08-02 | 18 Months | 3 | 0.08% | - | - | 0% | S P Construction
New | PMC | Kannad | Mategaon | 60,27,223 | 61,02,199 | 31-01-2023 | 12 Months | 3 | 0.08% | - | - | 0% | M/S Rockline Construction
New | PMC | Kannad | Deoli | 48,61,426 | 47,51,012 | 20-02-2023 | 9 Months | 3 | 0.07% | - | - | 0% | Shree Vijay Khairanar
New | PMC | Kannad | Mungsapur | 30,42,510 | 29,87,671 | 20-02-2023 | 6 Months | 3 | 0.06% | - | - | 0% | M/S Rockline Construction
New | PMC | Kannad | Shevata | 59,66,123 | 55,41,309 | 20-02-2023 | 6 Months | 3 | 0.03% | - | - | 0% | Shree Kiran Bhausaheb Mhaisdhune
New | PMC | Kannad | Palshi Kh | 70,70,905 | 65,04,631 | 20-02-2023 | 12 Months | 3 | 0.02% | - | - | 0% | Patel Construction
New | PMC | Kannad | Nadrapur | 1,53,22,016 | 1,47,68,967 | 20-02-2023 | 18 Months | 3 | 0.01% | - | - | 0% | M/S V. R Mahajan
New | TSP | Khulatabad | Ghandeshwar | 53,23,861 | 53,23,858 | 30-06-2022 | 18 Months | 3 | 4.48% | - | - |  | M/S D.R.More
New | TSP | Khulatabad | Loni | 1,06,45,982 | 1,14,95,811 | 14-11-2022 | 18 Months | 3 | 4.35% | - | - | 0% | M/S V R Mahajan
New | PMC | Khulatabad | Sultanabad | 10,53,748 | 10,53,748 | 2022-07-09 | 3 Months | 3 | 0.33% | - | - | 0% | Sarpanch, Grampanchayat - Dhamangaon
New | TSP | Khulatabad | Daregaon | 2,96,10,766 | 3,39,92,968 | 2022-09-12 | 18 Months | 3 | 0.24% | - | - | 0% | Shree Sambhaji Bhaosaheb Shirsath
New | PMC | Khulatabad | Palaswadi & Sekhapuri | 88,76,200 | 86,79,100 | 20-02-2023 | 9 Months | 3 | 0.21% | - | - | 0% | Shree Vijay Khairanar
New | PMC | Khulatabad | Malkapur | 1,31,96,324 | 1,29,17,254 | 31-01-2023 | 18 Months | 3 | 0.17% | - | - | 0% | Shree B Y Dhakane
New | PMC | Khulatabad | Akhatwada | 1,65,04,712 | 1,54,44,986 | 2023-09-02 | 18 Months | 3 | 0.12% | - | - | 0% | S P Construction
New | PMC | Khulatabad | Salukheda | 72,30,278 | 65,01,488 | 2023-02-01 | 9 Months | 3 | 0.09% | - | - | 0% | Shree Arun Ganapat Edhate
New | PMC | Khulatabad | Sawkheda | 22,19,880 | 23,95,642 | 20-02-2023 | 6 Months | 3 | 0.08% | - | - | 0% | Shree Swaraj Darakh
New | TSP | Khulatabad | Palasgaon | 1,75,57,983 | 1,63,78,096 | 2023-02-08 | 18 Months | 3 | 0.06% | - | - | 0% | S P Construction
New | PMC | Paithan | Chanakwadi | 27,32,842 | 27,05,520 | 29-09-2022 | 3 Months | 3 | 91.79% | - | - | 0% | Shree Trushikesh Kale
New | PMC | Paithan | Khadgaon Paithan | 27,54,763 | 26,86,820 | 21-09-2022 | 3 Months | 3 | 78.09% | 74.93% | 20.13 | 0% | M/S V R Mahajan
New | PMC | Paithan | Wadala | 14,11,256 | 14,11,260 | 15-07-2022 | 3 Months | 3 | 71.75% | 51.79% | 7.31 |  | Mr Asharam Govindrao Pawar
New | PMC | Paithan | Inayatpur | 6,77,816 | 6,78,571 | 2022-06-23 | 3 Months | 3 | 61.99% | 51.58% | 3.5 | 0% | Sarapanch , Grampanchayat - Khadagaon
New | PMC | Paithan | Kaudgaon & Teherpur | 38,13,299 | 36,41,519 | 27-09-2022 | 3 Months | 3 | 57.88% | - | - | 0% | Shree Yogesh Uttamrao Rathod
New | PMC | Paithan | Shahpurmanegaon | 7,78,620 | 7,78,621 | 23-06-2022 | 3 Months | 3 | 55.21% | 46.87% | 3.65 | 0% | Sarpanch, Grampanchayat - Chauryahattar Jalgaon
New | PMC | Paithan | Karanjkheda | 12,35,958 | 12,35,958 | 2022-04-03 | 3 Months | 3 | 37.2% | 36.27% | 4.48 | 0% | Sarpanch Grampanchayat - Karanjkheda(Solnapur)
New | PMC | Paithan | Ismailpur | 8,55,335 | 8,55,357 | 31-03-2022 | 3 Months | 3 | 36.66% | 31.14% | 2.66 | 0% | Sarapanch , Grampanchayat - Changatpuri
New | PMC | Paithan | Mankapur, Balapur & Mulani Wadgaon | 23,63,973 | 23,07,473 | 23-01-2023 | 3 Months | 3 | 21.35% | - | - | 0% | Shree Shrikesh Sonawane
New | PMC | Paithan | Khadgaon | 27,54,826 | 26,86,820 | 21-09-2022 | 3 Months | 3 | 21.25% | - | - | 0% | M/S V R Mahajan
New | PMC | Paithan | Hiwara Chondala | 10,87,879 | 10,87,879 | 31-03-2022 | 3 Months | 3 | 18.89% | - | - |  | Sarpanch,Gram Panchayat, Chinchala
New | PMC | Paithan | Naygaon | 17,35,491 | 17,22,521 | 15-11-2022 | 3 Months | 3 | 15.51% | - | - | 0% | Shree Amol Anna Bhopale
New | PMC | Paithan | Naigaon 1 | 17,35,385 | 17,22,521 | 2022-11-15 | 3 Months | 3 | 15.25% | - | - | 0% | Shree Amol Anna Bhopale
New | PMC | Paithan | Kawasan | 15,39,132 | 15,39,057 | 14-12-2022 | 3 Months | 3 | 12.2% | - | - | 0% | Shree Amol Badranath Kalasakar
New | PMC | Paithan | Waki | 3,13,867 | 3,13,867 | 31-03-2022 | 3 Months | 3 | 0.14% | - | - | 0% | Sarpanch , Grampanchayat - Imampur
New | PMC | Paithan | Alipur | 3,90,425 | 3,90,425 | 28-07-2022 | 3 Months | 3 | 0.11% | - | - | 0% | Sarpanch, Grampanchayat - Lakhegaon
New | PMC | Paithan | Tondoli | 10,92,127 | 10,92,127 | 31-03-2022 | 3 Months | 3 | 0.1% | - | - | 0% | Sarpanch , Grampanchayat - Tondoli
New | PMC | Paithan | Adool Tanda | 9,70,447 | 9,70,447 | 2022-07-09 | 3 Months | 3 | 0.1% | - | - | 0% | Sarpanch , Grampanchayat - Adool (Bk)
New | PMC | Paithan | Taru Pimpalwadi | 11,16,047 | 11,16,047 | 31-03-2022 | 3 Months | 3 | 0.08% | - | - | 0% | Sarapanch , Grampanchayat - Taru Pimpalwadi
New | PMC | Paithan | Muradabad | 6,50,508 | 6,50,508 | 31-03-2022 | 3 Months | 3 | 0.06% | - | - | 0% | Sarpanch, Grampanchayat - Adool (Kh)
New | PMC | Paithan | Bramhagavhan | 19,27,427 | 18,22,625 | 29-09-2022 | 3 Months | 3 | 0.05% | - | - | 0% | Shree Ajinkya Ramrao Rathod
New | PMC | Paithan | Kasarpadli | 8,25,089 | 13,64,709 | 16-01-2023 | 3 Months | 3 | 0.05% | - | - | 0% | Shree Alok Gorade
New | PMC | Paithan | Shringarwadi | 11,15,958 | 11,15,958 | 31-03-2022 | 3 Months | 3 | 0.05% | - | - | 0% | Sarpanch , Grampanchayat - Shringarwadi
New | PMC | Paithan | Yasinpur | 4,59,687 | 4,59,687 | 31-03-2022 | 3 Months | 3 | 0.04% | - | - |  | Sarpanch, Gram Panchayat, Yasinpur
New | PMC | Paithan | Dhorkin | 36,66,325 | 35,00,764 | 23-01-2023 | 3 Months | 3 | 0.04% | - | - | 0% | Shree Arun Wasankar
New | PMC | Paithan | Nanegaon | 8,13,937 | 8,13,937 | 2022-07-28 | 3 Months | 3 | 0.04% | - | - | 0% | Sarpanch , Grampanhayat - Kherda
New | PMC | Paithan | Wawa | 10,09,438 | 10,09,438 | 31-03-2022 | 3 Months | 3 | 0.04% | - | - | 0% | Sarpanch , Grampanchayat - Balanagar
New | TSP | Paithan | Aliyabad | 17,40,159 | 15,13,938 | 2022-12-02 | 3 Months | 3 | 0.03% | - | - |  | M/S Hariom Construction - Mundwadi
New | PMC | Paithan | Diyanatpur | 6,22,218 | 6,22,218 | 31-03-2022 | 3 Months | 3 | 0.03% | - | - | 0% | Sarpanch, Grampanchayat - Pachalgaon
New | PMC | Paithan | Hanumantgaon | 10,51,186 | 10,51,186 | 2022-03-31 | 3 Months | 3 | 0.03% | - | - | 0% | Sarpanch, Grampanchayat - Paithan Kheda
New | PMC | Paithan | Kasar Padli | 13,89,775 | 13,89,775 | 16-01-2023 | 3 Months | 3 | 0.03% | - | - | 0% | Shree Alok Gorade
New | PMC | Paithan | Salwadgaon | 10,69,440 | 10,69,440 | 31-03-2022 | 3 Months | 3 | 0.03% | - | - | 0% | Sarpanch , Gram Panchayat - Salwadgaon
New | TSP | Paithan | Hirapur | 13,28,408 | 12,07,124 | 27-06-2022 | 3 Months | 3 | 0.02% | - | - |  | Shree B.B. Lahamge
New | PMC | Paithan | Chaurhyattar Jalgaon | 15,96,891 | 15,85,496 | 24-01-2023 | 3 Months | 3 | 0.02% | - | - | 0% | Shree Amol Aanna Bhopale
New | TSP | Paithan | Dabharul | 73,01,012 | 75,42,517 | 17-11-2022 | 4 Months | 3 | 0.01% | - | - | 0% | Shree Sandeep Niwruti Awhad
New | TSP | Paithan | Isarwadi | 86,25,758 | 90,16,351 | 17-11-2022 | 4 Months | 3 | 0.01% | - | - | 0% | Shree Sandeep Niwruti Awhad
New | TSP | Paithan | Pategaon | 39,73,346 | 41,28,743 | 29-11-2022 | 3 Months | 3 | 0.01% | - | - | 0% | M/S Rockline Construction
New | PMC | Paithan | Mirkheda | 54,68,258 | 13,91,829 | 23-01-2023 | 3 Months | 3 | 0.01% | - | - | 0% | Shree Piyush Kantilal Salawe
New | PMC | Paithan | Adul Bk | 44,33,766 | 43,20,247 | 23-01-2023 | 3 Months | 3 | 0.01% | - | - | 0% | Khushi Construction
New | PMC | Paithan | Dera | 10,35,360 | 10,35,360 | 2022-03-31 | 3 Months | 3 | 0.01% | - | - | 0% | Sarpanch, Grampanchayat - Dawarwadi
New | PMC | Paithan | Porgaon & Porgaon Tanda | 23,77,852 | 22,35,152 | 23-01-2023 | 3 Months | 3 | 0.01% | - | - | 0% | Shrimati Priyanka Rohit Nawandar
New | PMC | Phulambari | Pirbawada | 76,90,385 | 85,18,179 | 2022-11-18 | 6 Months | 3 | 26.41% | 2-.-2% | - | 0% | Shree S. R. Jaiswal
New | TSP | Phulambari | Gevrai Paiga | 1,53,98,371 | 1,71,55,083 | 30-06-2022 | 18 Months | 3 | 22.31% | 16.13% | 27.67 | 0% | M/S D R More
New | PMC | Phulambari | Shevta Kh | 26,97,281 | 27,27,509 | 27-12-2022 | 3 Months | 3 | 0.43% | - | - | 0% | Shree Shubham Nanduppa Chunake
New | PMC | Phulambari | Sanjul | 67,24,884 | 67,24,289 | 23-12-2022 | 12 Months | 3 | 0.15% | - | - | 0% | Shree Ghanshyam Narayan Pawar
New | PMC | Phulambari | Pophala | 1,14,98,242 | 1,06,76,059 | 25-01-2023 | 18 Months | 3 | 0.14% | - | - | 0% | Shree Aanna Bhagwan Mote
New | PMC | Phulambari | Babhulgaon | 84,72,830 | 79,98,394 | 30-01-2023 | 18 Months | 3 | 0.14% | - | - | 0% | Shree Arun Baburao Gadekar
New | PMC | Phulambari | Wiramgaon | 86,59,305 | 84,76,303 | 25-01-2023 | 9 Months | 3 | 0.1% | - | - | 0% | Shree Namadeo Murlidhar Ghodake
New | PMC | Phulambari | Adagaon Kh | 83,31,019 | 78,68,356 | 20-02-2023 | 9 Months | 3 | 0.05% | - | - | 0% | Shree Ramesh Panditrao Pawar
New | PMC | Phulambari | Murshidbadwadi | 1,02,84,090 | 93,58,559 | 20-02-2023 | 18 Months | 3 | 0.05% | - | - | 0% | M/S Ruchita Construction
New | PMC | Phulambari | Relgaon | 58,68,621 | 66,22,309 | 2022-11-22 | 18 Months | 3 | 0.04% | - | - | 0% | M/S Nandini Construction
New | PMC | Phulambari | Adgaon Bk | 73,12,081 | 70,15,953 | 20-02-2023 | 9 Months | 3 | 0.03% | - | - | 0% | Shree Anna Bhagawan Mote
New | PMC | Phulambari | Gumsatala | 54,54,515 | 51,46,273 | 20-02-2023 | 3 Months | 3 | 0.03% | - | - | 0% | Shree Ganesh Sarjerao Mete
New | TSP | Sillod | Chinchpur | 1,12,92,115 | 1,28,02,279 | 30-06-2022 | 15 Months | 3 | 14.03% | - | - |  | Sandeep Bhanudas Jnjala
New | PMC | Sillod | Pirola | 12,35,370 | 12,35,715 | 2022-09-07 | 3 Months | 3 | 9.53% | - | - | 0% | Sarpanch , Gram Panchayat - Pirola
New | PMC | Sillod | Didgaon | 46,89,272 | 48,53,380 | 23-01-2023 | Months | 3 | 6.57% | - | - | 0% | Suresh Ratanlal Jaisawal
New | PMC | Sillod | Mhasla Kh | 35,76,372 | 34,65,528 | 23-01-2023 | 3 Months | 3 | 6.27% | - | - | 0% | Sachin Chandrakant Deshmukh
New | PMC | Sillod | Pimpri | 23,20,530 | 22,97,553 | 23-01-2023 | 6 Months | 3 | 4.16% | - | - | 0% | Nandini Construction
New | PMC | Sillod | Doiphoda | 15,76,658 | 16,03,576 | 23-01-2023 | 6 Months | 3 | 2.48% | - | - | 0% | Shree Sachin Chandrakant Deshmukh
New | PMC | Sillod | Borgaon Sarwani | 42,41,664 | 41,97,163 | 28-12-2022 | 6 Months | 3 | 0.68% | - | - | 0% | Shubham Subhash Gavhane
New | PMC | Sillod | Golegaon Kh | 25,63,883 | 25,14,885 | 23-01-2023 | 6 Months | 3 | 0.44% | - | - | 0% | Swaraj Jagdish Darakh
New | TSP | Sillod | Bankinhola | 50,90,942 |  |  | Months |  | 0.43% | - | - | 0%
New | PMC | Sillod | Upli | 26,14,896 | 25,62,596 | 23-01-2023 | Months |  | 0.4% | - | - | 0% | Ganraj Construction
New | PMC | Sillod | Bhaigaon & Warkhedi | 61,71,883 | 61,10,790 | 23-01-2023 | 6 Months | 3 | 0.31% | - | - | 0% | M/S Nandini Construction
New | TSP | Sillod | Golegaon Bk | 72,04,667 | 72,04,621 | 23-01-2023 | 6 Months | 3 | 0.28% | - | - | 0% | Namrata Jayprakash Chavan
New | PMC | Sillod | Dakala | 5,64,297 | 5,65,179 | 2022-09-07 | 3 Months | 3 | 0.06% | - | - | 0% | Gram Panchayat Halda
New | TSP | Soegaon | Jangli Kota | 1,21,37,510 | 1,32,73,580 | 30-06-2022 | 18 Months | 3 | 30.94% | 29.-7% | - |  | Shree Dilip Ramarao More
New | PMC | Soegaon | Kinhi | 1,03,63,231 | 1,01,07,364 | 21-12-2022 | 12 Months | 3 | 0.18% | - | - | 0% | Saurabh Machhindra Kurhade
New | PMC | Soegaon | Thana | 98,63,549 | 93,70,271 | 23-01-2023 | 12 Months | 3 | 0.13% | - | - | 0% | Shree Swapnil Ramdas Kapase
New | PMC | Soegaon | Amkheda | 1,48,42,708 | 1,48,42,085 | 28-12-2022 | 12 Months | 3 | 0.13% | - | - | 0% | M/S Khushi Construction
New | PMC | Soegaon | Jarandi | 1,37,96,356 | 1,44,84,836 | 23-01-2023 | 6 Months | 3 | 0.13% | - | - | 0% | Shree Vilas Vitthal Patil
New | PMC | Soegaon | Warkhedi Kh | 47,13,493 | 46,31,082 | 18-11-2022 | 12 Months | 3 | 0.12% | - | - | 0% | Shree Suresh Ratanlal Jaiswal
New | PMC | Soegaon | Pohribk & Kh | 1,35,72,286 | 1,28,18,747 | 30-01-2023 | 12 Months | 3 | 0.12% | - | - | 0% | M/S Sambhaji Bhaosaheb Shirsath
New | PMC | Soegaon | Jawala | 65,93,601 | 65,93,618 | 31-01-2023 | 6 Months | 3 | 0.11% | - | - | 0% | Namrata Jayprakash Chavhan
New | PMC | Soegaon | Tidka | 1,16,70,011 | 1,15,30,664 | 31-01-2023 | 18 Months | 3 | 0.1% | - | - | 0% | Shree Virendrasingh Vijaysingh Chavhan
New | PMC | Soegaon | Palashkeda | 1,69,84,553 | 1,68,14,616 | 23-01-2023 | 12 Months | 3 | 0.08% | - | - | 0% | Shree Mahadeo Tukaram Fad
New | PMC | Soegaon | Mukhed | 75,18,772 | 75,26,526 | 23-01-2023 | 18 Months | 3 | 0.03% | - | - | 0% | Shree Ghanshyam Narayan Pawar
New | PMC | Soegaon | Wakadi | 88,78,106 | 82,36,508 | 20-02-2023 | 6 Months | 3 | 0.03% | - | - | 0% | M/S Rockline Construction
New | PMC | Vaijapur | Makramatpur | 11,85,714 | 11,85,714 | 31-03-2022 | 3 Months | 3 | 90% | - | - |  | Sarpanch , Grampanchayat - Tidhi
New | PMC | Vaijapur | Mhaski | 11,98,214 | 11,98,214 | 31-03-2022 | 3 Months | 3 | 90% | - | - |  | Sarpanch , Grampanchayat - Mhaski
New | PMC | Vaijapur | Narayanpur | 5,51,786 | 5,51,786 | 31-03-2022 | 3 Months | 3 | 90% | - | - |  | Sarpanch , Grampanchayat - Kangoni
New | PMC | Vaijapur | Kangoni | 5,96,005 | 5,96,005 | 31-03-2022 | 3 Months | 3 | 83.67% | 58.72% | 3.5 |  | Sarpanch, Grampanchayat - Kangoni
New | PMC | Vaijapur | Ekodi Sagaj | 14,74,342 | 14,38,179 | 2022-11-10 | 3 Months | 3 | 80.06% | - | - | 0% | Real Constro Projects Pvt Ltd - Aurangabad
New | PMC | Vaijapur | Malegaon Kannad | 12,67,189 | 12,67,189 | 2022-04-03 | 3 Months | 3 | 80% | - | - |  | Sarpanch , Grampanchayat - Malegaon Kannad
New | PMC | Vaijapur | Baigaon | 13,68,446 | 13,33,026 | 2022-09-12 | 3 Months | 3 | 72.28% | - | - | 0% | Shree Akshay Deochanad Hagawane
New | PMC | Vaijapur | Shahajatpur | 10,68,799 | 10,68,799 | 2022-04-03 | 3 Months | 3 | 72.16% | 53.45% | 5.71 |  | Sarpanch,Gram Panchayat, Shahajatpur
New | PMC | Vaijapur | Bhatana | 17,17,943 | 16,66,698 | 2022-09-07 | 3 Months | 3 | 71.58% | 68.2% | 11.37 | 0% | Shree S N Borde
New | PMC | Vaijapur | Jarul | 25,49,900 | 24,08,354 | 2022-03-11 | 3 Months | 3 | 71.42% | - | - | 0% | Shree V G Fulare
New | PMC | Vaijapur | Babtara | 37,64,023 | 39,30,006 | 29-09-2022 | 3 Months | 3 | 66.85% | - | - | 0% | Shree Yashwant Sambhaji Kambalkar
New | PMC | Vaijapur | Hingoni | 18,72,007 | 18,47,299 | 14-11-2022 | 3 Months | 3 | 66.48% | - | - |  | Shree Vaibhav Pralhad Somvanshi
New | PMC | Vaijapur | Daskul | 7,52,337 | 7,52,337 | 16-03-2022 | 3 Months | 3 | 65.21% | 53.84% | 4.05 |  | Sarpanch , Grampanchayt - Daskul
New | PMC | Vaijapur | Ballali Sagaj | 18,27,768 | 18,39,574 | 2022-11-10 | 3 Months | 3 | 62.63% | - | - | 0% | Real Constro Projects Pvt Ltd - Aurangabad
New | PMC | Vaijapur | Sawkhed Ganga | 30,33,483 | 29,57,695 | 14-11-2022 | 3 Months | 3 | 62.17% | - | - | 0% | Shree Sagar Sunil Shinde
New | PMC | Vaijapur | Koradgaon | 19,38,008 | 19,07,232 | 25-10-2022 | 3 Months | 3 | 59% | - | - | 0% | Real Constro Projects Pvt Ltd - Aurangabad
New | PMC | Vaijapur | Bhingi | 13,29,462 | 13,29,462 | 16-03-2022 | 3 Months | 3 | 56.02% | 48.33% | 6.43 |  | Sarapnach , Gramsevak - Bhingi
New | PMC | Vaijapur | Panghavan | 19,04,095 | 18,90,898 | 31-10-2022 | 3 Months | 3 | 53.6% | - | - | 0% | Vaibhav Pralhadrao Somwanshi - Ladgaon
New | PMC | Vaijapur | Kanak Sagaj | 21,97,488 | 21,86,862 | 14-10-2022 | 3 Months | 3 | 39.93% | - | - | 0% | Real Constro Projects Pvt Ltd - Aurangabad
New | PMC | Vaijapur | Persoda | 41,44,907 | 41,08,107 | 20-12-2022 | 3 Months | 3 | 37.21% | - | - | 0% | Shree Swastik Jagannath Fulare
New | PMC | Vaijapur | Sakegaon | 28,55,811 | 27,25,129 | 23-01-2023 | 3 Months | 3 | 28.5% | - | - | 0% | Shree Pramod Kamasaheb Kawade
New | PMC | Vaijapur | Khirdi Hargovinpur | 9,40,473 | 9,40,473 | 23-06-2022 | 3 Months | 3 | 27.67% | - | - | 0% | Sarpanch , Grampanchayat - Khirdi Hargovindapur
New | PMC | Vaijapur | Pendephal | 15,38,621 | 15,29,731 | 24-11-2022 | 3 Months | 3 | 20.13% | - | - | 0% | Shree Vaibhav Pralhadrao Somawanshi
New | PMC | Vaijapur | Rahegaon | 8,22,152 | 8,22,152 | 28-07-2022 | 3 Months | 3 | 18.37% | - | - | 0% | Sarpanch , Grampanchayat - Rahegaon
New | PMC | Vaijapur | Bendawadi | 9,60,810 | 9,60,810 | 31-03-2022 | 3 Months | 3 | 13.58% | - | - | 0% | Sarpanch Grampanchayat - Bendawadi
New | PMC | Vaijapur | Hilalpur | 19,36,362 | 19,39,075 | 28-12-2022 | 3 Months | 3 | 10.81% | - | - | 0% | Real Constro Projects Pvt Ltd
New | PMC | Vaijapur | Bhaigaon Ganga | 10,02,593 | 10,02,593 | 31-03-2022 | 3 Months | 3 | 0.53% | - | - |  | Sarpanch, Gram Panchayat - Bhaigaon Ganga
New | PMC | Vaijapur | Kiratpur | 5,51,578 | 5,51,578 | 31-03-2022 | 3 Months | 3 | 0.37% | - | - |  | Sarpanch Gram Panchayat - Kiratpur
New | PMC | Vaijapur | Talwada | 29,19,607 | 28,69,972 | 2022-06-07 | 3 Months | 3 | 0.26% | - | - |  | Omkar Bhausaheb Tandale
New | PMC | Vaijapur | Waghla | 32,33,243 | 30,98,544 | 2022-08-12 | 6 Months | 3 | 0.26% | - | - | 0% | Real Constro Projects Pvt Ltd
New | PMC | Vaijapur | Dongaon | 7,05,828 | 13,71,416 | 23-01-2023 | 3 Months | 3 | 0.24% | - | - | 0% | Mahesh Gowardhan Kale
New | PMC | Vaijapur | Wadji | 43,46,121 | 41,90,191 | 13-10-2022 | 6 Months | 3 | 0.23% | - | - | 0% | Shree Akshay Deochand Hagawane - Chandagaon
New | PMC | Vaijapur | Awwalgaon | 29,27,847 | 30,18,660 | 23-01-2023 | 3 Months | 3 | 0.19% | - | - | 0% | Shree Dipak Manikrao Ambilake
New | PMC | Vaijapur | Lakh Khandala | 20,77,460 | 19,13,540 | 2022-08-12 | 3 Months | 3 | 0.19% | - | - | 0% | Shree Rahul Balasaheb Udage
New | PMC | Vaijapur | Janephal | 41,67,481 | 41,48,854 | 21-12-2022 | 3 Months | 3 | 0.18% | - | - | 0% | Shree S N Borde
New | PMC | Vaijapur | Chendupal | 14,81,604 | 15,33,407 | 29-11-2022 | 3 Months | 3 | 0.17% | - | - | 0% | Shree Deepak Manikrao Ambilake
New | PMC | Vaijapur | Pokhari | 39,25,641 | 37,59,596 | 23-01-2023 | 6 Months | 3 | 0.16% | - | - | 0% | Anjali Ashok Gayakwad
New | PMC | Vaijapur | Walan | 20,15,890 | 20,07,792 | 23-01-2023 | 3 Months | 3 | 0.14% | - | - | 0% | Shree Rohit Pradip Tribhuwan
New | PMC | Vaijapur | Vaijapur Rural-2 | 1,31,66,161 | 1,27,56,720 | 25-01-2023 | 18 Months | 3 | 0.05% | - | - | 0% | Shree Jagdamba Construction
New | PMC | Vaijapur | Wanjargaon | 30,72,586 | 30,52,287 | 31-01-2023 | 3 Months | 3 | 0.01% | - | - | 0% | Shree Jagdamba Construction

## Executive Summary
Taluka | Category | Total No. of Scheme | No. of Schemes based on Physical Progress %
|  |  | 0-25% | 25-50% | 50-75% | 75-100% | Commissioned
Aurangabad | Retro | 39 | 34 | 3 | 1 | 1 | 0 | Aurangabad
| New | 6 | 6 | 0 | 0 | 0 | 0 | Gangapur
Gangapur | Retro | 145 | 98 | 8 | 4 | 14 | 21 | Kannad
| New | 32 | 16 | 5 | 1 | 4 | 6 | Khulatabad
Kannad | Retro | 77 | 70 | 4 | 2 | 1 | 0 | Paithan
| New | 21 | 21 | 0 | 0 | 0 | 0 | Phulambari
Khulatabad | Retro | 16 | 16 | 0 | 0 | 0 | 0 | Sillod
| New | 10 | 10 | 0 | 0 | 0 | 0 | Soegaon
Paithan | Retro | 93 | 60 | 19 | 10 | 4 | 0 | Vaijapur
| New | 41 | 33 | 2 | 4 | 2 | 0
Phulambari | Retro | 19 | 17 | 1 | 1 | 0 | 0
| New | 12 | 11 | 1 | 0 | 0 | 0
Sillod | Retro | 24 | 11 | 6 | 3 | 1 | 3
| New | 13 | 13 | 0 | 0 | 0 | 0
Soegaon | Retro | 21 | 15 | 1 | 2 | 3 | 0
| New | 12 | 11 | 1 | 0 | 0 | 0
Vaijapur | Retro | 62 | 28 | 10 | 19 | 4 | 1
| New | 40 | 18 | 4 | 12 | 6 | 0
| Retro | 0 | 0 | 0 | 0 | 0 | 0
| New | 0 | 0 | 0 | 0 | 0 | 0
| Retro | 0 | 0 | 0 | 0 | 0 | 0
| New | 0 | 0 | 0 | 0 | 0 | 0
| Retro | 0 | 0 | 0 | 0 | 0 | 0
| New | 0 | 0 | 0 | 0 | 0 | 0
| Retro | 0 | 0 | 0 | 0 | 0 | 0
| New | 0 | 0 | 0 | 0 | 0 | 0
| Retro | 0 | 0 | 0 | 0 | 0 | 0
| New | 0 | 0 | 0 | 0 | 0 | 0
| Retro | 0 | 0 | 0 | 0 | 0 | 0
| New | 0 | 0 | 0 | 0 | 0 | 0
| Retro | 0 | 0 | 0 | 0 | 0 | 0
| New | 0 | 0 | 0 | 0 | 0 | 0
| Retro | 0 | 0 | 0 | 0 | 0 | 0
| New | 0 | 0 | 0 | 0 | 0 | 0
| Retro | 0 | 0 | 0 | 0 | 0 | 0
| New | 0 | 0 | 0 | 0 | 0 | 0
Total | Retro | 496 | 349 | 52 | 42 | 28 | 25
| New | 187 | 139 | 13 | 17 | 12 | 6
Grand Total |  | 683 | 488 | 65 | 59 | 40 | 31
PMC
Taluka | Category | Total No. of Scheme | No. of Schemes based on Physical Progress %
|  |  | 0-25% | 25-50% | 50-75% | 75-100% | Commissioned
Aurangabad | Retro | 39 | 34 | 3 | 1 | 1 | 0
| New | 5 | 5 | 0 | 0 | 0 | 0
Gangapur | Retro | 144 | 98 | 8 | 3 | 14 | 21
| New | 32 | 16 | 5 | 1 | 4 | 6
Kannad | Retro | 77 | 70 | 4 | 2 | 1 | 0
| New | 19 | 19 | 0 | 0 | 0 | 0
Khulatabad | Retro | 16 | 16 | 0 | 0 | 0 | 0
| New | 6 | 6 | 0 | 0 | 0 | 0
Paithan | Retro | 85 | 56 | 18 | 9 | 2 | 0
| New | 36 | 28 | 2 | 4 | 2 | 0
Phulambari | Retro | 12 | 10 | 1 | 1 | 0 | 0
| New | 11 | 10 | 1 | 0 | 0 | 0
Sillod | Retro | 22 | 11 | 4 | 3 | 1 | 3
| New | 10 | 10 | 0 | 0 | 0 | 0
Soegaon | Retro | 19 | 15 | 1 | 2 | 1 | 0
| New | 11 | 11 | 0 | 0 | 0 | 0
Vaijapur | Retro | 61 | 27 | 10 | 19 | 4 | 1
| New | 40 | 18 | 4 | 12 | 6 | 0
| Retro | 0 | 0 | 0 | 0 | 0 | 0
| New | 0 | 0 | 0 | 0 | 0 | 0
| Retro | 0 | 0 | 0 | 0 | 0 | 0
| New | 0 | 0 | 0 | 0 | 0 | 0
| Retro | 0 | 0 | 0 | 0 | 0 | 0
| New | 0 | 0 | 0 | 0 | 0 | 0
| Retro | 0 | 0 | 0 | 0 | 0 | 0
| New | 0 | 0 | 0 | 0 | 0 | 0
| Retro | 0 | 0 | 0 | 0 | 0 | 0
| New | 0 | 0 | 0 | 0 | 0 | 0
| Retro | 0 | 0 | 0 | 0 | 0 | 0
| New | 0 | 0 | 0 | 0 | 0 | 0
| Retro | 0 | 0 | 0 | 0 | 0 | 0
| New | 0 | 0 | 0 | 0 | 0 | 0
| Retro | 0 | 0 | 0 | 0 | 0 | 0
| New | 0 | 0 | 0 | 0 | 0 | 0
| Retro | 0 | 0 | 0 | 0 | 0 | 0
| New | 0 | 0 | 0 | 0 | 0 | 0
Total | Retro | 475 | 337 | 49 | 40 | 24 | 25
| New | 170 | 123 | 12 | 17 | 12 | 6
Grand Total |  | 645 | 460 | 61 | 57 | 36 | 31
TSP
Taluka | Category | Total No. of Scheme | No. of Schemes based on Physical Progress %
|  |  | 0-25% | 25-50% | 50-75% | 75-100% | Commissioned
Aurangabad | Retro | 0 | 0 | 0 | 0 | 0 | 0
| New | 1 | 1 | 0 | 0 | 0 | 0
Gangapur | Retro | 1 | 0 | 0 | 1 | 0 | 0
| New | 0 | 0 | 0 | 0 | 0 | 0
Kannad | Retro | 0 | 0 | 0 | 0 | 0 | 0
| New | 2 | 2 | 0 | 0 | 0 | 0
Khulatabad | Retro | 0 | 0 | 0 | 0 | 0 | 0
| New | 4 | 4 | 0 | 0 | 0 | 0
Paithan | Retro | 8 | 4 | 1 | 1 | 2 | 0
| New | 5 | 5 | 0 | 0 | 0 | 0
Phulambari | Retro | 7 | 7 | 0 | 0 | 0 | 0
| New | 1 | 1 | 0 | 0 | 0 | 0
Sillod | Retro | 2 | 0 | 2 | 0 | 0 | 0
| New | 3 | 3 | 0 | 0 | 0 | 0
Soegaon | Retro | 2 | 0 | 0 | 0 | 2 | 0
| New | 1 | 0 | 1 | 0 | 0 | 0
Vaijapur | Retro | 1 | 1 | 0 | 0 | 0 | 0
| New | 0 | 0 | 0 | 0 | 0 | 0
| Retro | 0 | 0 | 0 | 0 | 0 | 0
| New | 0 | 0 | 0 | 0 | 0 | 0
| Retro | 0 | 0 | 0 | 0 | 0 | 0
| New | 0 | 0 | 0 | 0 | 0 | 0
| Retro | 0 | 0 | 0 | 0 | 0 | 0
| New | 0 | 0 | 0 | 0 | 0 | 0
| Retro | 0 | 0 | 0 | 0 | 0 | 0
| New | 0 | 0 | 0 | 0 | 0 | 0
| Retro | 0 | 0 | 0 | 0 | 0 | 0
| New | 0 | 0 | 0 | 0 | 0 | 0
| Retro | 0 | 0 | 0 | 0 | 0 | 0
| New | 0 | 0 | 0 | 0 | 0 | 0
| Retro | 0 | 0 | 0 | 0 | 0 | 0
| New | 0 | 0 | 0 | 0 | 0 | 0
| Retro | 0 | 0 | 0 | 0 | 0 | 0
| New | 0 | 0 | 0 | 0 | 0 | 0
| Retro | 0 | 0 | 0 | 0 | 0 | 0
| New | 0 | 0 | 0 | 0 | 0 | 0
Total | Retro | 21 | 12 | 3 | 2 | 4 | 0
| New | 17 | 16 | 1 | 0 | 0 | 0
Grand Total |  | 38 | 28 | 4 | 2 | 4 | 0

## Dist. Overview
Sr No. | Taluka | Category | Total Schemes |  | Work Order Issued |  | Work in Progress |  | Work Not Started
|  |  | PMC | TSP | PMC | TSP | PMC | TSP | PMC | TSP |  |  | Aurangabad
1 | Aurangabad | Retro | 83 | 3 | 58 | 0 | 39 | 0 | 19 | 0 |  |  | Gangapur | Taluka | No. of Schemes |  |  | Work Order Issued |  |  | Work In Progress |  |  | Work Not Started
|  | New | 21 | 5 | 11 | 2 | 5 | 1 | 6 | 1 |  |  | Kannad |  | Retro | New | Total | Retro | New | Total | Retro | New | Total | Retro | New | Total
2 | Gangapur | Retro | 151 | 0 | 148 | 1 | 144 | 1 | 4 | 0 |  |  | Khulatabad | Amravati | 1 | 11 | 12 | 1 | 11 | 12 |  | 7 | 7 | 1 | 4 | 5
|  | New | 33 | 1 | 32 | 0 | 32 | 0 | 0 | 0 |  |  | Paithan | Bhatkuli | 2 |  | 2 | 2 |  | 2 | 1 |  | 1 | 1 |  | 1
3 | Kannad | Retro | 126 | 0 | 93 | 0 | 77 | 0 | 16 | 0 |  |  | Phulambari | Chandu Bazar | 1 | 1 | 2 | 1 | 1 | 2 | 1 |  | 1 |  | 1 | 1
|  | New | 43 | 3 | 31 | 2 | 19 | 2 | 12 | 0 |  |  | Sillod | Chandur Railway |  | 2 | 2 |  | 2 | 2 |  | 2 | 2
4 | Khulatabad | Retro | 45 | 0 | 31 | 0 | 16 | 0 | 15 | 0 |  |  | Soegaon | Chikaldhara | 9 | 12 | 21 | 9 | 12 | 21 | 2 | 7 | 9 | 7 | 5 | 12
|  | New | 10 | 6 | 8 | 4 | 6 | 4 | 2 | 0 |  |  | Vaijapur | Dhamangaon | 4 | 2 | 6 | 4 | 2 | 6 | 2 | 2 | 4 | 2 |  | 2
5 | Paithan | Retro | 106 | 10 | 89 | 10 | 85 | 8 | 4 | 2 |  |  |  | Dharni | 15 | 25 | 40 | 15 | 25 | 40 | 7 | 10 | 17 | 8 | 15 | 23
|  | New | 42 | 7 | 38 | 6 | 36 | 5 | 2 | 1 | 3 |  |  | Morshi | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 2
6 | Phulambari | Retro | 35 | 3 | 23 | 7 | 12 | 7 | 11 | 0 | 1 |  |  | Nandgaon | 15 | 8 | 23 | 15 | 8 | 23 | 11 | 5 | 16 | 4 | 3 | 7
|  | New | 34 | 9 | 19 | 1 | 11 | 1 | 8 | 0 | 3 |  |  | Tiosa | 6 | 2 | 8 | 6 | 2 | 8 | 4 | 1 | 5 | 2 | 1 | 3
7 | Sillod | Retro | 45 | 4 | 45 | 4 | 22 | 2 | 23 | 2 |  |  |  | Warud |  | 15 | 15 |  | 15 | 15 |  | 9 | 9 |  | 6 | 6
|  | New | 35 | 4 | 35 | 3 | 10 | 3 | 25 | 0 |  |  |  | Total | 54 | 79 | 133 | 54 | 79 | 133 | 29 | 44 | 73 | 25 | 35 | 60
8 | Soegaon | Retro | 26 | 5 | 24 | 2 | 19 | 2 | 5 | 0 | [6 empty] | 0 | 0 | 0
|  | New | 15 | 3 | 15 | 3 | 11 | 1 | 4 | 2 | [6 empty] | 0 | 0 | 0
9 | Vaijapur | Retro | 88 | 3 | 80 | 1 | 61 | 1 | 19 | 0 | [6 empty] | 0 | 0 | 0
|  | New | 69 | 1 | 63 | 2 | 40 | 0 | 23 | 2
10 |  | Retro | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | New |  |  |  | 0 | 0 | 0 | 0 | 0
11 |  | Retro |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  | Alibag
|  | New |  |  |  | 0 | 0 | 0 | 0 | 0
12 |  | Retro |  |  |  | 0 | 0 | 0 | 0 | 0
|  | New |  |  |  | 0 | 0 | 0 | 0 | 0
13 |  | Retro |  |  |  | 0 | 0 | 0 | 0 | 0
|  | New |  |  |  | 0 | 0 | 0 | 0 | 0
14 |  | Retro |  |  |  | 0 | 0 | 0 | 0 | 0
|  | New |  |  |  | 0 | 0 | 0 | 0 | 0
15 |  | Retro |  |  |  | 0 | 0 | 0 | 0 | 0 |  | Uran
|  | New |  |  |  | 0 | 0 | 0 | 0 | 0
16 |  | Retro |  |  |  | 0 | 0 | 0 | 0 | 0
|  | New |  |  |  | 0 | 0 | 0 | 0 | 0
17 |  | Retro |  |  |  |  | 0 | 0 | 0 | 0
|  | New |  | 0 |  |  | 0 | 0 | 0 | 0
| Total | Retro | 705 | 28 | 591 | 25 | 475 | 21 | 116 | 4
|  | New | 302 | 39 | 252 | 23 | 170 | 17 | 82 | 6
| Grand Total |  | 1007 | 67 | 843 | 48 | 645 | 38 | 198 | 10
|  |  | 1074 |  | 891 |  | 683 |  | 208

## Amravati - Dist Overview
Taluka | No. of Schemes |  |  | Work Order Issued |  |  | Work In Progress |  |  | Work Not Started
| Retro | New | Total | Retro | New | Total | Retro | New | Total | Retro | New | Total
Amravati
Bhatkuli
Chandu Bazar
Chandur Railway
Chikaldhara
Dhamangaon
Dharni
Morshi
Nandgaon
Tiosa
Warud
Total

## Sheet5
Alibag Taluka
1 | Poynad | Arvind Dhondu Pashilkar | 1,98,75,762 | 2022-03-11 | 13 Months | 30% | 26.06% | 5179650.48 | 387
2 | Kurkundi Koltebhi | Suprabhat Infrazone Pvt.Ltd. ( Aashish Suresh Gurav ) | 66,20,883 | 25-11-2022 | 9 Months | 29% | - | -
3 | Dehen Bhakarwad | Gajrai Construction ( Dipak Mhanure | 81,72,095 | 19-10-2022 | 10 Months | 28% | - | - |  | Alibag Taluka
4 | Mahan | Bhargavi Construction ( Umesh Pandurang Tople) | 11,16,903 | 2022-07-12 | 13 Months | 27% | - | - |  | 1 | Tajpura | Dhanesh Padmakar Tambdkar | 58,33,381 | 26-09-2022 | 13 Months | 45.53% | 45.13% | 26.32
5 | Revas | Shivsai Construction ( Trupti Jitendra Pawar) | 92,79,303 | 2022-03-11 | 13 Months | 25% | - | - |  | 2 | Bodani | Vishal Rajendra Mande | 1,59,96,871 | 13-10-2022 | 13 Months | 32.99% | 28.02% | 4482913
6 | Aambepur | Arvind Dhondu Pashilkar | 1,95,36,802 | 2022-12-12 | 13 Months | 25% | - | - |  | 3 | Navenagar | Sagar Dilip Bankhele | 82,29,679 | 2022-06-10 | 13 Months | 30.65% | 29.91% | 2461496
7 | Shrigaon Medhekhar | Arvind Dhondu Pashilkar | 1,98,89,387 | 21-11-2022 | 13 Months | 0.4% | - | - |  | 4 | Chinchoti | Zada Enterprises | 1,98,581 | 28-11-2022 | 13 Months | 30% | - | -
8 | Hemnagar | Hitesh Prbhakar Thakur | 80,60,775 | 21-11-2022 | 10 Months | 0.38% | - | - |  | 5 | Usar | Jay Hanuman Construction ( Raju Kashinath Magar) | 1,05,02,166 | 17-10-2022 | 13 Months | 25% | - | -
9 | Saral | Hitesh Prbhakar Thakur | 58,65,513 | 14-11-2022 | 10 Months | 0.01% | - | - |  | 6 | Mahajane | Beban Construction ( Nadim Khalil Beban) | 76,08,705 | 26-09-2022 | 13 Months | 22.8% | - | -
Karjat Taluka | [9 empty] | 7 | Ramraj | Dhanesh Padmakar Tambdkar | 1,17,01,878 | 13-10-2022 | 13 Months | 18.27% | - | -
10 | Wave | Jay Baldigambar Construction (Nainesh Ashok Dighe ) | 82,75,257 | 2022-09-10 | 9 Months | 16% | - | - |  | 8 | Vanavli | Jay Hanuman Construction ( Raju Kashinath Magar) | 84,34,568 | 21-11-2022 | 9 Months | 11% | - | -
Mangaon Taluka | [9 empty] | 9 | Pezari | Arvind Dhondu Pashilkar | 1,57,34,783 | 29-11-2022 | 13 Months | 10.33% | 28.9% | 4547450
11 | Mugavali | Shrishel Shakarappa Aasgi | 69,79,571 | 27-09-2022 | 13 Months | 56% | 54.03% | 3770896 |  | 10 | Bhadane | Jay Hanuman Construction ( Raju Kashinath Magar) | 62,41,267 | 25-11-2022 | 9 Months | 10% | - | -
12 | Repoli | Aniket Pramod Ghosalkar | 68,70,018 | 2022-01-11 | 9 Months | 56% | 53.65% | 3685580 |  | 11 | Beloshi | Beban Construction ( Nadim Khalil Beban) | 99,74,288 | 2022-07-10 | 13 Months | 7.59% | - | -
13 | Jawali | Shrishel Shakarappa Aasgi | 71,48,209 | 27-09-2022 | 10 Months | 35% | 33.91% | 2423985 |  | 12 | Bherase | D.K. Construction ( Dinesh Manohar Khaire) | 1,12,71,421 | 13-10-2022 | 13 Months | 5.2% | - | -
14 | Shiravali Tarfe Nijampur | Shrishel Shakarappa Aasgi | 57,07,193 | 2022-06-10 | 9 Months | 34% | 30.84% | 1759842 |  | 13 | Wave | Beban Construction ( Nadim Khalil Beban) | 66,01,362 | 30-09-2022 | 13 Months | 0.93% | - | -
15 | Kelgan | Vishal Laxshumanrav Sarangkar | 85,88,767 | 2022-09-11 | 9 Months | 30% | - | - |  | 14 | Lonare | Chakrapani Parshuram Mhatre | 44,13,468 | 2022-03-10 | 13 Months | 0.04% | - | -
16 | Umroli Diwali | Ganesh Rajeshirke | 81,33,985 | 27-09-2022 | 13 Months | 29.78% | 18.7% | 1521246 |  | 15 | Bopoli Vaghjai | Shrinath Ashok Patil | 67,89,104 | 25-11-2022 | 9 Months | 0.01% | - | -
17 | Nivi | Rohan Rajendrakumar Kadam | 86,20,397 | 21-10-2022 | 9 Months | 28% | - | - |  | 16 | Kude | Hitesh Prbhakar Thakur | 5,20,357 | 2022-09-12 | 9 Months | 0.01% | - | -
18 | Moor | Gajrai Construction ( Dipak Mhanure | 1,02,65,679 | 30-09-2022 | 13 Months | 27% | 10.5% | 1078083 |  | Karjat Taluka
19 | Kalamanje | Rohan Rajendrakumar Kadam | 80,28,375 | 25-10-2022 | 9 Months | 27% | - | - |  | 17 | Hedawali | Fairwing Infracon Pvt.Ltd. ( Anil Piparkar) | 1,30,22,064 | 19-10-2022 | 13 Months | 39% | - | -
20 | Goregaon | Shrishel Shakarappa Aasgi | 2,16,64,425 | 17-10-2022 | 13 Months | 26% | 22.73% | 4923859 |  | 18 | Gudhawan | Om Construction & Devlpers (Pramod Khade ) | 1,33,50,252 | 21-10-2022 | 13 Months | 29% | - | -
21 | Wadhvan | Sanjay Ekanath Chavhan | 50,28,414 | 27-09-2022 | 9 Months | 25.11% | - | - |  | 19 | Ekasal | Samir Ram Logale | 98,84,056 | 25-10-2022 | 10 Months | 25% | - | -
22 | Shrivali Tarf Govele | Ganesh Rajeshirke | 59,56,263 | 2022-06-10 | 13 Months | 25% | 23.43% | 1395807 |  | 20 | Wadap | Pawar Infra ( Vinayak Pawar) | 98,66,831 | 2022-01-12 | 10 Months | 25% | - | -
23 | Sangi | Mira Construction ( Ganraj Shubhash Pashilkar) | 55,30,331 | 2022-07-10 | 13 Months | 24% | 23.83% | 1318098 |  | 21 | Salokh T Need | Chakrapani Parshuram Mhatre | 68,39,957 | 2022-07-10 | 7 Months | 21.65% | - | -
24 | Kalvan | Sanjay Ekanath Chavhan | 68,85,408 | 27-09-2022 | 13 Months | 18.66% | - | - |  | 22 | Mugape | Pawar Infra ( Vinayak Pawar) | 35,15,698 | 27-09-2022 | 10 Months | 15.52% | - | -
25 | Muthavali Tarfe Nijampur | Ganesh Rajeshirke | 50,45,673 | 2022-07-10 | 13 Months | 16.3% | - | - |  | 23 | Nangurle | Pawar Infra ( Vinayak Pawar) | 54,47,912 | 27-09-2022 | 9 Months | 12.68% | - | -
26 | Manjurne | Niraj Narendra Deshmukh | 44,56,927 | 30-09-2022 | 13 Months | 10.13% | - | - |  | 24 | Chochi | Arvind Dhondu Pashilkar | 1,67,49,868 | 2022-12-12 | 13 Months | 12% | - | -
27 | Dhaksheli | Mira Construction ( Ganraj Shubhash Pashilkar) | 48,30,847 | 30-09-2022 | 13 Months | 7.29% | - | - |  | 25 | Salpe | Pawar Infra ( Vinayak Pawar) | 61,83,404 | 14-11-2022 | 9 Months | 11% | - | -
28 | Bhale | Arvind Dhondu Pashilkar | 1,59,36,082 | 27-09-2022 | 13 Months | 6% | - | - |  | 26 | Petha | Pawar Infra ( Vinayak Pawar) | 4,50,881 | 14-11-2022 | 7 Months | 9.59% | - | -
29 | Javathe | Mira Construction ( Ganraj Shubhash Pashilkar) | 62,88,695 | 30-09-2022 | 10 Months | 1.17% | 56.18% | 3533233 |  | 27 | Chevane | Fairwing Infracon Pvt.Ltd. ( Anil Piparkar) | 88,05,431 | 26-09-2022 | 13 Months | 0.88% | - | -
30 | Sai | Raj Enterprises ( Vijay Salunkhe ) | 2,59,92,496 | 13-10-2022 | 19 Months | 0.95% | - | - |  | 28 | Sugave | Fairwing Infracon Pvt.Ltd. ( Anil Piparkar) | 1,71,23,996 | 2022-07-12 | 13 Months | 0.12% | - | -
31 | Waki Tarf Nizampur | Dhanraj Enterprises ( Sudarshan Kadam) | 59,71,413 | 2022-07-10 | 7 Months | 0.36% | - | - |  | Khalapur Taluka
32 | Cheravali | U. V. Giri | 39,58,631 | 27-09-2022 | 7 Months | 0.11% | 33.6% | 1329974 |  | 29 | Talashi | Hitesh Prbhakar Thakur | 44,17,995 | 19-10-2022 | 7 Months | 30% | - | -
33 | Tharmari | Ganesh Rajeshirke | 1,18,46,014 | 2022-07-10 | 13 Months | 0.09% | - | - |  | 30 | Wavarle | D.K. Construction ( Dinesh Manohar Khaire) | 1,77,74,543 | 2022-01-11 | 13 Months | 25% | - | -
34 | Rudrawali | Rohan Rajendrakumar Kadam | 8,91,152 | 25-10-2022 | 9 Months | 0.07% | - | - |  | 31 | Bhilavale | Gaikar Construction ( Dashrath Arjun Gaikar) | 1,36,16,583 | 21-10-2022 | 13 Months | 15% | - | -
35 | Umbardi | Mira Construction ( Ganraj Shubhash Pashilkar) | 54,95,785 | 30-09-2022 | 13 Months | 0.06% | - | - |  | 32 | Sodewadi | Samir Ram Logale | 1,44,04,161 | 25-11-2022 | 13 Months | 15% | 12.51% | 1802218
36 | Muthwali Tarf Tale | Shrishel Shakarappa Aasgi | 57,07,193 | 2022-06-10 | 13 Months | 0.03% | - | - |  | 33 | Karambelii | Pawar Infra ( Vinayak Pawar) | 94,28,405 | 2022-07-10 | 10 Months | 10% | - | -
37 | Saje | Gundekar Mukund Madhukar | 1,02,48,916 | 2022-09-11 | 13 Months | 0.03% | - | - |  | 34 | Dolavali & Mankivali | Fairwing Infracon Pvt.Ltd. ( Anil Piparkar) | 1,12,54,265 | 26-09-2022 | 13 Months | 0.14% | - | -
Murud Taluka | [9 empty] | 35 | Majgaon | Shailesh Sambhaji Patil | 62,13,697 | 25-11-2022 | 10 Months | 0.01% | - | -
38 | Mahalunge Kh. | Jay Hanuman Construction ( Raju Kashinath Magar) | 32,18,261 | 21-11-2022 | 9 Months | 11% | - | - |  | Mahad Taluka
Panvel Taluka | [9 empty] | 36 | Warangi | Rohan Rajesh Temakar | 99165 | 30-09-2022 | 10 Months | 13% | - | -
39 | Sangade | Saniya Vijay Pashilkar | 9,84,227 | 29-09-2022 | 7 Months | 0.56% | - |  |  | Mangaon Taluka
40 | Nitalas | Saniya Vijay Pashilkar | 99021 | 29-09-2022 | 7 Months | 0.29% | - | - |  | 37 | Harkolkond | Karan Kishor Patil | 7,74,851 | 2022-09-11 | 10 Months | 28% | - | -
[10 empty] | 38 | Kandalgaon Khu. | Mira Construction ( Ganraj Shubhash Pashilkar) | 58,60,935 | 25-11-2022 | 9 Months | 0.37% | - | -
[10 empty] | 39 | Boriwali Bormach | Raj Enterprises ( Vijay Salunkhe ) | 1,15,53,873 | 2022-12-12 | 13 Months | 0.16% | - | -
Mhasla Taluka
[10 empty] | 40 | Mendadikond | Jayvant Shantaram Aavere | 1,08,39,911 | 2022-07-12 | 13 Months | 28% | 9.69% | 1050420
[10 empty] | 41 | Krushannagar | Sagar Ravindra Mohite | 17,92,689 | 2022-09-11 | 7 Months | 25% | - | -
[10 empty] | 42 | Ghonse | Arvind Dhondu Pashilkar | 1,89,94,389 | 2022-03-11 | 13 Months | 25% | - | -
[10 empty] | 43 | Tamhane Karambe | Jayvant Shantaram Aavere | 77,56,625 | 2022-06-10 | 13 Months | 15.75% | - | -
[10 empty] | 44 | Ghum | Jayvant Shantaram Aavere | 28,90,464 | 13-10-2022 | 10 Months | 12.76% | - | -
[10 empty] | 45 | Sanderi | R. M. Construction ( Majahar Deshmukh ) | 1,71,80,295 | 14-11-2022 | 13 Months | 12% | - | -
[10 empty] | 46 | Devghar Kond | Jayvant Shantaram Aavere | 52,05,703 | 2022-09-11 | 7 Months | 11% | - | -
[10 empty] | 47 | Kudtudi | Sagar Ravindra Mohite | 51,77,658 | 2022-03-11 | 7 Months | 10% | - | -
[10 empty] | 48 | Pabhare | Devidas Sambhaji Chavhan | 2,87,09,736 | 2022-02-11 | 13 Months | 4.92% | - | -
[10 empty] | 49 | Kharsai | Arvind Dhondu Pashilkar | 19,71,188 | 2022-01-11 | 13 Months | 0.66% | - | -
Murud Taluka
[10 empty] | 50 | Eakdara | Ninad Naresh Salunkhe | 1,33,67,386 | 13-10-2022 | 13 Months | 0.04% | - | -
[10 empty] | 51 | Wawdungi - Saigaon | Dhanesh Padmakar Tambdkar | 56,65,819 | 13-10-2022 | 9 Months | 0.01% | - | -
Panvel Taluka
[10 empty] | 52 | Deravli | Shrimarkadey Construction | 40,96,674 | 2022-12-12 | 7 Months | 54.96% | - | -
[10 empty] | 53 | Dapiwali | Shri. Enterprises ( Manoj Khadekar ) | 38,42,082 | 2022-09-12 | 7 Months | 40.27% | - | -
[10 empty] | 54 | Umroli | Achitya Construction ( Akshay Prakash Shete ) | 65,82,286 | 19-10-2022 | 9 Months | 27% | - | -
[10 empty] | 55 | Tamsai | Shrimarkadey Construction | 28,89,726 | 2022-03-11 | 7 Months | 20.71% | - | -
[10 empty] | 56 | Ambe Tarfe Taloje | Nikhil Construction ( Shantaram Hiraji Borkar) | 62,27,355 | 30-09-2022 | 13 Months | 17% | 16.82% | 1047355
[10 empty] | 57 | Poynje | Achitya Construction ( Akshay Prakash Shete ) | 78,74,529 | 2022-03-11 | 10 Months | 15% | - | -
[10 empty] | 58 | Khirane | Shrimarkadey Construction | 7,72,691 | 2022-01-11 | 9 Months | 13% | - | -
[10 empty] | 59 | Pali Ku. | Achitya Construction ( Akshay Prakash Shete ) | 46,11,995 | 2022-02-12 | 7 Months | 10% | - | -
[10 empty] | 60 | Kahale | Shri. Enterprises ( Manoj Khadekar ) | 1,95,42,392 | 19-10-2022 | 13 Months | 5.22% | - | -
[10 empty] | 61 | Kondale | Achitya Construction ( Akshay Prakash Shete ) | 46,79,019 | 2022-01-11 | 7 Months | 1.55% | 24.21% | 1132760
[10 empty] | 62 | Nitale | Achitya Construction ( Akshay Prakash Shete ) | 38,08,504 | 2022-03-11 | 7 Months | 0.16% | - | -
[10 empty] | 63 | Karambeli T. Taloje | Nikhil Construction ( Shantaram Hiraji Borkar) | 85,74,336 | 25-10-2022 | 9 Months | 0.08% | - | -
[10 empty] | 64 | Kasarbhat | Shailesh Sambhaji Patil | 44,28,877 | 29-11-2022 | 7 Months | 0.05% | - | -
[10 empty] | 65 | Dundare | Achitya Construction ( Akshay Prakash Shete ) | 1,26,09,353 | 2022-01-11 | 13 Months | 0.03% | - | -
[10 empty] | 66 | Karade Kh | Nikhil Construction ( Shantaram Hiraji Borkar) | 88,09,693 | 30-09-2022 | 9 Months | 0.01% | - | -
Pen Taluka
[10 empty] | 67 | Karambeli | D.K. Construction ( Dinesh Manohar Khaire) | 1,44,20,159 | 2022-07-10 | 13 Months | 62% | 60.47% | 8719873
[10 empty] | 68 | Warsai | D.K. Construction ( Dinesh Manohar Khaire) | 1,67,50,807 | 13-10-2022 | 13 Months | 45% | 43.28% | 7249093
[10 empty] | 69 | Koleti | Shri. Enterprises ( Manoj Khadekar ) | 96,82,355 | 20-10-2022 | 10 Months | 39% | 37.03% | 3585311
[10 empty] | 70 | Padle | D.K. Construction ( Dinesh Manohar Khaire) | 92,36,579 | 2022-11-08 | 10 Months | 37% | - | -
[10 empty] | 71 | Kharpada | D.K. Construction ( Dinesh Manohar Khaire) | 1,13,00,892 | 2022-10-08 | 14 Months | 35% | - | -
[10 empty] | 72 | Nighvali | D.K. Construction ( Dinesh Manohar Khaire) | 74,57,644 | 21-09-2022 | 9 Months | 34% | - | -
[10 empty] | 73 | Kurnad | D.K. Construction ( Dinesh Manohar Khaire) | 1,13,83,506 | 2022-10-08 | 13 Months | 30% | - | -
[10 empty] | 74 | Dadar | Nilesh Construction ( Nilesh Tulshiram Mhatre ) | 79,52,801 | 19-10-2022 | 9 Months | 29% | - | -
[10 empty] | 75 | Jite | R. M. Construction ( Majahar Deshmukh ) | 1,71,87,787 | 2022-03-10 | 13 Months | 27.38% | - | -
[10 empty] | 76 | Patani Pandapur | Nikhil Construction ( Shantaram Hiraji Borkar) | 1,44,67,144 | 2022-09-12 | 13 Months | 26% | - | -
[10 empty] | 77 | Kondhavi | D.K. Construction ( Dinesh Manohar Khaire) | 1,99,71,674 | 2022-01-12 | 13 Months | 25% | - | -
[10 empty] | 78 | Talekhar | Janhavi Vikas Naik | 76,88,486 | 2022-09-12 | 10 Months | 25% | - | -
[10 empty] | 79 | Mohili Khalsa | D.K. Construction ( Dinesh Manohar Khaire) | 22,23,926 | 2022-10-08 | 8 Months | 25% | - | -
[10 empty] | 80 | Talavali | Madhura Emterprises ( Prany Patil ) | 25,63,415 | 2022-07-10 | 7 Months | 16% | - | -
[10 empty] | 81 | Hetavne | Shailesh Sambhaji Patil | 68,30,523 | 30-04-2021 | 10 Months | 15% | - | -
[10 empty] | 82 | Belwade Bu. & 04 Wadya | D.K. Construction ( Dinesh Manohar Khaire) | 73,49,114 | 25-11-2021 | 10 Months | 15% | - | -
[10 empty] | 83 | Adharne | D.K. Construction ( Dinesh Manohar Khaire) | 1,34,59,855 | 2022-09-12 | 13 Months | 13% | - | -
[10 empty] | 84 | Karoti | D.K. Construction ( Dinesh Manohar Khaire) | 8,12,798 | 2021-03-08 | 10 Months | 12% | - | -
[10 empty] | 85 | Kasu | Rane Construction & Devlapers ( Sanket Rane ) | 14,07,485 | 2022-09-11 | 13 Months | 10% | - | -
[10 empty] | 86 | Mohili Enam | G.D. Mohite Construction ( Ganpat Dashrath Mohite ) | 22,23,926 | 2022-08-07 | 8 Months | 10% | - | -
[10 empty] | 87 | Jirne | D.K. Construction ( Dinesh Manohar Khaire) | 1,95,46,818 | 27-09-2022 | 13 Months | 0.13% | - | -
[10 empty] | 88 | Belwade Khurd | D.K. Construction ( Dinesh Manohar Khaire) | 32,10,234 | 27-09-2022 | 7 Months | 0.07% | - | -
[10 empty] | 89 | Mhaiswadi | Aakash Tulshidas Kamble | 71,80,203 | 13-12-2022 | 10 Months | 0.03% | - | -
[10 empty] | 90 | Virani | Rakesh Krushana Patil | 1,16,97,932 | 2022-03-11 | 13 Months | 0.02% | - | -
[10 empty] | 91 | Usar | D.K. Construction ( Dinesh Manohar Khaire) | 61,58,751 | 28-09-2022 | 13 Months | 0.01% | - | -
[10 empty] | 92 | Salinde | S. S. Construction ( Sunil Krushna Mokal ) | 1,01,47,546 | 2022-07-12 | 13 Months | 0.01% | - | -
Poladpur Taluka
[10 empty] | 93 | Charai | Shri. Sai Construction (Abhijit Vithoba Mhatre ) | 63,46,212 | 2022-01-12 | 9 Months | 27% | - | -
[10 empty] | 94 | Chandale | Karan Kishor Patil | 30,02,765 | 30-09-2022 | 10 Months | 14.12% | - | -
[10 empty] | 95 | Keonale | Sahyadri Construction ( Gani Babasaheb Dhamankar ) | 95,50,433 | 13-10-2022 | 13 Months | 12.43% | - | -
[10 empty] | 96 | Naneghol | Aadesha Anant Tudilkar | 26,69,492 | 13-10-2022 | 7 Months | 9.28% | - | -
[10 empty] | 97 | Devapur | Nilesh Construction ( Nilesh Tulshiram Mhatre ) | 43,42,365 | 30-09-2022 | 13 Months | 1.52% | - | -
Roha Taluka
[10 empty] | 98 | Gaichol | Shri. Enterprises ( Manoj Khadekar ) | 29,27,741 | 27-09-2022 | 10 Months | 71% | 69.09% | 2022891
[10 empty] | 99 | Khargaon Gaulwadi | Mansi Enterprises ( Haresh Naynekar) | 32,93,635 | 2022-03-10 | 10 Months | 63% | 60.29% | 1985720
[10 empty] | 100 | Wali | Shri. Enterprises ( Manoj Khadekar ) | 56,77,344 | 2022-06-10 | 9 Months | 44.7% | - | -
[10 empty] | 101 | Aadiwasiwadi Kolad | Sagar Ravindra Mohite | 45,95,953 | 25-11-2022 | 7 Months | 38.45% | - | -
[10 empty] | 102 | Madhali Kh | Vishal Rajendra Mande | 40,18,488 | 2022-06-10 | 7 Months | 37.22% | - | -
[10 empty] | 103 | Dhamansai | Shri. Enterprises ( Manoj Khadekar ) | 1,74,58,535 | 30-09-2022 | 13 Months | 31.28% | - | -
[10 empty] | 104 | Barshet | Mansi Enterprises ( Haresh Naynekar) | 34,00,531 | 14-11-2022 | 7 Months | 29% | - | -
[10 empty] | 105 | Pugaon | Suprabhat Infrazone Pvt.Ltd. ( Aashish Suresh Gurav ) | 1,38,81,156 | 2022-12-12 | 13 Months | 28% | - | -
[10 empty] | 106 | Medha | Shri. Enterprises ( Manoj Khadekar ) | 40,19,949 | 26-09-2022 | 7 Months | 27.4% | - | -
[10 empty] | 107 | Pale Tarfe Ashtami | Dhanesh Padmakar Tambdkar | 43,13,091 | 2022-09-12 | 7 Months | 27% | - | -
[10 empty] | 108 | Muthawali Khu. | Gundekar Mukund Madhukar | 44,02,386 | 2022-09-11 | 7 Months | 25% | - | -
[10 empty] | 109 | Ghera Surgad | Gundekar Mukund Madhukar | 44,69,892 | 2022-09-11 | 7 Months | 23.29% | 21.9% | 978967
[10 empty] | 110 | Landhar | Shivsai Construction ( Trupti Jitendra Pawar) | 64,88,194 | 2022-07-10 | 9 Months | 21.62% | - | -
[10 empty] | 111 | Songaon | D.K. Construction ( Dinesh Manohar Khaire) | 68,68,945 | 30-09-2022 | 13 Months | 20.19% | - | -
[10 empty] | 112 | Khabere | Vishal Rajendra Mande | 30,02,637 | 19-10-2022 | 13 Months | 20% | - | -
[10 empty] | 113 | Wazaroli | Shri. Enterprises ( Manoj Khadekar ) | 28,95,865 | 21-10-2022 | 7 Months | 18.59% | - | -
[10 empty] | 114 | Wandoli | Rohan Rajesh Temakar | 75,81,464 | 13-10-2022 | 13 Months | 18.45% | - | -
[10 empty] | 115 | Khaire Kh | Aakash Tulshidas Kamble | 34,82,709 | 2022-07-10 | 7 Months | 17.13% | - | -
[10 empty] | 116 | Mukte | Mansi Enterprises ( Haresh Naynekar) | 52,99,683 | 27-09-2022 | 10 Months | 13.1% | - | -
[10 empty] | 117 | Sarsoli | Vishal Rajendra Mande | 44,79,297 | 2022-01-11 | 7 Months | 13% | - | -
[10 empty] | 118 | Talawali Tarfe Ghosale | Dhanesh Padmakar Tambdkar | 41,75,199 | 19-10-2022 | 13 Months | 10% | - | -
[10 empty] | 119 | Dankanhe | Shri. Enterprises ( Manoj Khadekar ) | 8,66,775 | 30-09-2022 | 9 Months | 7.4% | - | -
[10 empty] | 120 | Sangade | Shivsai Construction ( Trupti Jitendra Pawar) | 38,20,277 | 30-09-2022 | 10 Months | 5.73% | - | -
[10 empty] | 121 | Sambhe | Vishal Rajendra Mande | 95,05,419 | 2022-06-10 | 10 Months | 3.12% | - | -
[10 empty] | 122 | Nivi | Nikhil Construction ( Shantaram Hiraji Borkar) | 84,87,872 | 2022-07-10 | 9 Months | 2% | - | -
[10 empty] | 123 | Tamhanshet | Mansi Enterprises ( Haresh Naynekar) | 77,13,065 | 21-11-2022 | 9 Months | 0.58% | - | -
[10 empty] | 124 | Khairale | Shri. Enterprises ( Manoj Khadekar ) | 92,19,044 | 1907-01-06 | 9 Months | 0.19% | - | -
[10 empty] | 125 | Mahsadi | Gajrai Construction ( Dipak Mhanure | 26,10,361 | 21-11-2022 | 7 Months | 0.16% | - | -
[10 empty] | 126 | Rotha Khu. | Devidas Sambhaji Chavhan | 74,42,488 | 25-11-2022 | 9 Months | 0.08% | - | -
[10 empty] | 127 | Dhankanhe Adiwasiwadi | Vishal Rajendra Mande | 31,05,994 | 2022-10-10 | 7 Months | 0.05% | - | -
[10 empty] | 128 | Kharkhardi | Hitesh Prbhakar Thakur | 42,70,735 | 2022-03-10 | 10 Months | 0.01% | - | -
[10 empty] | 129 | Kadsure | Vivek Rohidas Patil | 1,53,73,412 | 21-11-2022 | 13 Months | 0.01% | - | -
[10 empty] | 130 | Tamsoli | Vishal Rajendra Mande | 92,00,749 | 2022-01-12 | 9 Months | 0.01% | - | -
Shriwardhan Taluka
[10 empty] | 131 | Saygaon | Jayvant Shantaram Aavere | 1,02,99,390 | 14-10-2022 | 13 Months | 55.13% | 55.22% | 5686864
[10 empty] | 132 | Kudki | Arvind Dhondu Pashilkar | 79,83,674 | 25-10-2022 | 10 Months | 28% | - | -
[10 empty] | 133 | Sakhrone | Jayvant Shantaram Aavere | 74,23,007 | 25-10-2022 | 10 Months | 25% | - | -
[10 empty] | 134 | Karle | Dtta Shivaji Pawar | 1,04,07,837 | 14-11-2022 | 13 Months | 25% | - | -
[10 empty] | 135 | Dandguri | Sagar Ravindra Mohite | 1,10,99,301 | 27-09-2022 | 13 Months | 0.28% | - | -
[10 empty] | 136 | Bapwan Kadne | Prasad Construction ( Prasad Prakash Ketkar ) | 56,70,559 | 2022-01-11 | 12 Months | 0.09% | - | -
Sudhagad Taluka
[10 empty] | 137 | Mulshi | G.D. Mohite Construction ( Ganpat Dashrath Mohite ) | 24,05,197 | 23-12-2021 | 8 Months | 75% | - | -
[10 empty] | 138 | Bhajre Navin Vasahat | G.D. Mohite Construction ( Ganpat Dashrath Mohite ) | 23,56,065 | 23-12-2021 | 9 Months | 75% | - | -
[10 empty] | 139 | Bhilpada Khuravle | G.D. Mohite Construction ( Ganpat Dashrath Mohite ) | 54,54,352 | 20-01-2022 | 9 Months | 75% | - | -
[10 empty] | 140 | Dhokshet | G.D. Mohite Construction ( Ganpat Dashrath Mohite ) | 73,56,525 | 2022-10-02 | 9 Months | 75% | - | -
[10 empty] | 141 | Khandpoli | G.D. Mohite Construction ( Ganpat Dashrath Mohite ) | 71,00,781 | 31-03-2022 | 9 Months | 50% | - | -
[10 empty] | 142 | Navghar | G.D. Mohite Construction ( Ganpat Dashrath Mohite ) | 60,23,618 | 29-04-2022 | 8 Months | 50% | - | -
[10 empty] | 143 | Kavele | G.D. Mohite Construction ( Ganpat Dashrath Mohite ) | 98,98,438 | 2022-02-09 | 10 Months | 45% | - | -
[10 empty] | 144 | Bhalgul | G.D. Mohite Construction ( Ganpat Dashrath Mohite ) | 5,88,525 | 2022-08-09 | 8 Months | 38% | - | -
[10 empty] | 145 | Mangaon Khu. | G.D. Mohite Construction ( Ganpat Dashrath Mohite ) | 34,12,065 | 13-09-2022 | 8 Months | 38% | - | -
[10 empty] | 146 | Amnori | G.D. Mohite Construction ( Ganpat Dashrath Mohite ) | 62,45,775 | 2022-08-09 | 10 Months | 37% | - | -
[10 empty] | 147 | Falyan | G.D. Mohite Construction ( Ganpat Dashrath Mohite ) | 70,78,327 | 2022-08-09 | 11 Months | 36% | - | -
[10 empty] | 148 | Usale | G.D. Mohite Construction ( Ganpat Dashrath Mohite ) | 37,16,427 | 2022-08-09 | 8 Months | 36% | - | -
[10 empty] | 149 | Majre Jambhulpada | G.D. Mohite Construction ( Ganpat Dashrath Mohite ) | 77,89,477 | 2022-02-09 | 10 Months | 35% | - | -
[10 empty] | 150 | Pilosari | G.D. Mohite Construction ( Ganpat Dashrath Mohite ) | 63,00,278 | 20-01-2021 | 10 Months | 34% | - | -
[10 empty] | 151 | Pawsalwadi | G.D. Mohite Construction ( Ganpat Dashrath Mohite ) | 64,13,803 | 2022-02-09 | 9 Months | 33% | - | -
[10 empty] | 152 | Tivre | G.D. Mohite Construction ( Ganpat Dashrath Mohite ) | 56,21,938 | 2022-02-09 | 8 Months | 30% | - | -
[10 empty] | 153 | Harneri | G.D. Mohite Construction ( Ganpat Dashrath Mohite ) | 37,44,328 | 2022-02-09 | 8 Months | 30% | - | -
[10 empty] | 154 | Sidheshwar Budruk | G.D. Mohite Construction ( Ganpat Dashrath Mohite ) | 58,92,533 | 19-10-2022 | 7 Months | 27% | - | -
[10 empty] | 155 | Kubharghar | G.D. Mohite Construction ( Ganpat Dashrath Mohite ) | 42,43,332 | 19-10-2022 | 7 Months | 26% | - | -
[10 empty] | 156 | Pui | G.D. Mohite Construction ( Ganpat Dashrath Mohite ) | 30,51,808 | 25-10-2022 | 7 Months | 26% | - | -
[10 empty] | 157 | Pedhali | G.D. Mohite Construction ( Ganpat Dashrath Mohite ) | 97,66,228 | 30-06-2022 | 10 Months | 26% | - | -
[10 empty] | 158 | Parli Padghvli | G.D. Mohite Construction ( Ganpat Dashrath Mohite ) | 3,45,00,802 | 2022-08-07 | 17 Months | 26% | - | -
[10 empty] | 159 | Kansal | G.D. Mohite Construction ( Ganpat Dashrath Mohite ) | 1,05,58,315 | 13-12-2022 | 13 Months | 25% | - | -
[10 empty] | 160 | Ghotavde | G.D. Mohite Construction ( Ganpat Dashrath Mohite ) | 13,80,345 | 16-06-2022 | 13 Months | 20% | - | -
[10 empty] | 161 | Fanswadi (Grampachayt Gomashi) | Madhura Emterprises ( Prany Patil ) | 41,46,717 | 30-04-2021 | 8 Months | 15% | - | -
[10 empty] | 162 | Tadgaon | G.D. Mohite Construction ( Ganpat Dashrath Mohite ) | 1,56,17,381 | 2022-09-12 | 13 Months | 12% | - | -
[10 empty] | 163 | Hedawali | G.D. Mohite Construction ( Ganpat Dashrath Mohite ) | 54,99,238 | 26-09-2022 | 9 Months | 11% | - | -
[10 empty] | 164 | Vaghoshi | G.D. Mohite Construction ( Ganpat Dashrath Mohite ) | 82,20,941 | 2022-09-11 | 9 Months | 10% | - | -
[10 empty] | 165 | Pimpaloli | Madhura Emterprises ( Prany Patil ) | 38,16,411 | 30-04-2021 | 8 Months | 10% | - | -
[10 empty] | 166 | Nere | G.D. Mohite Construction ( Ganpat Dashrath Mohite ) | 61,41,419 | 29-09-2022 | 9 Months | 3% | - | -
[10 empty] | 167 | Kharchunde | G.D. Mohite Construction ( Ganpat Dashrath Mohite ) | 75,51,499 | 27-09-2022 | 10 Months | 0.95% | - | -
[10 empty] | 168 | Nenavali | Shreys Sudhakar Mhatre | 55,57,287 | 26-09-2022 | 7 Months | 0.55% | - | -
[10 empty] | 169 | Varhad Jambhulpada | G.D. Mohite Construction ( Ganpat Dashrath Mohite ) | 1,98,53,456 | 2022-07-10 | 13 Months | 0.36% | - | -
[10 empty] | 170 | Chive | G.D. Mohite Construction ( Ganpat Dashrath Mohite ) | 42,68,442 | 13-12-2022 | 7 Months | 0.21% | - | -
[10 empty] | 171 | Nadsur | D.K. Construction ( Dinesh Manohar Khaire) | 1,94,09,156 | 13-10-2022 | 13 Months | 0.09% | - | -
[10 empty] | 172 | Kasarwadi (Asare) | G.D. Mohite Construction ( Ganpat Dashrath Mohite ) | 74,83,592 | 27-09-2022 | 9 Months | 0.07% | - | -
[10 empty] | 173 | Balap | K. T. Construction ( Sagar Yashwant Patil) | 81,60,313 | 26-09-2022 | 9 Months | 0.05% | - | -
[10 empty] | 174 | Nandgaon | Rohan Rajesh Temakar | 82,32,697 | 30-09-2022 | 7 Months | 0.04% | - | -
[10 empty] | 175 | Mangaon Budruk | G.D. Mohite Construction ( Ganpat Dashrath Mohite ) | 23,08,403 | 2022-01-11 | 7 Months | 0.04% | - | -
[10 empty] | 176 | Koshimble | Shreys Sudhakar Mhatre | 40,25,318 | 26-09-2022 | 7 Months | 0.03% | - | -
[10 empty] | 177 | Vasunde | G.D. Mohite Construction ( Ganpat Dashrath Mohite ) | 69,38,134 | 13-10-2022 | 9 Months | 0.02% | - | -
[10 empty] | 178 | Wave Tarfe Haveli | G.D. Mohite Construction ( Ganpat Dashrath Mohite ) | 81,93,095 | 13-10-2022 | 9 Months | 0.02% | - | -
[10 empty] | 179 | Rabgaon | G.D. Mohite Construction ( Ganpat Dashrath Mohite ) | 1,92,70,397 | 2022-01-11 | 13 Months | 0.02% | - | -
[10 empty] | 180 | Mahagaon | G.D. Mohite Construction ( Ganpat Dashrath Mohite ) | 1,97,81,429 | 2022-10-10 | 13 Months | 0.01% | - | -
[10 empty] | 181 | Dighewadi | K. T. Construction ( Sagar Yashwant Patil) | 67,07,564 | 21-10-2022 | 9 Months | 0.01% | - | -
Tala Taluka
[10 empty] | 182 | Borghar Haweli | Aakash Tulshidas Kamble | 85,48,925 | 2022-03-11 | 9 Months | 32% | 27.51% | 2352011
[10 empty] | 183 | Borichamal | Karan Kishor Patil | 40,26,653 | 19-10-2022 | 7 Months | 28% | - | -
[10 empty] | 184 | Wanjloshi | Rohan Ravindra Mandvkar | 45,96,422 | 2022-03-11 | 7 Months | 25% | - | -
[10 empty] | 185 | Rahatad | Shri. Enterprises ( Manoj Khadekar ) | 84,18,953 | 14-10-2022 | 9 Months | 11% | - | -
[10 empty] | 186 | Belghar | Rohan Ravindra Mandvkar | 30,84,383 | 29-11-2022 | 7 Months | 3.7% | - | -
[10 empty] | 187 | Kude | Jayesh Dattatry Kalekar | 1,02,62,651 | 2022-09-11 | 13 Months | 2.5% | - | -
[10 empty] | 188 | Salshet | Rohan Ravindra Mandvkar | 31,87,953 | 21-10-2022 | 7 Months | 1.72% | - | -
[10 empty] | 189 | Barpe | Rohan Ravindra Mandvkar | 40,35,339 | 19-10-2022 | 7 Months | 0.45% | - | -