## Slide 1
NABARD CONSULTANCY SERVICES
PROGRESS REPORT
DISTRICT: CHANDRAPUR
JAL JEEVAN MISSION
NAGPUR REGION
MARCH 2023

## Slide 2: District Work Status
Taluka | Category | No. of Schemes | Work Order Issued | Work In Progress | Work Not Started
Bramhapuri | Retro | 37 | 35 | 25 | 10
 | New | 29 | 29 | 26 | 3
Chimur | Retro | 97 | 93 | 53 | 40
 | New | 20 | 19 | 9 | 10
Mul | Retro | 18 | 17 | 5 | 12
 | New | 10 | 9 | 4 | 5
Nagbid | Retro | 43 | 42 | 28 | 14
 | New | 19 | 18 | 6 | 12
Sawali | Retro | 21 | 21 | 13 | 8
 | New | 20 | 18 | 14 | 4
Sindewahi | Retro | 33 | 30 | 20 | 10
 | New | 21 | 21 | 16 | 5
Warora | Retro | 76 | 72 | 28 | 44
 | New | 7 | 6 | 1 | 5
Total | Retro | 325 | 310 | 172 | 138
 | New | 126 | 120 | 76 | 44
Grand Total |  | 451 | 430 | 248 | 182

## Slide 3: Executive Summary Work in Progress Schemes
Taluka | Category | Total No. of Schemes | No. of Schemes based on Physical Progress % |  |  |  | 
 |  |  | < 25% | 25 < 50% | 50 < 75% | 75 < 100% | Commissioned
Bramhapuri | Retro | 25 | 23 | 1 | 1 | 0 | 0
 | New | 26 | 21 | 4 | 1 | 0 | 0
Chimur | Retro | 53 | 48 | 3 | 1 | 1 | 0
 | New | 9 | 8 | 1 | 0 | 0 | 0
Mul | Retro | 5 | 4 | 1 | 0 | 0 | 0
 | New | 4 | 4 | 0 | 0 | 0 | 0
Nagbid | Retro | 28 | 24 | 3 | 1 | 0 | 0
 | New | 6 | 6 | 0 | 0 | 0 | 0
Sawali | Retro | 13 | 12 | 1 | 0 | 0 | 0
 | New | 14 | 13 | 1 | 0 | 0 | 0
Sindewahi | Retro | 20 | 15 | 5 | 0 | 0 | 0
 | New | 16 | 16 | 0 | 0 | 0 | 0
Warora | Retro | 28 | 17 | 8 | 2 | 1 | 0
 | New | 1 | 1 | 0 | 0 | 0 | 0
Total | Retro | 172 | 143 | 22 | 5 | 2 | 0
 | New | 76 | 69 | 6 | 1 | 0 | 0
Grand Total |  | 248 | 212 | 28 | 6 | 2 | 0

## Slide 4: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
Bramhapuri Taluka |  |  |  |  |  |  |  | 
1 | Chandgaon | Shri. Svapnil Vasantrao Meshram | 9,19,338 | 27-09-2022 | 12 Months | 62.42% | - | -
2 | Adyaljani | Me. Kamlesh Buillding Materiyal | 65,82,638 | 21-01-2023 | 16 Months | 25.56% | - | -
3 | Jugnala | Me. Arohi Solution | 1,21,38,379 | 30-01-2023 | 16 Months | 23.51% | - | -
4 | Zilbodi | Roshan Bhagwan Navghare | 19,49,079 | 09-12-2022 | 12 Months | 21.75% | - | -
5 | Mui | Nikhil Popatrao Buddhe | 43,87,441 | 21-01-2023 | 14 Months | 15.06% | - | -
6 | Maldongri | Shrikant Gopalji Jayaswal | 1,02,07,443 | 17-01-2023 | 15 Months | 14.99% | 10.35% | 10.56
7 | Belpatli | Shri Roshan Bhagvan Navghde | 26,65,653 | 01-08-2022 | 14 Months | 13.89% | - | -
8 | Sondri | Shri. Akashy Khemraj Tidke | 63,79,706 | 03-10-2022 | 20 Months | 13.27% | - | -
9 | Udapur | Me. Tirupati Construction | 1,19,17,850 | 27-01-2023 | 16 Months | 12.59% | - | -
10 | Khandala | Warhi Construction | 87,22,023 | 30-01-2023 | 16 Months | 12.38% | - | -
11 | Chaugan | Akshay Khemraj Tikde | 1,45,80,237 | 13-12-2022 | 16 Months | 7.79% | - | -
12 | Nanhori | Shailesh Ravishankar Jaiswal | 1,67,41,590 | 19-12-2023 | 20 Months | 6.87% | - | -
13 | Mudaza | Shri Avinash Murlidhar Maske | 1,29,54,066 | 07-11-2022 | 18 Months | 6.18% | 5.61% | 7.27

## Slide 5: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
14 | Kudesawli | Avinash Maske | 57,54,225 | 07-11-2022 | 17 Months | 6.08% | - | -
15 | Baradkinhi | Shri Avinas Murlidhar Maske | 1,09,96,837 | 25-01-2023 | 16 Months | 6.00% | 4.50% | 4.95
16 | Hardoli | Shri. Sagar Maroti Bagmare | 82,97,644 | 31-01-2023 | 16 Months | 5.46% | - | -
17 | Marar Mendha | Me. Arohi Solution | 84,02,018 | 27-01-2023 | 16 Months | 4.51% | - | -
18 | Waygaon | Shri. Sandeep Anandrao Tupat | 47,73,652 | 31-01-2023 | 14 Months | 3.57% | - | -
19 | Ranmochan | Nikhil Popatrao Buddhe | 55,80,423 | 17-01-2023 | 16 Months | 2.67% | - | -
20 | Chorti | Shri. Amol Mahadev Sukare | 65,58,719 | 31-01-2023 | 16 Months | 2.55% | - | -
21 | Nandgaon Jani | Pritam Gyaneshwar Asutkar | 49,73,294 | 13-01-2023 | 16 Months | 1.74% | - | -
22 | Dighori | Shri Vahari Construction | 1,25,86,619 | 21-01-2023 | 16 Months | 1.08% | - | -
23 | Halda | Shrikant Gopalji Jaiswal | 1,97,50,451 | 17-01-2023 | 16 Months | 0.91% | - | -
24 | Chandali | Avinash Maske | 32,14,380 | 22-06-2022 | 14 Months | 0.71% | - | -
25 | Gangalwadi | Me. Tirupati Construction | 1,42,88,760 | 31-01-2023 | 16 Months | 0.53% | - | -
Chimur Taluka |  |  |  |  |  |  |  | 
26 | Paradpar | Shri Shrikant Gopalji Jayasval | 17,85,433 | 11-11-2022 | 14 Months | 94.81% | - | -

## Slide 6: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
27 | Navegaon Peth | Shri. Shrikant Gopal Jayasval | 60,06,920 | 11-11-2022 | 18 Months | 54.45% | - | -
28 | Wadhona | Shri Swapnil Vasantrao Meshram | 15,65,903 | 28-09-2022 | 12 Months | 47.68% | 43.71% | 6.84
29 | Satara | Shri Gajanan Udapure | 29,95,872 | 11-01-2022 | 14 Months | 46.90% | - | -
30 | Dabka Heti | Shri. Pragat Namdev Sahare | 41,35,346 | 28-09-2022 | 16 Months | 39.36% | 35.75% | 14.78
31 | Sawarla | Shri Sumit Jagdish Govardhar | 52,43,585 | 31-10-2022 | 16 Months | 24.06% | 15.94% | 8.36
32 | Doma | Shri Ajaysingh Dhunna | 1,04,42,510 | 07-11-2022 | 18 Months | 23.54% | 17.76% | 18.55
33 | Mangaigaon | Shri Shrikant Gopal Jayasval | 98,65,015 | 11-11-2022 | 18 Months | 19.52% | - | -
34 | Dongarla | Sumit Jagdish Govardhan | 33,82,623 | 09-12-2022 | 12 Months | 18.48% | 12.25% | 4.14
35 | Harni | Shrikant Jayaswal | 25,04,998 | 11-11-2022 | 12 Months | 17.37% | 12.04% | 3.02
36 | Piti Chuha | Prakash Construction Company | 11,08,203 | 01-07-2022 | 14 Months | 16.53% | - | -
37 | Hiwra | Shri. Ajaysingh Dhunna | 59,76,350 | 30-01-2023 | 16 Months | 16.14% | 12.69% | 7.58
38 | Jamgaon | Dinesh Dhukre | 24,00,964 | 30-12-2022 | 18 Months | 15.83% | - | -
39 | Wadala (Shivra) | Kunal Sunil Jumle | 9,23,855 | 09-12-2022 | 10 Months | 15.26% | - | -
40 | Kolari | Shri Shrikant Gopal Jayasval | 46,97,950 | 11-11-2022 | 18 Months | 14.09% | - | -

## Slide 7: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
41 | Sonegaon (Ga) | Shri. Shrikant Gopal Jayasval | 59,19,615 | 27-01-2023 | 16 Months | 13.44% | - | -
42 | Jamani | Milind Raut | 34,97,955 | 31-10-2022 | 14 Months | 12.73% | 9.56% | 3.34
43 | Motegaon | Shri Shrikant Gopal Jayasval | 89,62,125 | 11-11-2022 | 18 Months | 11.15% | - | -
44 | Nimdhela | Shri. Gajanan Somaji Udapure | 50,29,330 | 31-01-2023 | 16 Months | 10.86% | - | -
45 | Baradghat | Shubham Gajanan Udapure | 36,43,206 | 31-01-2023 | 14 Months | 10.05% | - | -
46 | Yerkheda | Shri. Shrikant Gopal Jayasval | 31,74,786 | 11-11-2022 | 18 Months | 10.01% | - | -
47 | Bramhangaon | Shrikrupa Building Material Suppliers | 33,85,281 | 31-10-2022 | 14 Months | 9.24% | - | -
48 | Shivra | Shri. Pravin Borkar | 49,72,516 | 24-11-2022 | 18 Months | 9.02% | - | -
49 | Kawthala | Shri Parvin Haridas Borkar | 29,44,247 | 17-11-2022 | 12 Months | 8.40% | - | -
50 | Talodi | Shri Anil Gore | 1,04,28,573 | 03-11-2022 | 18 Months | 7.86% | - | -
51 | Murpar | Kalyani Sakharkar | 92,84,503 | 09-12-2022 | 16 Months | 7.47% | - | -
52 | Amarpuri | Shri Vikram Godam | 23,96,597 | 07-11-2022 | 12 Months | 6.13% | - | -
53 | Ambeneri | Shri. Gajanan Somaji Udapure | 58,12,784 | 31-10-2022 | 18 Months | 5.68% | - | -
54 | Majra Begde | Shri. Nitesh Mohan Samarth | 45,04,732 | 31-01-2023 | 14 Months | 5.61% | - | -

## Slide 8: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
55 | Kitadi Makta | Shri Pravin Haridas | 23,53,729 | 17-11-2022 | 12 Months | 5.18% | - | -
56 | Keslabodi | Milind Raut | 86,12,223 | 17-01-2023 | 16 Months | 4.76% | - | -
57 | Piparda | Shri. Shrikant Gopal Jayasval | 77,50,867 | 11-11-2022 | 18 Months | 4.56% | - | -
58 | Nandara | Shri. Gajanan Somaji Udapure | 61,34,912 | 28-09-2022 | 17 Months | 3.98% | - | -
59 | Chak Jambhulvihira | Ku. Pooja Panjabrao Shinde | 42,21,368 | 01-11-2022 | 16 Months | 3.30% | - | -
60 | Karbada Chaiti | Ku. Kalyani Madan Sakharkar | 17,93,536 | 27-01-2023 | 16 Months | 3.17% | - | -
61 | Puyardand | Dinesh Dhukre | 46,61,664 | 05-12-2022 | 14 Months | 2.59% | - | -
62 | Tekepar | Shri. Shrikant Gopal Jayasval | 69,97,287 | 11-11-2022 | 18 Months | 2.09% | - | -
63 | Sawargaon | Shri. Shrikant Jayaswal | 1,14,13,374 | 11-11-2022 | 14 Months | 1.88% | - | -
64 | Kajalsar | Shri. Shrikant Gopal Jayasval | 1,70,98,250 | 31-01-2023 | 16 Months | 1.65% | - | -
65 | Kewada | Shri. Shrikant Gopal Jayasval | 1,55,50,286 | 22-11-2022 | 20 Months | 1.39% | - | -
66 | Kawadasi (Deshmane) | Kalyani Madan Sakharkar | 1,11,95,478 | 09-12-2022 | 20 Months | 1.35% | - | -
67 | Mangrud & Zari | Shri. Mohsin Khan Nasib Khan | 17,97,332 | 27-09-2022 | 9 Months | 1.21% | - | -
68 | Pachgaon | Ku. Pragya Dayaram Ramteke | 21,85,655 | 07-11-2022 | 14 Months | 1.03% | - | -

## Slide 9: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
69 | Khandala | Shri Mayur Bapurao Gajbhe | 31,02,375 | 22-11-2022 | 14 Months | 1.03% | - | -
70 | Titwa | Next Inovation | 33,21,221 | 09-12-2022 | 12 Months | 0.69% | - | -
71 | Lohara | Shri. Shrikant Gopal Jayasval | 1,09,88,121 | 22-11-2022 | 20 Months | 0.69% | - | -
72 | Borgaon Butti | Shri. Aniket Sanjay Khanke | 44,83,859 | 31-01-2023 | 14 Months | 0.57% | - | -
73 | Navegaon (Ramdeghi) | Nitesh Mohan Samarth | 42,16,993 | 08-12-2022 | 14 Months | 0.55% | - | -
74 | Masal Tukum | Shri. Gajanan Somaji Udapure | 59,69,065 | 28-09-2022 | 17 Months | 0.39% | - | -
75 | Saradpar | T. K. Construction | 64,89,040 | 31-10-2022 | 20 Months | 0.36% | - | -
76 | Bothali | Shrikrupa Building Material Suppliers | 83,07,006 | 21-01-2023 | 16 Months | 0.28% | - | -
77 | Navtala | Shri Pravin Haridas | 91,34,550 | 21-10-2022 | 14 Months | 0.26% | - | -
78 | Jambulghat | Shri. Shrikant Gopal Jayasval | 3,19,04,627 | 27-01-2023 | 16 Months | 0.08% | - | -
Mul Taluka |  |  |  |  |  |  |  | 
79 | Chandpur | Shri M.K. Veragade | 1,52,70,580 | 25-01-2023 | 16 Months | 26.49% | 22.54% | 34.42
80 | Khalwaspeth | Shri Kishor Parbhudas Ghadse | 72,04,310 | 21-01-2023 | 16 Months | 14.86% | 11.49% | 8.28
81 | Uthalpeth | Shri. Kishor Parbhudas Ghadse | 68,04,868 | 30-01-2023 | 16 Months | 14.15% | 8.72% | 5.93

## Slide 10: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
82 | Naleshwar | Shri. Ramendra Rapeti Bala | 77,23,692 | 27-01-2023 | 16 Months | 4.58% | - | -
83 | Junasurla | Maa. Durga Construction Murkhada | 1,58,66,805 | 21-01-2023 | 16 Months | 0.39% | - | -
 | Nagbid Taluka |  |  |  |  |  |  | 
84 | Kachepar | Prakash Construction Company | 12,16,886 | 01-08-2022 | 12 Months | 70.77% | 60.61% | 7.38
85 | Mohadi Mokasa | Shivam Liladhar Hemne | 87,96,604 | 19-12-2022 | 18 Months | 46.67% | 38.41% | 33.79
86 | Wasala Mendha & Makta | Ku. Manali Arun Tangdaplavar | 43,27,336 | 27-01-2023 | 20 Months | 28.28% | - | -
87 | Irvha | Tushar Sukru Hatwar | 24,64,333 | 11-01-2022 | 12 Months | 28.10% | - | -
88 | Navegaon Pandav | Shri. Arvind Vinayak Mahajan | 46,19,419 | 01-11-2022 | 18 Months | 21.16% | 12.81% | 5.92
89 | Balapur Kh | Sarang Manapure | 42,79,983 | 27-01-2023 | 16 Months | 15.22% | - | -
90 | Kanpa | Ajaysingh Dhunna | 86,36,365 | 24-11-2022 | 18 Months | 9.40% | 7.68% | 6.63
91 | Kordha | Shri. Ajay Chafle | 58,12,599 | 31-01-2023 | 16 Months | 9.01% | - | -
92 | Tekri | Shri. Ajay Chafle | 59,78,105 | 31-01-2023 | 16 Months | 8.85% | - | -
93 | Kothulna | Ashish Namdev Katekhaye | 30,44,497 | 11-01-2022 | 12 Months | 8.63% | - | -
94 | Korambi | Kamlesh Building Material Suppliers | 24,74,380 | 11-11-2022 | 12 Months | 8.33% | - | -

## Slide 11: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
95 | Telimendha | Shri Ashish Namdev Kathekhaye | 37,20,205 | 01-11-2022 | 18 Months | 7.36% | - | -
96 | Mangali Arab | Shri. Ajay Chafle | 70,37,430 | 31-01-2023 | 16 Months | 6.40% | - | -
97 | Nanded | Shri Shrikant G Jaiswal | 1,15,85,240 | 16-01-2023 | 16 Months | 6.01% | - | -
98 | Chargaon Chak & Chargaon Manpur | Shri Rohit Dinesh Dupare | 32,81,234 | 07-11-2022 | 14 Months | 5.49% | - | -
99 | Panjarepar | Tushar Sukru Hatwar | 39,86,826 | 11-01-2022 | 18 Months | 5.14% | - | -
100 | Jivnapur | Shri Sohebudin Khajhi | 30,32,044 | 01-11-2022 | 18 Months | 5.09% | - | -
101 | Chindhichak | Shri. Shrikant Gopal Jayasval | 1,21,02,942 | 27-01-2023 | 20 Months | 3.97% | - | -
102 | Balapur | Ss Dange | 88,68,711 | 23-01-2023\ | 16 Months | 2.86% | - | -
103 | Navegaon(Hundeshwari) | Shri Ajay Nanaji Chafale | 75,44,070 | 25-01-2023 | 16 Months | 2.45% | - | -
104 | Kojbi & Kojbi Chak | Tanvir |  |  | 12 Months | 2.07% | - | -
105 | Chindimal | Shri Ashish Namdev Katkhaye | 20,40,832 | 27-09-2022 | 14 Months | 1.80% | - | -
106 | Walni & Mendha Chargaon | Asit Adhir Mandal | 64,21,881 | 12-05-2022 | 18 Months | 1.57% | - | -
107 | Akapur | Swapnil Vasantrao Meshram | 41,15,655 | 10-03-2022 | 18 Months | 1.07% | - | -
108 | Kitadi Mendha | Me. Tirupati Construction | 39,24,306 | 31-01-2023 | 14 Months | 0.65% | - | -

## Slide 12: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
109 | Vilam | Shri. Ajay Chafle | 63,06,488 | 31-01-2023 | 16 Months | 0.56% | - | -
110 | Khadki (Panodi) | Shri. Ajay Nanaji Chafle | 82,14,812 | 31-01-2023 | 16 Months | 0.43% | - | -
111 | Kanhalgaon & Sonuli | Goroba Bhagirath Shinde | 1,12,21,597 | 26-12-2022 | 20 Months | 0.32% | - | -
Sawali Taluka |  |  |  |  |  |  |  | 
112 | Sakhri | Shri. Deepak P. Gonewar | 4,14,74,656 | 31-01-2023 | 18 Months | 30.71% | 20.49% | 84.98
113 | Vtad Khurd | Pise | 3,74,34,105 | 27-01-2023 | 16 Months | 20.23% | 5.88% | 22.01
114 | Antargaon | Shri. Anil Narayan Gore | 1,67,24,927 | 30-01-2023 | 16 Months | 13.58% | - | -
115 | Pendhari | Shri. Sushil Kavadu Nareddiwar | 96,05,517 | 17-01-2023 | 16 Months | 7.54% | - | -
116 | Sonapur | Me. Pawar Constriuction | 1,15,82,432 | 30-01-2023 | 16 Months | 6.30% | - | -
117 | Upari | Pawar Construction | 96,43,793 | 16-01-2023 | 16 Months | 5.45% | - | -
118 | Nifandra | Shri. Deepak P. Gonewar | 82,92,338 | 31-01-2023 | 16 Months | 5.01% | - | -
119 | Nimgaon | Shri. Kishor Anil Gore | 1,26,49,523 | 21-01-2023 | 16 Months | 3.88% | - | -
120 | Belgaon | Rohankar Treding Company | 75,63,408 | 21-01-2023 | 16 Months | 3.82% | - | -
121 | Kapsi | Me. Pavar Construstion | 1,44,24,052 | 27-01-2023 | 16 Months | 2.79% | - | -

## Slide 13: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
122 | Khedi | Asit Mondal | 87,86,687 | 17-01-2023 | 16 Months | 2.41% | - | -
123 | Donala | Jyoti Construction Company | 51,55,800 | 21-01-2023 | 16 Months | 0.51% | - | -
124 | Chandli Bk | Shri. Ankush Arun Wargantiwar | 95,75,430 | 23-11-2022 | 16 Months | 0.33% | - | -
Sindewahi Taluka |  |  |  |  |  |  |  | 
125 | Palasgaon Jat | Shri. Kishor Anil Gore | 90,12,763 | 07-12-2022 | 16 Months | 40.73% | - | -
126 | Antargaon | Shri. Asit A Mandal | 79,13,351 | 10-11-2022 | 20 Months | 36.39% | - | -
127 | Petgaon | J.V.Construction | 1,40,57,234 | 03-10-2022 | 20 Months | 31.16% | - | -
128 | Kokewada & 3 Villages | Shri. Anil Narayan Gore | 1,54,70,258 | 12-01-2023 | 16 Months | 25.11% | - | -
129 | Kokewada | Anil Gore | 1,54,70,258 | 12-01-2023 | 16 Months | 25.10% | 20.25% | 31.33
130 | Kukadheti | Asit Adhir Mondal | 39,58,550 | 11-03-2022 | 18 Months | 13.20% | - | -
131 | Minghari | Maa Durga Construction | 70,46,856 | 03-10-2022 | 20 Months | 11.99% | - | -
132 | Yergaon | Me. Onkar Construction | 74,13,454 | 31-01-2023 | 16 Months | 11.45% | - | -
133 | Kanhalgaon | Shri. Shrikant Gopal Jayaswal | 61,43,916 | 27-01-2023 | 15 Months | 4.00% | - | -
134 | Mendha Mal | Shri. Shrikant Gopal Jayaswal | 79,40,537 | 27-01-2023 | 16 Months | 3.53% | - | -

## Slide 14: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
135 | Mohadi | Shri. Shrikant Gopalji Jayasval | 1,57,16,281 | 17-01-2023 | 16 Months | 3.04% | - | -
136 | Chitki | Shri Swapnil Vasant Meshram | 18,61,213 | 27-09-2022 | 12 Months | 1.13% | - | -
137 | Sarandi | Shri. Ajikaya Chandrashekhar Mankar | 45,99,063 | 31-01-2023 | 14 Months | 0.65% | - | -
138 | Pawnachak | Shri. Onkar Construction | 55,67,715 | 31-01-2023 | 16 Months | 0.62% | - | -
139 | Tekari | Shri. Shrikant Gopalji Jayasval | 99,76,974 | 17-01-2023 | 16 Months | 0.57% | - | -
140 | Singadzari | Shrikant Gopal Jaiswal | 79,55,013 | 25-01-2023 | 16 Months | 0.45% | - | -
141 | Gadbori | Shri. Shrikant Gopalji Jayasval | 86,62,472 | 17-01-2023 | 16 Months | 0.41% | - | -
142 | Jamsala New And Old | Shri. Shrikant Gopal Jayaswal | 1,00,72,703 | 27-01-2023 | 16 Months | 0.35% | - | -
143 | Ladbori | Shri. Shrikant Gopalji Jayasval | 1,28,71,258 | 17-01-2023 | 16 Months | 0.28% | - | -
144 | Shivni | Shri. Shrikant Gopalji Jayasval | 1,73,24,837 | 17-01-2023 | 16 Months | 0.20% | - | -
Warora Taluka |  |  |  |  |  |  |  | 
145 | Vanli Vangram | Shri. Pritam Dnyaneshwar Aasutkar | 9,13,503 | 21-04-2022 | 9 Months | 86.47% | 71.68% | 6.55
146 | Wadadhamal | Shri. Vaibhav Lahuji Gaorkar | 25,54,047 | 03-10-2022 | 14 Months | 58.23% | - | -
147 | Gaul Bhuj | Shri Nikhil Nanaji Thakre | 45,24,326 | 12-06-2022 | 14 Months | 55.24% | 54.53% | 24.67

## Slide 15: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
148 | Borgaon | Pawan Bopanwar | 21,36,446 | 28-09-2022 | 12 Months | 47.36% | 43.00% | 9.19
149 | Girola | Srg Construction | 52,78,233 | 07-12-2022 | 14 Months | 40.33% | 36.46% | 19.24
150 | Yensa | Shri. Pritam Dnyaneshwar Aasutkar | 27,65,376 | 03-10-2022 | 14 Months | 39.09% | - | -
151 | Mandav Gurhad | Shri Sunil Utam Bhoyar | 35,04,107 | 17-06-2022 | 14 Months | 37.16% | 30.30% | 10.62
152 | Bembal Tukum | Nikhil Thakare | 63,09,629 | 13-01-2023 | 18 Months | 33.62% | 30.58% | 19.29
153 | Jamkhula | Shri. Nikhil Nanaji Thakare | 22,39,525 | 17-06-2022 | 14 Months | 33.21% | - | -
154 | Shegaon Bk | Shri Madhukar K Veragade | 1,57,44,319 | 03-10-2022 | 20 Months | 30.64% | 23.45% | 36.92
155 | Chargaon Kh | Nikhil Thakare | 75,08,216 | 06-12-2022 | 18 Months | 25.80% | 23.31% | 17.50
156 | Waygaon Bhoyer | Shri. Pritam Dnyaneshwar Aasutkar | 15,95,985 | 03-10-2022 | 12 Months | 24.44% | - | -
157 | Arvi | Nikhil Thakare | 28,00,520 | 13-01-2023 | 14 Months | 24.10% | 18.78% | 5.26
158 | Umri | Kisor Anil Gore | 22,58,595 | 26-09-2022 | 14 Months | 23.18% | - | -
159 | Dongargaon | Shri Nikhil Nanaji Thakre | 33,70,686 | 17-06-2022 | 14 Months | 20.01% | 11.95% | 4.03
160 | Jamgaon Kh | Saurabh Vairagade | 25,56,295 | 12-07-2022 | 12 Months | 19.60% | - | -
161 | Khambada | Sumit B More | 69,17,449 | 10-03-2022 | 17 Months | 18.92% | - | -

## Slide 16: Abstract of Schemes – Work in Progress Category – “Retro”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
162 | Salori Yensa | Shri. Pritam Dnyaneshwar Aasutkar | 18,41,892 | 13-09-2022 | 14 Months | 18.89% | 15.90% | 2.93
163 | New Soit | Nikhil Thakre | 39,92,486 | 24-11-2022 | 16 Months | 16.29% | - | -
164 | Fattapur Raiyyatwari | Shri Sunil Utam Bhoyar | 28,18,792 | 17-06-2022 | 14 Months | 15.25% | - | -
165 | Dahegaon | Nikhil Thakare | 53,48,145 | 12-07-2022 | 16 Months | 13.76% | - | -
166 | Kosarsar | Shri. K. M. Dev | 56,59,033 | 27-09-2022 | 14 Months | 12.59% | - | -
167 | Abamakta | Nikhil Thakare | 45,03,237 | 12-01-2023 | 14 Months | 10.92% | - | -
168 | Tembhurda | Ujjwal Construction | 47,55,297 | 31-10-2022 | 18 Months | 6.93% | - | -
169 | Hudki | Atul Prushotam Gore | 38,66,429 | 07-12-2022 | 14 Months | 5.65% | - | -
170 | Waigaon | Shri. Nikhil Nanaji Thakre | 61,06,569 | 27-01-2023 | 16 Months | 4.06% | - | -
171 | Chargaon Bk | Sunil Utam Bhoyar | 65,55,600 | 13-01-2023 | 16 Months | 4.01% | - | -
172 | Bodkha | Shri. Nikhil Nanaji Thakre | 66,69,142 | 31-01-2023 | 15 Months | 1.32% | - | -

## Slide 17: Abstract of Schemes – Work in Progress Category – “New”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
Bramhapuri Taluka |  |  |  |  |  |  |  | 
1 | Gaidongari | Akshay Khemraj Tidake | 44,07,617 | 03-10-2022 | 16 Months | 53.82% | 43.94% | 19.37
2 | Rampuri | Avinash Maske | 32,88,054 |  |  | 48.10% | 41.42% | 13.62
3 | Kalamgaon | Shri. Asit Adhir Mandal | 68,33,534 | 01-11-2022 | 20 Months | 36.94% | 32.13% | 21.96
4 | Surbodi | Tirupati Construction | 63,52,256 | 24-01-2023 | 16 Months | 31.55% | 22.31% | 14.17
5 | Parsodi | Shri. Chetan Vinod Chandragiriwar | 33,94,105 | 28-09-2022 | 16 Months | 30.55% | - | -
6 | Navegaon Khurd | Aarohi Solutions | 58,37,770 | 03-10-2022 | 16 Months | 22.01% | - | -
7 | Kharbi (Khedmakta) | Akshay Khemraj Tidke | 37,64,208 | 13-12-2022 | 14 Months | 19.06% | 16.09% | 6.06
8 | Maher | Akshay Khemraj Tidake | 38,25,969 | 13-12-2022 | 14 Months | 19.04% | 16.44% | 6.29
9 | Parsodi Jani | Shri. Chetan Vinod Chandragiriwar | 25,00,019 | 28-09-2022 | 14 Months | 15.75% | 10.07% | 2.52
10 | Saighata | Arvind Vinayak Mahajan | 51,54,640 | 13-01-2023 | 16 Months | 14.01% | 13.30% | 6.86
11 | Uchali & Kaleta | Shri. Vilas Sontakke | 1,35,52,548 | 01-11-2022 | 20 Months | 11.53% | - | -
12 | Kothulna | Akshya Khemraj Tidke | 57,67,817 | 31-01-2023 | 16 Months | 7.44% | - | -
13 | Bhaleshwar | Akshay Tikde | 68,94,325 | 17-01-2023 | 16 Months | 6.91% | - | -

## Slide 18: Abstract of Schemes – Work in Progress Category – “New”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
14 | Brlgaon Kh & Murpar | Shri. Shrikant Gopalji Jayaswal | 1,20,81,282 | 17-01-2023 | 17 Months | 6.87% | - | -
15 | Powanpar | Shri. Roshan Bhagvan Navghade | 46,20,061 | 27-01-2023 | 14 Months | 6.51% | - | -
16 | Saygaon | Shri Avinash Murlidhar Maske | 55,43,798 | 07-11-2022 | 16 Months | 4.21% | - | -
17 | Chikalgaon | Prashant Ramchandre Ramteke | 1,10,38,716 | 13-12-2022 | 16 Months | 4.09% | - | -
18 | Gawarla | Shri. Roshan Navghade | 29,91,364 | 27-01-2023 | 14 Months | 3.20% | - | -
19 | Borgaon | Shri. Avinash Murlidhar Maske | 71,05,826 | 01-11-2022 | 20 Months | 2.55% | - | -
20 | Kosambi Khadasmara | Shri Amol Mahadav Sukare | 74,19,672 | 06-06-2022 | 20 Months | 2.29% | - | -
21 | Belgaon | Tirupati Construction | 1,10,99,639 | 21-01-2023 | 16 Months | 1.30% | - | -
22 | Kothunlna | Shri. Akshya Khemraj Tidke | 57,67,817 | 31-01-2023 | 16 Months | 0.53% | - | -
23 | Bhagwanpur | Shri. Amol Mahadev Sukare | 61,17,370 | 31-01-2023 | 16 Months | 0.50% | - | -
24 | Boddegaon | Shri. Saurabh Rameshvar Bhandarkar | 74,54,171 | 31-01-2023 | 16 Months | 0.48% | - | -
25 | Ganeshpur & Chichkheda | Me. Gori Construction | 1,48,26,922 | 31-01-2023 | 16 Months | 0.23% | - | -
26 | Sawalgaon | Pritam Ganeshwar Ashutakar | 1,43,59,887 | 30-01-2023 | 16 Months | 0.21% | - | -

## Slide 19: Abstract of Schemes – Work in Progress Category – “New”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
Chimur Taluka |  |  |  |  |  |  |  | 
27 | Umri Buti | Pargya Dayaram Ramteke | 18,80,487 | 05-12-2022 | 12 Months | 49.75% | 37.08% | 6.97
28 | Navegaon Bramhan | Shri. Savapnil Kumar Raut | 46,63,438 | 27-01-2023 | 14 Months | 14.56% | 12.78% | 5.96
29 | Jamani | Milind Raut |  |  |  | 12.57% | - | -
30 | Chiklpar | Mayur Baburao Gajbhey | 21,60,695 | 09-12-2022 | 14 Months | 3.67% | - | -
31 | Pandharpauni | Shri Partik Shribharos Dhok | 26,08,685 | 22-11-2022 | 14 Months | 3.27% | - | -
32 | Umri Butti | Pradnya Dayaram Ramteke | 18,80,487 | 05-12-2021 | 12 Months | 3.11% | - | -
33 | Kaparla (Kh) & (Bk) | Shri Sumit Sunil Bisvas | 42,72,637 | 06-07-2022 | 18 Months | 3.02% | - | -
34 | Kalamgaon Neri | Shri Savpnilkumar Harishchand Raut | 30,44,204 | 24-01-2023 | 14 Months | 0.75% | - | -
35 | Khapari (Dak Bangla) | Aniket Khanke |  |  |  | 0.51% | - | -
Mul Taluka |  |  |  |  |  |  |  | 
36 | Bhejgaon | Shri. Ankush Arun Wargantiwar | 1,45,86,700 | 14-11-2022 | 18 Months | 19.71% | 12.26% | 17.88
37 | Tadbhuj | Shri. Dhanjay Kesavrao Barde | 27,87,058 | 31-01-2023 | 14 Months | 2.52% | - | -
38 | Shivapur | Shri K.M. Dev | 76,90,301 | 17-01-2023 | 16 Months | 0.94% | - | -
39 | Golabhuj | Shri. Rajat Anil Mungelwar | 44,73,816 | 17-01-2023 | 14 Months | 0.69% | - | -

## Slide 20: Abstract of Schemes – Work in Progress Category – “New”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
Nagbid Taluka |  |  |  |  |  |  |  | 
40 | Umargaon | Milind Ramesh Gahane | 22,65,376 | 10-03-2022 | 16 Months | 11.42% | - | -
41 | Bond Nawanagar & Rajoli | Shri A,S. Dange | 96,63,842 | 23-01-2023 | 16 Months | 8.07% | - | -
42 | Mindala | Shri Rajendra Devrao Kannamwar | 58,06,990 | 01-08-2022 | 18 Months | 7.25% | 6.69% | 3.88
43 | Dhamangaon 1 | Malatai Anandrao Khardiwar | 24,14,484 | 12-08-2022 | 12 Months | 4.74% | - | -
44 | Pardi Jatin | Me. Trimurti Construction | 38,77,799 | 31-01-2023 | 14 Months | 0.65% | - | -
45 | Ranparsodi | Me. Ajay Nanaji Chafle | 61,76,988 | 31-01-2023 | 16 Months | 0.57% | - | -
Sawali Taluka |  |  |  |  |  |  |  | 
46 | Pardi | Ankush Arun Wargantiwar | 74,90,662 | 20-04-2022 | 24 Months | 34.24% | - | -
47 | Saikheda | Shri. Asit Adhir Mandal | 74,67,488 | 13-01-2023 | 16 Months | 18.55% | - | -
48 | Mangarmendha & Meha Kh | Shri. Asit Adhir Mandal | 75,02,331 | 17-01-2023 | 16 Months | 18.23% | 15.47% | 11.61
49 | Navegaon | Shri. Asit Adhir Mandal | 74,22,520 | 17-01-2023 | 16 Months | 4.53% | - | -
50 | Bormala | Me. Pavar Construction | 1,16,21,962 | 31-01-2023 | 16 Months | 3.59% | - | -
51 | Dabgaon Chak | Shri. Asit Adhir Mandal | 2,46,26,612 | 31-01-2023 | 16 Months | 3.27% | - | -

## Slide 21: Abstract of Schemes – Work in Progress Category – “New”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
52 | Dongargaon Mhaske | Shri. Ankush Wargantiwar | 1,12,67,559 | 17-01-2023 | 16 Months | 1.57% | - | -
53 | Chkhali&Barsagad | Shri. Asit Adhir Mandal | 83,52,953 | 17-01-2023 | 16 Months | 1.00% | - | -
54 | Usarpar Chak & Usapar Tukum | Me. Pavar Construction | 1,37,38,881 | 31-01-2023 | 16 Months | 0.72% | - | -
55 | Janakapur Tukum | Rajendra Devraoji Kananvar | 55,86,391 | 31-01-2023 | 12 Months | 0.55% | - | -
56 | Janakpur Tuikum | Shri. Parsent Pudlik Baagre | 31,10,630 | 31-01-2023 | 12 Months | 0.49% | - | -
57 | Gaydongari | Me. Pavar Construstion | 67,64,854 | 27-01-2023 | 16 Months | 0.47% | - | -
58 | Karoli | Me Pavar Construction | 93,69,985 | 31-01-2023 | 16 Months | 0.33% | - | -
59 | Jamkeroda&Pethgaon | Shrikant Jayaswal | 1,33,63,618 | 16-01-2023 | 16 Months | 0.23% | - | -
Sindewahi Taluka |  |  |  |  |  |  |  | 
60 | Mohobodi | Shri Lakhan Pawar | 28,34,351 | 23-01-2023 | 14 Months | 20.26% | 17.72% | 5.02
61 | Kukkaddheti | Shri. Shrikant Gopal Jayaswal | 44,19,622 | 27-01-2023 | 14 Months | 13.46% | - | -
62 | Jatlapur (Mota) | Maa. Laxmi Construction Gunjhewahi | 45,57,837 | 31-01-2023 | 14 Months | 12.30% | - | -
63 | Bamani Chak | Me. Maa Laxmi Construction Gujewahi | 36,34,255 | 31-01-2023 | 14 Months | 9.69% | - | -
64 | Khairi Chak | Maa. Laxmi Construction Gunjhewahi | 47,76,794 | 31-01-2023 | 14 Months | 8.75% | - | -

## Slide 22: Abstract of Schemes – Work in Progress Category – “New”
Sr No | Scheme Name | Name of Agency | W.O. Amount (excl GST) | W.O. Date | Construction Period | Physical Progress | RA Bill (Recommended) % | RA Bill (Recommended) In Lakhs
65 | Murpar | Shri. Kishor Parbhudas Ghadse | 54,04,469 | 31-01-2023 | 16 Months | 8.27% | - | -
66 | Gadmaushi Chak | Shri. Asit Adhir Mandal | 64,29,883 | 21-12-2022 | 16 Months | 5.64% | - | -
67 | Alesur & Alesur Chak | Shri. Shrikant Gopal Jayaswal | 1,17,83,360 | 27-01-2023 | 16 Months | 4.53% | - | -
68 | Chargaon Bagde | Omkar Construction | 66,95,808 | 13-01-2023 | 16 Months | 3.98% | - | -
69 | Kacchepar | Shrikant Gopal Jaiswal | 87,24,388 | 25-01-2023 | 16 Months | 3.79% | - | -
70 | Bamani Mal | Me. Maa Laxmi Construction Gunjhewahi | 31,61,783 | 31-01-2023 | 14 Months | 3.05% | - | -
71 | Sawargatha | Shri. Asit Adhir Mandal | 54,09,891 | 21-12-2022 | 16 Months | 0.85% | - | -
72 | Ghot | Shri. Asit Adhir Mandal | 54,74,520 | 13-01-2023 | 16 Months | 0.56% | - | -
73 | Kalamgaon Ganna | Asit Adhir Mondal | 71,19,116 | 28-09-2022 | 20 Months | 0.41% | - | -
74 | Naleshwar | Shrikant Jayaswal | 88,49,965 | 16-01-2023 | 16 Months | 0.40% | - | -
75 | Wasera | Shrikant Gopal Jaiswal | 1,73,93,105 | 25-01-2023 | 16 Months | 0.20% | - | -
Warora Taluka |  |  |  |  |  |  |  | 
76 | Gaul Kh | Shri. Akshya Ashok Daf | 48,97,375 | 30-01-2023 | 14 Months | 11.78% | - | -

## Slide 23
DASHBOARD

## Slide 24
Work Status
Dashboard

## Slide 25
Dashboard
Progress Milestone

## Slide 26
Work Status: Taluka Wise
Work Status:
Dashboard

## Slide 27
MS – PROJECT
Work in Progress Schemes

## Slide 28
Project Overview Physical Progress vs Financial Progress vs Time Overrun

## Slide 29
Late Schemes

## Slide 30
SAMPLE SITE VISIT PHOTOS

## Slide 31
, Tal.

## Slide 32
Thank You!